## Project Detail 042517
Line Number | Project Name | Project Number | Project Name | Asset Managing Department | Contract Type | Estimated Construction Contract Cost | Estimated Total Project Cost | Fiscal Year Advertising | Quarter Advertising | Award Status | NEW
1 | City Heights Rec Center Improvements | B17040 | City Heights Rec Center Improvements | Environmental Services | Multiple Award Construction Contract | 400000 | 460000 | 2017 | Q4 | On Schedule | NEW
2 | Martin Luther King Jr. Rec Center Improvements | B17037 | Martin Luther King Jr. Rec Center Improvements | Environmental Services | Multiple Award Construction Contract | 400000 | 460000 | 2017 | Q4 | On Schedule | NEW
3 | Southeastern Division Police Sub-Station Improvements | B17038 | Southeastern Division Police Sub-Station Improvements | Environmental Services | Multiple Award Construction Contract | 400000 | 460000 | 2017 | Q4 | On Schedule | NEW
4 | Mid City Division Police Sub-Station Improvements | B17039 | Mid City Division Police Sub-Station Improvements | Environmental Services | Multiple Award Construction Contract | 400000 | 460000 | 2017 | Q4 | On Schedule | NEW
5 | Fire Station 14 Roof & HVAC Replacement | B13189 | Fire Station 14 Roof & HVAC Replacement | Fire-Rescue | Design Bid Build | 689841 | 1027000 | 2017 | Q2 | On Schedule
6 | Fire Station 19 Roof & HVAC Replacement | B13190 | Fire Station 19 Roof & HVAC Replacement | Fire-Rescue | Design Bid Build | 577964 | 936000 | 2017 | Q2 | On Schedule
7 | North University City Fire Station 50 | S13021 | North University City Fire Station 50 | Fire-Rescue | Design Build | 8042000 | 14000000 | 2017 | Q4 | On Schedule | NEW
8 | La Jolla Children's Pool Lifeguard Station | S00644 | La Jolla Children's Pool Lifeguard Station | Fire-Rescue | Design Bid Build | 50196 | 60235 | 2017 | Q3 | Awarded | NEW
9 | SAN YSIDRO BRANCH LIBRARY | S00802 | SAN YSIDRO BRANCH LIBRARY | Library | Design Build | 10300000 | 12827000 | 2017 | Q1 | Awarded
10 | Mission Hills - Hillcrest Library | S13022 | Mission Hills - Hillcrest Library | Library | Design Build | 17794327 | 17847523 | 2016 | Q4 | Awarded
11 | Balboa Park GC Fuel Tank Installation | B12019 | Balboa Park GC Fuel Tank Installation | Park & Recreation | Design Bid Build | 370000 | 445405 | 2017 | Q4 | On Schedule
12 | Cesar Solis Community Park | S00649 | Cesar Solis Community Park | Park & Recreation | Design Bid Build | 14997000 | 16800000 | 2016 | Q4 | Awarded
13 | Torrey Meadows Neighborhood Park | S00651 | Torrey Meadows Neighborhood Park | Park & Recreation | Design Bid Build | 3365750 | 7922755 | 2016 | Q3 | Awarded
14 | Chicano Park ADA Upgrades | S13003 | Chicano Park ADA Upgrades | Park & Recreation | Design Bid Build | 957221 | 1410893 | 2017 | Q2 | Awarded
15 | Evans Pond Reclaimed Water Pipeline Inst | S13010 | Evans Pond Reclaimed Water Pipeline Inst | Park & Recreation | Design Bid Build | 307968 | 427468 | 2017 | Q3 | On Schedule
16 | Chollas Lake Pk Playground Improvements | S14002 | Chollas Lake Pk Playground Improvements | Park & Recreation | Design Bid Build | 1181807 | 1739000 | 2017 | Q4 | On Schedule
17 | Mid City Skate Park-Park de la Cruz Neighborhood Park Improv | S15003 | Mid City Skate Park-Park de la Cruz Neighborhood Park Improv | Park & Recreation | Design Bid Build | 3409940 | 5094000 | 2016 | Q4 | Awarded
18 | San Ysidro Community Pk ADA Improvements | S15033 | San Ysidro Community Pk ADA Improvements | Park & Recreation | Design Bid Build | 587043 | 870000 | 2017 | Q2 | Awarded
19 | University Village Park Tot Lot | S13005 | University Village Park Tot Lot | Park & Recreation | Design Bid Build | 389697 | 545253 | 2016 | Q4 | Awarded
20 | Linda Vista Skate Park | S15008 | Linda Vista Skate Park | Park & Recreation | Design Bid Build | 2986000 | 3744995 | 2016 | Q4 | Awarded | NEW
21 | Del Mar Mesa Neighborhood Park Phase II | S13023 | Del Mar Mesa Neighborhood Park Phase II | Park & Recreation | Design Bid Build | 1526569 | 2226964 | 2016 | Q4 | Awarded | NEW
22 | Kelly St Neighborhood Pk Security Lighting Upgrade | S16016 | Kelly St Neighborhood Pk Security Lighting Upgrade | Park & Recreation | Design Bid Build | 85000 | 150000 | 2017 | Q4 | On Schedule | NEW
23 | Encanto Community Pk Security Lighting Upgrade | S16017 | Encanto Community Pk Security Lighting Upgrade | Park & Recreation | Design Bid Build | 239560 | 404560 | 2017 | Q4 | On Schedule | NEW
24 | Marie Widman Memorial Pk Sec Lighting | S16018 | Marie Widman Memorial Pk Sec Lighting | Park & Recreation | Design Bid Build | 175000 | 300000 | 2017 | Q4 | On Schedule | NEW
25 | Skyline Hills Community Pk Security Lighting Upgrade | S16021 | Skyline Hills Community Pk Security Lighting Upgrade | Park & Recreation | Design Bid Build | 85000 | 150000 | 2017 | Q4 | On Schedule | NEW
26 | Silver Wing Pk Ballfield Lighting - Ph 2 | S16051 | Silver Wing Pk Ballfield Lighting - Ph 2 | Park & Recreation | Design Bid Build | 858139 | 1138617 | 2017 | Q1 | On Schedule | NEW
27 | Balboa Park Plaza de Panama | L17002 | Balboa Park Plaza de Panama | Park & Recreation | Design Bid Build | 60038145 | 78108614 | 2017 | Q4 | On Schedule | NEW
28 | Larsen Field ADA Improvements Phase II | S13004 | Larsen Field ADA Improvements Phase II | Park & Recreation | Design Bid Build | 1099123 | 1689000 | 2016 | Q3 | Awarded
29 | Southcrest Trails Neighborhood Park | S01071 | Southcrest Trails Neighborhood Park | Park & Recreation | Design Bid Build | 1659956 | 1717580 | 2017 | Q3 | Awarded | NEW
30 | Old Fire Station 29 Demolition & Temporary Park Improvements | BM1000003-16 | Old Fire Station 29 Demolition & Temporary Park Improvements | Park & Recreation | Design Bid Build | 397953 | 750000 | 2017 | Q3 | Awarded | NEW
31 | Police Range Refurbishment | S10118 | Police Range Refurbishment | Police | Design Bid Build | 846718 | 1078000 | 2016 | Q4 | Awarded
32 | Police HQ Co-Generation Repower Project Phase II | S10131 | Police HQ Co-Generation Repower Project Phase II | Police | Design Bid Build | 922134 | 1854653 | 2016 | Q4 | Awarded
33 | Sewer & AC Water Group 764A (S) | B00380 | Sewer & AC Water Group 764A (S) | Public Utilities | Design Bid Build | 2691518 | 4112092 | 2017 | Q2 | On Schedule
34 | Sewer & AC Water Group Job 776 (S) | B00387 | Sewer & AC Water Group Job 776 (S) | Public Utilities | Design Bid Build | 5912086 | 8495523 | 2017 | Q2 | Awarded
35 | Sewer Group 818 | B00414 | Sewer Group 818 | Public Utilities | Design Bid Build | 1987864 | 3330921 | 2017 | Q2 | Awarded
36 | SPS 13 14 16 25A & 85 Dual FM | B00501 | SPS 13 14 16 25A & 85 Dual FM | Public Utilities | Design Bid Build | 3095480 | 3646480 | 2017 | Q4 | On Schedule
37 | La Jolla Country Club Reservoir | B11024 | La Jolla Country Club Reservoir | Public Utilities | Design Bid Build | 5215000 | 8505000 | 2017 | Q3 | On Schedule
38 | Water Group Job 952 | B11048 | Water Group Job 952 | Public Utilities | Design Bid Build | 2952000 | 4082681 | 2017 | Q4 | On Schedule
39 | CI - Water and Sewer Group Job 966 (W) | B12086 | CI - Water and Sewer Group Job 966 (W) | Public Utilities | Design Bid Build | 1447100 | 2122400 | 2018 | Q1 | On Schedule
40 | Tyrian St/Soledad Ave Sewer Main Replace | B12111 | Tyrian St/Soledad Ave Sewer Main Replace | Public Utilities | Design Bid Build | 643536 | 1346500 | 2016 | Q3 | Awarded
41 | Sewer Group 835 | B13157 | Sewer Group 835 | Public Utilities | Design Bid Build | 2501955 | 3741840 | 2017 | Q1 | Awarded
42 | Water and Sewer GJ 955 (W) | B13186 | Water and Sewer GJ 955 (W) | Public Utilities | Design Bid Build | 2719392 | 3973952 | 2017 | Q2 | On Schedule
43 | Sewer & AC Water Group 776 (W) | B13197 | Sewer & AC Water Group 776 (W) | Public Utilities | Design Bid Build | 1787914 | 2678464 | 2017 | Q2 | Awarded
44 | Sewer & AC Water Group 764A (W) | B13201 | Sewer & AC Water Group 764A (W) | Public Utilities | Design Bid Build | 1212402 | 1767738 | 2017 | Q2 | On Schedule
45 | Sewer and AC Water Group 837 (S) | B13214 | Sewer and AC Water Group 837 (S) | Public Utilities | Design Bid Build | 1452000 | 2206461 | 2017 | Q3 | Awarded
46 | Pipeline Rehabilitation AE-1 | B14030 | Pipeline Rehabilitation AE-1 | Public Utilities | Design Bid Build | 4394017 | 6988558 | 2017 | Q2 | Awarded
47 | S Mission Valley TS Accelerated Project | B14068 | S Mission Valley TS Accelerated Project | Public Utilities | Design Bid Build | 378659 | 600000 | 2016 | Q4 | Awarded
48 | Water and Sewer Group 955 (S) | B14069 | Water and Sewer Group 955 (S) | Public Utilities | Design Bid Build | 504300 | 738700 | 2017 | Q2 | On Schedule
49 | Water Group 969 | B14100 | Water Group 969 | Public Utilities | Design Bid Build | 1000000 | 1686100 | 2017 | Q4 | On Schedule
50 | SPS 23T - Reliability Improvements | B14131 | SPS 23T - Reliability Improvements | Public Utilities | Design Bid Build | 1400000 | 1911000 | 2017 | Q4 | On Schedule
51 | SPS 76 Generator | B14168 | SPS 76 Generator | Public Utilities | Design Bid Build | 41500 | 75000 | 2017 | Q4 | On Schedule
52 | AC Water & Sewer Group 1011 (S) | B15040 | AC Water & Sewer Group 1011 (S) | Public Utilities | Design Bid Build | 750000 | 977500 | 2017 | Q4 | On Schedule
53 | AC Water & Sewer Group 1011 (W) | B15041 | AC Water & Sewer Group 1011 (W) | Public Utilities | Design Bid Build | 6899000 | 8295950 | 2017 | Q4 | On Schedule
54 | Sewer and AC Water Group 837 (W) | B15071 | Sewer and AC Water Group 837 (W) | Public Utilities | Design Bid Build | 1418901 | 2249851 | 2017 | Q3 | Awarded
55 | AC Water & Sewer Group 1017 (S) | B15116 | AC Water & Sewer Group 1017 (S) | Public Utilities | Design Bid Build | 79373 | 188442 | 2017 | Q3 | On Schedule
56 | AC Water & Sewer Group 1017 (W) | B15119 | AC Water & Sewer Group 1017 (W) | Public Utilities | Design Bid Build | 5745671 | 7924255 | 2017 | Q3 | On Schedule
57 | Otay Valley Manhole Improvements Phase 3 | B15123 | Otay Valley Manhole Improvements Phase 3 | Public Utilities | Design Bid Build | 310369 | 406250 | 2016 | Q4 | Awarded
58 | AC Water and Sewer Group 1029 (S) | B15172 | AC Water and Sewer Group 1029 (S) | Public Utilities | Multiple Award Construction Contract | 995000 | 1326000 | 2017 | Q1 | On Schedule
59 | AC Water and Sewer Group 1029 (W) | B15174 | AC Water and Sewer Group 1029 (W) | Public Utilities | Multiple Award Construction Contract | 5140000 | 6854000 | 2017 | Q1 | On Schedule
60 | Pipeline Rehabilitation AI-1 | B15187 | Pipeline Rehabilitation AI-1 | Public Utilities | Design Bid Build | 4256683 | 4986045 | 2017 | Q1 | Awarded
61 | Pipeline Rehabilitation AJ-1 | B15201 | Pipeline Rehabilitation AJ-1 | Public Utilities | Design Bid Build | 4092518 | 4898092 | 2017 | Q1 | Awarded
62 | Remaining Small Diameter CI Water Ph I | B15206 | Remaining Small Diameter CI Water Ph I | Public Utilities | Design Bid Build | 2474500 | 3518500 | 2017 | Q4 | On Schedule
63 | Tyrian St/Soledad Ave & AC Wtr Main (W) | B15216 | Tyrian St/Soledad Ave & AC Wtr Main (W) | Public Utilities | Design Bid Build | 770364 | 982000 | 2016 | Q3 | Awarded
64 | Pipeline Rehabilitation AM-1 | B16002 | Pipeline Rehabilitation AM-1 | Public Utilities | Design Bid Build | 4664125 | 6075331 | 2017 | Q1 | Awarded
65 | PS2 Power Reliability & Surge Protection | S00312 | PS2 Power Reliability & Surge Protection | Public Utilities | Design Bid Build | 56228000 | 72100800 | 2017 | Q1 | On Schedule
66 | WDSU - Reservoirs & Dams - Ph II | S11106 | WDSU - Reservoirs & Dams - Ph II | Public Utilities | Design Build | 10000000 | 12049028 | 2017 | Q4 | On Schedule
67 | 69th & Mohawk Pump Station | S12011 | 69th & Mohawk Pump Station | Public Utilities | Design Bid Build | 11000000 | 15088594 | 2017 | Q1 | On Schedule
68 | Tierrasanta (Via Dominique) Pump Station | S12040 | Tierrasanta (Via Dominique) Pump Station | Public Utilities | Design Bid Build | 10995000 | 14319186 | 2016 | Q4 | Awarded
69 | Chollas Building | S11025 | Chollas Building | Public Utilities | Design Build | 29585997 | 37856871 | 2016 | Q2 | Awarded
70 | MOC 5 Materials Bins | B14133 | MOC 5 Materials Bins | Public Utilities | Design Bid Build | 477045 | 760000 | 2017 | Q1 | Awarded
71 | SBWRP Loop Control System & Valve Master Station Improvements | B16132 | SBWRP Loop Control System & Valve Master Station Improvements | Public Utilities | Design Build | 724488 | 900000 | 2017 | Q3 | On Schedule
72 | Water & Sewer Group 965 (W) | B12057 | Water & Sewer Group 965 (W) | Public Utilities | Design Bid Build | 2463903 | 3199547 | 2017 | Q3 | On Schedule
73 | Water & Sewer Group 965 (S) | B12048 | Water & Sewer Group 965 (S) | Public Utilities | Design Bid Build | 2468103 | 3147585 | 2017 | Q3 | On Schedule
74 | Pipeline Rehabilitantion AG1 | B14118 | Pipeline Rehabilitantion AG1 | Public Utilities | Design Bid Build | 3360977 | 5434000 | 2017 | Q2 | Awarded
75 | Water and Sewer Group 954(S) | B13203 | Water and Sewer Group 954(S) | Public Utilities | Design Bid Build | 751367 | 971407 | 2016 | Q4 | Awarded
76 | Water and Sewer Group 954(W) | B10187 | Water and Sewer Group 954(W) | Public Utilities | Design Bid Build | 3005466 | 3763530 | 2016 | Q4 | Awarded
77 | Tecolote Canyon Sewer | B11111 | Tecolote Canyon Sewer | Public Utilities | Design Bid Build | 518000 | 1143662 | 2016 | Q3 | Awarded
78 | Sewer and Water Group 701 (S) | B00452 | Sewer and Water Group 701 (S) | Public Utilities | Design Bid Build | 3590850 | 5365000 | 2016 | Q3 | Awarded
79 | Sewer and Water Group 701 (W) | B00039 | Sewer and Water Group 701 (W) | Public Utilities | Design Bid Build | 751352 | 1037000 | 2016 | Q3 | Awarded
80 | AC Water Group 1018A | B16146 | AC Water Group 1018A | Public Utilities | Design Bid Build | 5796313 | 8371352 | 2017 | Q3 | On Schedule
81 | Otay 2nd Pipeline Phase 2 | B15046 | Otay 2nd Pipeline Phase 2 | Public Utilities | Design Build | 9170000 | 12227000 | 2017 | Q2 | On Schedule
82 | AC Woodman St. Pipeline Replacement | B15081 | AC Woodman St. Pipeline Replacement | Public Utilities | Design Build | 2126000 | 2834000 | 2017 | Q2 | On Schedule
83 | AC Water & Sewer Group 1025 (S) | B15082 | AC Water & Sewer Group 1025 (S) | Public Utilities | Design Bid Build | 185674 | 349899 | 2017 | Q3 | On Schedule | NEW
84 | AC Water & Sewer Group 1025 (W) | B15083 | AC Water & Sewer Group 1025 (W) | Public Utilities | Design Bid Build | 6546486 | 7872700 | 2017 | Q3 | On Schedule | NEW
85 | AC Water Group 1031 | B16036 | AC Water Group 1031 | Public Utilities | Design Bid Build | 3302113 | 4993958 | 2017 | Q2 | Awarded | NEW
86 | Priority Sewer Main Replacement Group 16 | B16018 | Priority Sewer Main Replacement Group 16 | Public Utilities | Multiple Award Construction Contract | 8336427 | 12592494 | 2017 | Q2 | On Schedule | NEW
87 | Bayview Reservoir Solar Project | S14021 | Bayview Reservoir Solar Project | Public Utilities | Design Build | 712893 | 2325000 | 2017 | Q1 | Awarded | NEW
88 | MOC Complex Solar Project | S14022 | MOC Complex Solar Project | Public Utilities | Design Build | 1894327 | 2675000 | 2017 | Q1 | Awarded | NEW
89 | Emergency Strobe Lights at MBC, NC, SB | B13227 | Emergency Strobe Lights at MBC, NC, SB | Public Utilities | Design Bid Build | 404996 | 768995 | 2017 | Q3 | On Schedule | NEW
90 | Stadium Wetland Mitigation | 21003814 | Stadium Wetland Mitigation | Public Utilities | Design Bid Build | 3741518 | 5044169.9 | 2016 | Q4 | Awarded | NEW
91 | SEWER and AC Water GROUP 764 (S) | B00368 | SEWER and AC Water GROUP 764 (S) | Public Utilities | Design Bid Build | 1530495 | 2334561 | 2017 | Q3 | On Schedule | NEW
92 | Sewer & AC Water Group 821(S) | B00413 | Sewer & AC Water Group 821(S) | Public Utilities | Design Bid Build | 1855652 | 2863267 | 2017 | Q3 | On Schedule | NEW
93 | SEWER and AC Water GROUP 764 (W) | B15106 | SEWER and AC Water GROUP 764 (W) | Public Utilities | Design Bid Build | 1592964 | 2257713 | 2017 | Q3 | On Schedule | NEW
94 | Sewer & AC Water Group 821 (W) | B15107 | Sewer & AC Water Group 821 (W) | Public Utilities | Design Bid Build | 1396302 | 1908824 | 2017 | Q3 | On Schedule | NEW
95 | Bay Bridge Community Center ADA | B13076 | Bay Bridge Community Center ADA | Public Works - General Services | Design Bid Build | 331858 | 608000 | 2016 | Q4 | Awarded
96 | SY Comm and Rec CTR-ADA Barrier Removal | B13078 | SY Comm and Rec CTR-ADA Barrier Removal | Public Works - General Services | Design Bid Build | 761991 | 1240000 | 2016 | Q4 | Awarded
97 | Carmel Valley Rec Ctr ADA Access Impr | B14152 | Carmel Valley Rec Ctr ADA Access Impr | Public Works - General Services | Design Bid Build | 470000 | 673000 | 2017 | Q1 | On Schedule
98 | Carmel Creek Park Comft St ADA Access Im | B14153 | Carmel Creek Park Comft St ADA Access Im | Public Works - General Services | Design Bid Build | 159185 | 234000 | 2017 | Q2 | On Schedule
99 | Carmel Del Mar Comft St ADA Access Impro | B14154 | Carmel Del Mar Comft St ADA Access Impro | Public Works - General Services | Design Bid Build | 317200 | 431000 | 2017 | Q1 | On Schedule
100 | ADA Accessibility Improvements Group I | B15222 | ADA Accessibility Improvements Group I | Public Works - General Services | Design Build | 1318553 | 2175756 | 2017 | Q3 | On Schedule
101 | ADA Accessibility Improvements Group II | B15229 | ADA Accessibility Improvements Group II | Public Works - General Services | Design Build | 1107447 | 1968629 | 2017 | Q2 | On Schedule
102 | ADA Accessibility Improvements Group IV | B15230 | ADA Accessibility Improvements Group IV | Public Works - General Services | Design Bid Build | 411950 | 620000 | 2017 | Q2 | On Schedule
103 | Colina Del Sol Pool ADA | B13077 | Colina Del Sol Pool ADA | Public Works - General Services | Design Bid Build | 443823 | 836477 | 2016 | Q2 | Awarded
104 | Pioneer Park and Comfort Station | B12005 | Pioneer Park and Comfort Station | Public Works - General Services | Design Build | 201002 | 535086 | 2016 | Q3 | Awarded | NEW
105 | Memorial Park Community Building Clearance Activity | S15039 | Memorial Park Community Building Clearance Activity | Public Works - General Services | Design Bid Build | 370527 | 426106 | 2017 | Q1 | Awarded | NEW
106 | Barrio Youth Facilities 2 & 3 | B13067 | Barrio Youth Facilities 2 & 3 | Public Works - General Services | Design Bid Build | 546267 | 967371 | 2016 | Q3 | Awarded | NEW
107 | City Heights Youth & Community Center AD | B13068 | City Heights Youth & Community Center AD | Public Works - General Services | Design Bid Build | 284678 | 563962 | 2016 | Q1 | Awarded | NEW
108 | Marston House Roof Replacement | B16038 | Marston House Roof Replacement | Public Works - General Services | Design Bid Build | 385000 | 462000 | 2016 | Q2 | Awarded | NEW
109 | Carmel Mountain Library Roof Replacement | B16043 | Carmel Mountain Library Roof Replacement | Public Works - General Services | Design Bid Build | 530000 | 651562 | 2016 | Q2 | Awarded | NEW
110 | ADA Imp & Exp of Paradise Senior Center | S15002 | ADA Imp & Exp of Paradise Senior Center | Public Works - General Services | Design Bid Build | 295000 | 700000 | 2017 | Q2 | On Schedule | NEW
111 | Pacific Beach Library Roof & HVAC | B16045 | Pacific Beach Library Roof & HVAC | Public Works - General Services | Design Build | 1701850 | 1830480 | 2017 | Q2 | On Schedule | NEW
112 | Tierrasanta Rec Center Roof & HVAC | B16046 | Tierrasanta Rec Center Roof & HVAC | Public Works - General Services | Design Build | 930852 | 1000000 | 2017 | Q2 | On Schedule | NEW
113 | Beta Street and 37th Street Green Alley | B11057 | Beta Street and 37th Street Green Alley | Transportation & Storm Water | Design Bid Build | 537048 | 786959 | 2017 | Q1 | Awarded
114 | Bonillo Dr (4150) Storm Drain Replace | B12033 | Bonillo Dr (4150) Storm Drain Replace | Transportation & Storm Water | Design Bid Build | 223045 | 497045 | 2016 | Q3 | Awarded
115 | Camino del Este Path Xing Improvements | B13088 | Camino del Este Path Xing Improvements | Transportation & Storm Water | Design Bid Build | 302542 | 449640 | 2017 | Q4 | On Schedule
116 | Burroughs & W Dunlop Sts Storm Dr Repl | B13101 | Burroughs & W Dunlop Sts Storm Dr Repl | Transportation & Storm Water | Design Bid Build | 443824 | 878733 | 2017 | Q1 | Awarded
117 | El Cajon & 59th Obstruction DIF CR DS | B13105 | El Cajon & 59th Obstruction DIF CR DS | Transportation & Storm Water | Design Bid Build | 202133 | 324833 | 2016 | Q4 | Awarded
118 | Southeastern Obstruction DIF 13 CR | B13106 | Southeastern Obstruction DIF 13 CR | Transportation & Storm Water | Design Bid Build | 62735 | 240800 | 2016 | Q4 | Awarded
119 | Group Job 13I North Park DIF CR | B13111 | Group Job 13I North Park DIF CR | Transportation & Storm Water | Design Bid Build | 125235 | 474500 | 2017 | Q2 | Awarded
120 | Group Job 13J Peninsula DIF CR | B13112 | Group Job 13J Peninsula DIF CR | Transportation & Storm Water | Design Bid Build | 385203 | 737500 | 2016 | Q4 | Awarded
121 | Sunset Cliffs 3 SL Circuit Upgrade | B13141 | Sunset Cliffs 3 SL Circuit Upgrade | Transportation & Storm Water | Design Bid Build | 643138 | 943500 | 2017 | Q2 | Awarded
122 | Whitney Ct (6969) Storm Drain Replacement | B13210 | Whitney Ct (6969) Storm Drain Replacement | Transportation & Storm Water | Design Bid Build | 227150 | 681695 | 2017 | Q2 | Awarded
123 | New Streetlights - 19 Locations | B14012 | New Streetlights - 19 Locations | Transportation & Storm Water | Design Bid Build | 275500 | 389200 | 2017 | Q1 | Awarded
124 | Bikeway Striping Improvements-Citywide | B14040 | Bikeway Striping Improvements-Citywide | Transportation & Storm Water | Design Bid Build | 1000 | 10000 | 2017 | Q3 | On Schedule
125 | Golden Hill CR Obstruction DIF 14 | B14052 | Golden Hill CR Obstruction DIF 14 | Transportation & Storm Water | Design Bid Build | 107628 | 250500 | 2017 | Q1 | Awarded
126 | City Street Lights - 25 Locations | B14106 | City Street Lights - 25 Locations | Transportation & Storm Water | Design Bid Build | 220600 | 275300 | 2016 | Q4 | Awarded
127 | Alamo, Salvation, 68th Street Basins LID | B14120 | Alamo, Salvation, 68th Street Basins LID | Transportation & Storm Water | Design Bid Build | 2174000 | 3000000 | 2017 | Q4 | On Schedule
128 | Division St @ Valencia Pky TS | B15008 | Division St @ Valencia Pky TS | Transportation & Storm Water | Design Bid Build | 206155 | 275000 | 2017 | Q4 | On Schedule
129 | Guardrail Projects Group 1501 | B15224 | Guardrail Projects Group 1501 | Transportation & Storm Water | Design Bid Build | 64980 | 242000 | 2017 | Q2 | Awarded
130 | Euclid Ave & Home Improvements | S00886 | Euclid Ave & Home Improvements | Transportation & Storm Water | Design Bid Build | 60000 | 985820 | 2017 | Q1 | On Schedule
131 | La Jolla Mesa Drive Sidewalk | S00928 | La Jolla Mesa Drive Sidewalk | Transportation & Storm Water | Design Bid Build | 574900 | 826000 | 2017 | Q3 | On Schedule
132 | Bikeway Striping Improvements-Citywide | S00955 | Bikeway Striping Improvements-Citywide | Transportation & Storm Water | Design Bid Build | 73500 | 97000 | 2017 | Q3 | On Schedule
133 | Trojan Ave 56th to 60th UUD | B00718 | Trojan Ave 56th to 60th UUD | Transportation & Storm Water | Design Bid Build | 44301 | 228825 | 2017 | Q3 | Awarded
134 | Sunset Cliffs Dr Coronado to Newport UUD | B00720 | Sunset Cliffs Dr Coronado to Newport UUD | Transportation & Storm Water | Design Bid Build | 256122 | 305771 | 2017 | Q3 | On Schedule
135 | Fanual Street Phase II Grand to Reed UUD | B00722 | Fanual Street Phase II Grand to Reed UUD | Transportation & Storm Water | Design Bid Build | 85813 | 180000 | 2017 | Q3 | Awarded
136 | San Vicente Street to Ashmore UUD | B00725 | San Vicente Street to Ashmore UUD | Transportation & Storm Water | Design Bid Build | 48100 | 187817 | 2017 | Q3 | Awarded
137 | San Vicente Street to Ashmore UUD | B00725 | San Vicente Street to Ashmore UUD | Transportation & Storm Water | Design Bid Build | 38312 | 149597 | 2017 | Q1 | Awarded | NEW
138 | Moraga Ave to Idelwild UUD | B00726 | Moraga Ave to Idelwild UUD | Transportation & Storm Water | Design Bid Build | 185896 | 304173 | 2017 | Q3 | On Schedule
139 | Moraga Ave Ph II -Moraga Ct to Monair UUD | B00788 | Moraga Ave Ph II -Moraga Ct to Monair UUD | Transportation & Storm Water | Design Bid Build | 189809 | 275450 | 2017 | Q3 | On Schedule
140 | District 1 Block 1-J UUD | B00836 | District 1 Block 1-J UUD | Transportation & Storm Water | Design Bid Build | 137536 | 161808 | 2017 | Q4 | On Schedule
141 | District 4 Block 4-Z UUD | B00838 | District 4 Block 4-Z UUD | Transportation & Storm Water | Design Bid Build | 445780 | 610768 | 2017 | Q3 | On Schedule
142 | District 7 Block 7-A UUD (Street Lighting only) | B00842 | District 7 Block 7-A UUD (Street Lighting only) | Transportation & Storm Water | Design Bid Build | 160000 | 192000 | 2017 | Q3 | Awarded | NEW
143 | Altadena/Wightman/Winona-El Cajon UUD | B00850 | Altadena/Wightman/Winona-El Cajon UUD | Transportation & Storm Water | Design Bid Build | 87196 | 277867 | 2017 | Q3 | Awarded
144 | Euclid Ave UUD Streetlights (Euclid-Univ) (Street Lighting only) | B11131 | Euclid Ave UUD Streetlights (Euclid-Univ) (Street Lighting only) | Transportation & Storm Water | Design Bid Build | 60000 | 72000 | 2017 | Q3 | Awarded | NEW
145 | Block 7R Allied Gardens UUD | B12064 | Block 7R Allied Gardens UUD | Transportation & Storm Water | Design Bid Build | 773955 | 1000355 | 2017 | Q3 | On Schedule
146 | Lincoln Av UUD (30th St-Wabash Av) | B12066 | Lincoln Av UUD (30th St-Wabash Av) | Transportation & Storm Water | Design Bid Build | 72250 | 85000 | 2017 | Q3 | On Schedule
147 | Potomac St UUD (Calle Tres Lomas-Sea Breeze) | B12069 | Potomac St UUD (Calle Tres Lomas-Sea Breeze) | Transportation & Storm Water | Design Bid Build | 210126 | 229625 | 2017 | Q3 | On Schedule
148 | 32nd Street UUD (Market St - F St) | B13144 | 32nd Street UUD (Market St - F St) | Transportation & Storm Water | Design Bid Build | 80750 | 95000 | 2017 | Q4 | On Schedule
149 | Cardiff Street UUD (Carlisle Dr - Wade St) | B13145 | Cardiff Street UUD (Carlisle Dr - Wade St) | Transportation & Storm Water | Design Bid Build | 52800 | 134000 | 2017 | Q1 | Awarded
150 | Howard Avenue UUD (Park Bl - I-805) | B13146 | Howard Avenue UUD (Park Bl - I-805) | Transportation & Storm Water | Design Bid Build | 342550 | 403000 | 2017 | Q4 | On Schedule
151 | Mount Alifan Dr UUD (Genesee Ave-Mt Everest Blvd) | B13148 | Mount Alifan Dr UUD (Genesee Ave-Mt Everest Blvd) | Transportation & Storm Water | Design Bid Build | 57753 | 153000 | 2017 | Q1 | Awarded
152 | Paradise Valley Rd UUD (Potomac St-Parkland Wy) | B13149 | Paradise Valley Rd UUD (Potomac St-Parkland Wy) | Transportation & Storm Water | Design Bid Build | 9800 | 104000 | 2017 | Q1 | Awarded
153 | 28th Street UUD (Island Av - Clay St) | B13156 | 28th Street UUD (Island Av - Clay St) | Transportation & Storm Water | Design Bid Build | 114500 | 176000 | 2017 | Q1 | Awarded
154 | 25th (SB) Street UUP (Coronado-SB to Grove) - 20A | B15088 | 25th (SB) Street UUP (Coronado-SB to Grove) - 20A | Transportation & Storm Water | Design Bid Build | 30600 | 36000 | 2017 | Q4 | On Schedule
155 | 32nd Street UUP (Market to Imperial) - 20A | B15089 | 32nd Street UUP (Market to Imperial) - 20A | Transportation & Storm Water | Design Bid Build | 61200 | 72000 | 2017 | Q4 | On Schedule
156 | Woodrow Ave UUP (Calvacado to Aemacost) - 20A | B15091 | Woodrow Ave UUP (Calvacado to Aemacost) - 20A | Transportation & Storm Water | Design Bid Build | 45498 | 54000 | 2017 | Q1 | Awarded
157 | Wightman Street UUP (Chamoune to Euclid) - 20A | B15092 | Wightman Street UUP (Chamoune to Euclid) - 20A | Transportation & Storm Water | Design Bid Build | 61200 | 72000 | 2017 | Q4 | On Schedule
158 | Seminole Drive UUP (Stanley to Estelle) - 20A | B15093 | Seminole Drive UUP (Stanley to Estelle) - 20A | Transportation & Storm Water | Design Bid Build | 38250 | 45000 | 2017 | Q4 | On Schedule
159 | Mission Blvd UUP (Loring to Tourquoise) - 20A | B15094 | Mission Blvd UUP (Loring to Tourquoise) - 20A | Transportation & Storm Water | Design Bid Build | 76500 | 90000 | 2017 | Q4 | On Schedule
160 | Hilltop Drive UUP (Boundary to Toyne) - 20A | B15095 | Hilltop Drive UUP (Boundary to Toyne) - 20A | Transportation & Storm Water | Design Bid Build | 107100 | 126000 | 2017 | Q4 | On Schedule
161 | Hancock Street UUP (Witherby to Tourquoise) - 20A | B15096 | Hancock Street UUP (Witherby to Tourquoise) - 20A | Transportation & Storm Water | Design Bid Build | 53550 | 63000 | 2017 | Q4 | On Schedule
162 | 30th Street Phase III Broadway to K UUD | B00717 | 30th Street Phase III Broadway to K UUD | Transportation & Storm Water | Design Bid Build | 286722 | 322882 | 2017 | Q3 | On Schedule
163 | Mission Village-Ronda to Qualcomm Sdwk | B15004 | Mission Village-Ronda to Qualcomm Sdwk | Transportation & Storm Water | Design Bid Build | 705100 | 1085000 | 2017 | Q4 | On Schedule
164 | Grove Ave/Ingrid Ave@Hollister St TS | B13179 | Grove Ave/Ingrid Ave@Hollister St TS | Transportation & Storm Water | Design Bid Build | 151187 | 349500 | 2017 | Q1 | Awarded
165 | 31st St @ Ocean View Bl Traffic Signal | B14014 | 31st St @ Ocean View Bl Traffic Signal | Transportation & Storm Water | Design Bid Build | 199041 | 260000 | 2017 | Q4 | On Schedule
166 | 41st St @ National Ave Traffic Signal | B14016 | 41st St @ National Ave Traffic Signal | Transportation & Storm Water | Design Bid Build | 173287 | 330000 | 2017 | Q2 | Awarded
167 | Campanile Dr & Montezuma Rd Signal Mod | B13134 | Campanile Dr & Montezuma Rd Signal Mod | Transportation & Storm Water | Design Bid Build | 118800 | 155200 | 2016 | Q4 | Awarded
168 | Callado Rd Green St Infiltration BMP | B13198 | Callado Rd Green St Infiltration BMP | Transportation & Storm Water | Design Bid Build | 1000000 | 1650000 | 2017 | Q4 | On Schedule
169 | 3rd Ave @ Washington St Traffic Signal | B14062 | 3rd Ave @ Washington St Traffic Signal | Transportation & Storm Water | Design Bid Build | 163787 | 395100 | 2017 | Q1 | Awarded
170 | Block 2S1 South Mission Beach UUD | B12067 | Block 2S1 South Mission Beach UUD | Transportation & Storm Water | Design Bid Build | 363800 | 428000 | 2017 | Q4 | On Schedule
171 | Illion Street UUD (Gardena Av - Milton St) | B13147 | Illion Street UUD (Gardena Av - Milton St) | Transportation & Storm Water | Design Bid Build | 44079 | 125000 | 2017 | Q1 | Awarded
172 | District 2 Block 2-T UUD | B00835 | District 2 Block 2-T UUD | Transportation & Storm Water | Design Bid Build | 1054787 | 2022709 | 2016 | Q4 | Awarded | NEW
173 | NATL Ave (32nd to 43rd) UUD | B00787 | NATL Ave (32nd to 43rd) UUD | Transportation & Storm Water | Design Bid Build | 589923 | 1315107 | 2016 | Q4 | Awarded | NEW
174 | 30th St PH 3A 20A | B00719 | 30th St PH 3A 20A | Transportation & Storm Water | Design Bid Build | 219008 | 540513 | 2016 | Q4 | Awarded | NEW
175 | District 4 Block 4AA UUD | B00826 | District 4 Block 4AA UUD | Transportation & Storm Water | Design Bid Build | 1264553 | 2503304 | 2016 | Q4 | Awarded | NEW
176 | District 2 Block 2-E UUD | B00709 | District 2 Block 2-E UUD | Transportation & Storm Water | Design Bid Build | 1270150 | 4622791 | 2016 | Q4 | Awarded | NEW
177 | Mission Hills/Presidio Circuit Upgrades | B15234 | Mission Hills/Presidio Circuit Upgrades | Transportation & Storm Water | Design Bid Build | 480000 | 480000 | 2016 | Q4 | Awarded | NEW
178 | District 8 Block 8-F UUD | B00714 | District 8 Block 8-F UUD | Transportation & Storm Water | Design Bid Build | 76770 | 92124 | 2016 | Q4 | Awarded | NEW
179 | Asphalt Overlay 1508 | B15181 | Asphalt Overlay 1508 | Transportation & Storm Water | Design Bid Build | 4840880 | 5000000 | 2016 | Q4 | Awarded | NEW
180 | State Route 163 Friars | S00851 | State Route 163 Friars | Transportation & Storm Water | Design Bid Build | 609852 | 658640 | 2017 | Q1 | Awarded | NEW
181 | Mission Gorge Road Settlement Emergency | B16181 | Mission Gorge Road Settlement Emergency | Transportation & Storm Water | Design Bid Build | 4500000 | 6000000 | 2017 | Q1 | Awarded | NEW
182 | Emergency Storm Channel Debris & Sediment Clearing at Smythe Channel Culverts | 12004365 | Emergency Storm Channel Debris & Sediment Clearing at Smythe Channel Culverts | Transportation & Storm Water | Design Bid Build | 750000 | 750000 | 2017 | Q1 | Awarded | NEW
183 | Flashing Crosswalks Group 1501 | B15017 | Flashing Crosswalks Group 1501 | Transportation & Storm Water | Design Bid Build | 263131 | 580000 | 2017 | Q1 | Awarded | NEW
184 | Ulric St - Fashion Hills to David St K-Rail | B13163 | Ulric St - Fashion Hills to David St K-Rail | Transportation & Storm Water | Design Bid Build | 683730 | 1018100 | 2017 | Q1 | Awarded | NEW
185 | El Cajon Blvd. Median Improvements | S00826 | El Cajon Blvd. Median Improvements | Transportation & Storm Water | Design Bid Build | 296347 | 500000 | 2017 | Q1 | Awarded | NEW
186 | 31st Street UUD (Market St - L St) | B13143 | 31st Street UUD (Market St - L St) | Transportation & Storm Water | Design Bid Build | 2281 | 18000 | 2017 | Q1 | Awarded | NEW
187 | Toyon Rd (5655) Storm Drain Replacement | B13117 | Toyon Rd (5655) Storm Drain Replacement | Transportation & Storm Water | Design Bid Build | 300675 | 650000 | 2017 | Q2 | Awarded | NEW
188 | AC Overlay Group 1511, JOC7 (Bond#3 + $100K) | B15183 | AC Overlay Group 1511, JOC7 (Bond#3 + $100K) | Transportation & Storm Water | Design Bid Build | 5000000 | 6000000 | 2017 | Q3 | On Schedule | NEW
189 | Concrete Street Panel Group 1501 | B15199 | Concrete Street Panel Group 1501 | Transportation & Storm Water | Design Bid Build | 2535505 | 3300000 | 2016 | Q4 | Awarded | NEW
190 | AC Overlay Street Paving Group 1601 | B16024 | AC Overlay Street Paving Group 1601 | Transportation & Storm Water | Design Bid Build | 5800000 | 6848824 | 2017 | Q4 | On Schedule | NEW
191 | Concrete Street Panel Group 1601 | B16026 | Concrete Street Panel Group 1601 | Transportation & Storm Water | Design Bid Build | 3260098 | 3346685 | 2017 | Q4 | On Schedule | NEW
192 | Sidewalk Replacement Group 1602 | B16028 | Sidewalk Replacement Group 1602 | Transportation & Storm Water | Design Bid Build | 1162500 | 1200000 | 2017 | Q4 | On Schedule | NEW
193 | Sidewalk Replacement Group 1603 | B16029 | Sidewalk Replacement Group 1603 | Transportation & Storm Water | Design Bid Build | 871500 | 900000 | 2017 | Q4 | On Schedule | NEW
194 | Sidewalk Replacement Group 1604 | B16030 | Sidewalk Replacement Group 1604 | Transportation & Storm Water | Design Bid Build | 888960 | 918000 | 2017 | Q2 | On Schedule | NEW
195 | Emergency Construction Services for 202 Coast Blvd Beach Access Stair Replacement | B17029 | Emergency Construction Services for 202 Coast Blvd Beach Access Stair Replacement | Transportation & Storm Water | Design Bid Build | 350000 | 490000 | 2017 | Q2 | Awarded | NEW
196 | City Heights Pedestrian Improvements (P1-P8 & East Euclid Ave) | S15044 | City Heights Pedestrian Improvements (P1-P8 & East Euclid Ave) | Transportation & Storm Water | Design Bid Build | 2480243 | 4800000 | 2017 | Q2 | Awarded | NEW
197 | El Cajon Boulevard Pedestrian Improvement | B15210 | El Cajon Boulevard Pedestrian Improvement | Transportation & Storm Water | Design Bid Build | 496355 | 1260000 | 2017 | Q2 | Awarded | NEW
198 | Girard @ Pearl A P S La Jolla DIF 13 | B13104 | Girard @ Pearl A P S La Jolla DIF 13 | Transportation & Storm Water | Design Bid Build | 26248 | 210500 | 2017 | Q1 | Awarded | NEW
199 | Emergency Construction Services for Sorrento & Alvarado Creek Concrete Channel Emergency Repairs | 21003729 | Emergency Construction Services for Sorrento & Alvarado Creek Concrete Channel Emergency Repairs | Transportation & Storm Water | Design Bid Build | 1250000 | 1250000 | 2017 | Q2 | Awarded | NEW
200 | Repairs at a Storm Drainage Pipe at 2582 Manzana Way | B17079 | Repairs at a Storm Drainage Pipe at 2582 Manzana Way | Transportation & Storm Water | Design Bid Build | 100000 | 140000 | 2017 | Q3 | Awarded | NEW
201 | AC Overlay Group 1509, JOC5 (Bond#3 + $100K) | B15182 | AC Overlay Group 1509, JOC5 (Bond#3 + $100K) | Transportation & Storm Water | Design Bid Build | 1233246 | 6000000 | 2017 | Q3 | Awarded | NEW
202 | AC Overlay Group 1512, JOC8 (Bond#3 + other balances) | B15184 | AC Overlay Group 1512, JOC8 (Bond#3 + other balances) | Transportation & Storm Water | Design Bid Build | 4499970 | 6000000 | 2017 | Q2 | Awarded | NEW
203 | Sidewalk Replacement Group 1601 | B16027 | Sidewalk Replacement Group 1601 | Transportation & Storm Water | Design Bid Build | 836257 | 1136257 | 2017 | Q2 | Awarded | NEW
204 | Emergency Repairs: Storm Drain Pipe at 10818 Eberly Court | B17106 | Emergency Repairs: Storm Drain Pipe at 10818 Eberly Court | Transportation & Storm Water | Design Bid Build | 235000 | 325000 | 2017 | Q3 | Awarded | NEW
205 | Emergency Repairs: Storm Drain Pipe at 4128 Casita Way | B17107 | Emergency Repairs: Storm Drain Pipe at 4128 Casita Way | Transportation & Storm Water | Design Bid Build | 300000 | 375000 | 2017 | Q3 | Awarded | NEW
206 | Emergency Repairs: Storm Drain Pipe at 3337 Buena Vista Street | B17109 | Emergency Repairs: Storm Drain Pipe at 3337 Buena Vista Street | Transportation & Storm Water | Design Bid Build | 325000 | 400000 | 2017 | Q3 | Awarded | NEW
207 | Emergency Repairs: Storm Drain Pipe at 5006 Collwood Way | B17117 | Emergency Repairs: Storm Drain Pipe at 5006 Collwood Way | Transportation & Storm Water | Design Bid Build | 75000 | 150000 | 2017 | Q3 | Awarded | NEW
208 | Emergency Repairs: Storm Drain Pipe at 3215 Talbot Street | B17108 | Emergency Repairs: Storm Drain Pipe at 3215 Talbot Street | Transportation & Storm Water | Design Bid Build | 100000 | 130000 | 2017 | Q3 | Awarded | NEW
209 | Avenida De La Playa Storm Drain Reconstruction | S13018 | Avenida De La Playa Storm Drain Reconstruction | Transportation & Storm Water | Design Bid Build | 591383 | 11362508 | 2017 | Q2 | Awarded | NEW
210 | Emergency Repairs: Storm Drain Pipe at 9109 Hector Avenue | B17099 | Emergency Repairs: Storm Drain Pipe at 9109 Hector Avenue | Transportation & Storm Water | Design Bid Build | 2000000 | 2300000 | 2017 | Q3 | Awarded | NEW
211 | Uptown Traffic Signal Upgrades | B14010 | Uptown Traffic Signal Upgrades | Transportation & Storm Water | Design Bid Build | 25000 | 159500 | 2017 | Q3 | Awarded | NEW
212 | Asphalt Overlay Group 1502 | B15130 | Asphalt Overlay Group 1502 | Transportation & Storm Water | Design Bid Build | 11406644 | 13000000 | 2015 | Q3 | Awarded | NEW