## Forecast of Projects
Line Number | Project Name | Project Name (Text) | Project Number | Asset Managing Department | Contract Type | Estimated Total Contract Cost ($) | Estimated Total Project Cost ($) | Fiscal Year Advertising | Quarter Advertising | Fiscal Year Awarding | Quarter Awarding
1 | Block 8R UUP | Block 8R UUP | 21003599 | Transportation and Storm Water Department - Street Division | Design Bid Build | 7929999.965 | 10705499.6271 | FY20 | Q2 | FY20 | Q4
2 | Block 4Y UUP | Block 4Y UUP | 21003600 | Transportation and Storm Water Department - Street Division | Design Bid Build | 13497898 | 18222161.9994 | FY19 | Q4 | FY20 | Q2
3 | Mid-City and Bonita Pipeline | Mid-City and Bonita Pipeline | 21004648 | PUD Water | Minor Contract | 170100 | 224100 | FY20 | Q1 | FY20 | Q2
4 | Sewer and AC Water Group 765 (S) | Sewer and AC Water Group 765 (S) | B00369 | PUD Sewer | Design Bid Build | 2361197.9995 | 3347431.9992 | FY20 | Q3 | FY20 | Q4
5 | SEWER GJ 798C | SEWER GJ 798C | B00409 | PUD Sewer | Design Bid Build | 212419.9997 | 484379.9995 | FY20 | Q4 | FY20 | Q4
6 | Fanuel St PI Archer to Tourmaline UUD | Fanuel St PI Archer to Tourmaline UUD | B00721 | TSW | Job Order Contract | 90344 | 110000 | FY20 | Q4 | FY20 | Q4
7 | District 1 Block 1-J UUD | District 1 Block 1-J UUD | B00836 | TSW | Job Order Contract | 422808.85 | 521808.85 | FY20 | Q3 | FY20 | Q4
8 | PACIFIC BEACH PIPELINE SOUTH (S) | PACIFIC BEACH PIPELINE SOUTH (S) | B12117 | PUD Sewer | Design Bid Build | 2805909.9998 | 4033821.9965 | FY20 | Q2 | FY20 | Q3
9 | SD Mission Rd w/o Fairmount Av Sdwk S/S | SD Mission Rd w/o Fairmount Av Sdwk S/S | B13130 | TSW | Design Bid Build | 450422.68 | 814422.6795 | FY20 | Q3 | FY20 | Q4
10 | 31st Street UUD (Market St - L St) | 31st Street UUD (Market St - L St) | B13143 | TSW | Job Order Contract | 68601.9998 | 79999.9996 | FY19 | Q4 | FY20 | Q2
11 | Block 4-J1 UUD (Mid City) | Block 4-J1 UUD (Mid City) | B13152 | TSW | Job Order Contract | 378429.64 | 604999.9942 | FY19 | Q4 | FY20 | Q2
12 | Block 8C UUD (Greater Golden Hill) | Block 8C UUD (Greater Golden Hill) | B13155 | TSW | Job Order Contract | 480000 | 680000 | FY21 | Q1 | FY20 | Q4
13 | Ashley Falls Lg Scale Storm Flow Storage | Ashley Falls Lg Scale Storm Flow Storage | B14007 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 761566.9884 | 1649831.988 | FY19 | Q3 | FY20 | Q1
14 | Otay 2nd Pipeline Phase 1 | Otay 2nd Pipeline Phase 1 | B14092 | PUD Water | Design Bid Build | 10770053.996 | 14590261.6942 | FY19 | Q4 | FY20 | Q2
15 | Water Group 968 | Water Group 968 | B14099 | PUD Water | Design Bid Build | 2152300 | 3182499.9996 | FY20 | Q3 | FY20 | Q4
16 | Alamo, Salvation, 68th Street Basins LID | Alamo, Salvation, 68th Street Basins LID | B14120 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 2532333.9921 | 3539999.989 | FY20 | Q1 | FY20 | Q2
17 | Storm Drain Group 968 | Storm Drain Group 968 | B15028 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 131000 | 281000 | FY20 | Q3 | FY20 | Q4
18 | Block 4Y UUP | Block 4Y UUP | B15087 | Transportation and Storm Water Department - Street Division | Design Bid Build | 1348999.3296 | 1829000.3281 | FY19 | Q4 | FY20 | Q2
19 | 25th (SB) Street UUP (Coronado-SB to Gro | 25th (SB) Street UUP (Coronado-SB to Gro | B15088 | TSW | Job Order Contract | 84999.9997 | 125999.9997 | FY20 | Q2 | FY20 | Q3
20 | Block 8R UUP - CIP | Block 8R UUP - CIP | B15097 | Transportation and Storm Water Department - Street Division | Design Bid Build | 999999.997 | 1349999.9967 | FY20 | Q2 | FY20 | Q4
21 | AC Water & Sewer Group 1023 (S) | AC Water & Sewer Group 1023 (S) | B15117 | PUD Sewer | Design Bid Build | 239355.7893 | 557415.749 | FY20 | Q2 | FY20 | Q4
22 | AC Water & Sewer Group 1023 (W) | AC Water & Sewer Group 1023 (W) | B15120 | PUD Water | Design Bid Build | 3529844.1929 | 5537206.0389 | FY20 | Q2 | FY20 | Q4
23 | Off FHWA System Bridge Rehabilitation | Off FHWA System Bridge Rehabilitation | B15127 | Transportation Engineering & Operations Division | Design Bid Build | 270367.46 | 506121.8 | FY19 | Q4 | FY20 | Q2
24 | On System Bridge Rehabilitation | On System Bridge Rehabilitation | B15128 | Transportation Engineering & Operations Division | Design Bid Build | 1776763.5398 | 2469329.8893 | FY20 | Q1 | FY20 | Q2
25 | NCWRP Expansion (Pkg. 1) | NCWRP Expansion (Pkg. 1) | B15142 | Public Utilities | Design Bid Build | 9734000 | 12313000 | FY19 | Q4 | FY20 | Q4
26 | NCWRP Expansion (Pkg. 2) | NCWRP Expansion (Pkg. 2) | B15142 | Public Utilities | Design Bid Build | 148292000 | 191787000 | FY19 | Q4 | FY20 | Q4
27 | Citywide Street Lights Group 1601 | Citywide Street Lights Group 1601 | B16007 | TSW | Job Order Contract | 464999.9999 | 723850.9999 | FY20 | Q1 | FY20 | Q4
28 | Citywide Street Lights Group 1602 | Citywide Street Lights Group 1602 | B16008 | TSW | Job Order Contract | 430299.9999 | 599999.9999 | FY20 | Q1 | FY20 | Q2
29 | Remaining Small Diameter CI Water Ph2 | Remaining Small Diameter CI Water Ph2 | B16023 | PUD Water | Design Bid Build | 7779750 | 11312799.9998 | FY20 | Q2 | FY20 | Q4
30 | Sidewalk Replacement Group 1604 | Sidewalk Replacement Group 1604 | B16030 | TSW | Design Bid Build | 820594 | 1378209.96 | FY19 | Q4 | FY20 | Q1
31 | Sewer Group 776A | Sewer Group 776A | B16034 | PUD Sewer | Design Bid Build | 3788428.9974 | 5375123.9943 | FY20 | Q3 | FY20 | Q4
32 | Sewer & AC Water Group 841(S) | Sewer & AC Water Group 841(S) | B16037 | PUD Water | Design Bid Build | 1708355.95 | 2819294.5729 | FY20 | Q1 | FY20 | Q2
33 | ADACA Crown Point Missing Walkways GF 16 | ADACA Crown Point Missing Walkways GF 16 | B16095 | Development Services Department | Design Bid Build | 456126.6 | 920999.8399 | FY20 | Q1 | FY20 | Q3
34 | ADA S/W Group 4E College | ADA S/W Group 4E College | B16107 | Development Services Department | Design Bid Build | 360000 | 785898.9997 | FY20 | Q3 | FY20 | Q4
35 | Loma Palisades SL Series Circuit Conv | Loma Palisades SL Series Circuit Conv | B16118 | TSW | Job Order Contract | 545000 | 1296999.9994 | FY20 | Q2 | FY20 | Q3
36 | Sewer & AC Water Crown Point West (W) | Sewer & AC Water Crown Point West (W) | B16144 | PUD Sewer | Design Bid Build | 6403000 | 8586546.6182 | FY20 | Q3 | FY20 | Q4
37 | Sewer & AC Water Crown Point West (S) | Sewer & AC Water Crown Point West (S) | B16145 | PUD Sewer | Design Bid Build | 10436000 | 13438691.1271 | FY20 | Q3 | FY20 | Q4
38 | Cass St (Grand-Pacific) SL UU143 | Cass St (Grand-Pacific) SL UU143 | B17007 | TSW | Job Order Contract | 64800 | 147000 | FY19 | Q4 | FY20 | Q1
39 | Coronado SB (27th-Madden) SL UU193 | Coronado SB (27th-Madden) SL UU193 | B17008 | TSW | Job Order Contract | 54000 | 90000 | FY20 | Q2 | FY20 | Q3
40 | Hughes St (58th St to Jodi St) SL UU101 | Hughes St (58th St to Jodi St) SL UU101 | B17010 | TSW | Job Order Contract | 125000 | 183000 | FY19 | Q4 | FY20 | Q2
41 | Bernardo Hts Py @ Calle Pueblito TS | Bernardo Hts Py @ Calle Pueblito TS | B17018 | TSW | Job Order Contract | 330999.9998 | 552351.9998 | FY20 | Q1 | FY20 | Q2
42 | Adams Ave & 49th St Splitter Islands | Adams Ave & 49th St Splitter Islands | B17025 | Transportation and Storm Water Department - Street Division | Design Bid Build | 243853.9996 | 765853.9992 | FY20 | Q2 | FY20 | Q4
43 | Market Street Water Pipe Replacement | Market Street Water Pipe Replacement | B17052 | PUD Water | Design Bid Build | 1062131.999 | 1459701.999 | FY20 | Q3 | FY20 | Q4
44 | Market Street Sewer Pipe Replacement | Market Street Sewer Pipe Replacement | B17054 | PUD Sewer | Design Bid Build | 326133.999 | 470551.999 | FY20 | Q3 | FY20 | Q4
45 | Downtown Complete Streets Implementation | Downtown Complete Streets Implementation | B17056 | Transportation and Storm Water Department - Street Division | Design Bid Build | 2345678.9 | 8436978.2081 | FY19 | Q4 | FY20 | Q2
46 | TP South Golf Course Improvements | TP South Golf Course Improvements | B17063 | Parks & Recreation Department | Multiple Award Construction Contract | 13900000 | 17000000 | FY20 | Q1 | FY20 | Q3
47 | 70th-Alvarado to Saranac-Sidewalk | 70th-Alvarado to Saranac-Sidewalk | B17065 | Transportation Engineering & Operations Division | Design Bid Build | 304424.9991 | 647824.9989 | FY19 | Q3 | FY20 | Q2
48 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | B17071 | Street Division | Design Bid Build | 106912 | 144329 | FY20 | Q3 | FY20 | Q4
49 | Manzana Storm Drain Replacement | Manzana Storm Drain Replacement | B17079 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 853000 | 1250000 | FY20 | Q1 | FY20 | Q1
50 | Remaining Small Diameter CI Water Ph 3 | Remaining Small Diameter CI Water Ph 3 | B17091 | PUD Water | Design Bid Build | 3655000 | 5189999.9989 | FY20 | Q3 | FY20 | Q4
51 | Asphalt Resurfacing Group 1702 (Option C | Asphalt Resurfacing Group 1702 (Option C | B17095 | Transportation and Storm Water Department - Street Division | Design Bid Build | 10844715 | 5499999.9948 | FY20 | Q2 | FY20 | Q3
52 | San Vicente PH I-II Rd Imp UU505-UU506 | San Vicente PH I-II Rd Imp UU505-UU506 | B17098 | Street Division | Design Bid Build | 359483 | 485302.05 | FY20 | Q3 | FY20 | Q4
53 | India St at West Palm St Hybrid Beacon | India St at West Palm St Hybrid Beacon | B17100 | TSW | Design Bid Build | 237500 | 395400 | FY21 | Q1 | FY20 | Q4
54 | Plumosa Park Series Circuit Conversion | Plumosa Park Series Circuit Conversion | B17101 | TSW | Job Order Contract | 765000 | 1450000 | FY21 | Q1 | FY20 | Q4
55 | San Diego Central Library-Boiler Replac | San Diego Central Library-Boiler Replac | B17103 | Library Department | Job Order Contract | 1002999.9976 | 1810165.9971 | FY19 | Q4 | FY20 | Q1
56 | Sewer & AC Water Group 1032 (S) | Sewer & AC Water Group 1032 (S) | B17104 | PUD Sewer | Design Bid Build | 6389000 | 8517999.9989 | FY20 | Q3 | FY20 | Q4
57 | Sewer & AC Water Group 1032 (W) | Sewer & AC Water Group 1032 (W) | B17105 | PUD Sewer | Design Bid Build | 7071000 | 9427999.9984 | FY20 | Q3 | FY20 | Q4
58 | Plaza De Panama Pipeline Replacement (S) | Plaza De Panama Pipeline Replacement (S) | B17132 | PUD Sewer | Design Bid Build | 1102041.6193 | 1410102.7393 | FY19 | Q3 | FY20 | Q2
59 | Plaza De Panama Pipeline Replacement (W) | Plaza De Panama Pipeline Replacement (W) | B17139 | PUD Water | Design Bid Build | 2046648.718 | 2598048.1778 | FY19 | Q3 | FY20 | Q2
60 | Abbot Street Series Circuit | Abbot Street Series Circuit | B17145 | TSW | Design Bid Build | 375000 | 685093.79 | FY21 | Q1 | FY20 | Q4
61 | Pipeline Rehabilitation AR-1 | Pipeline Rehabilitation AR-1 | B17150 | PUD Sewer | Design Bid Build | 3258440 | 5090969 | FY20 | Q1 | FY20 | Q3
62 | Pipeline Rehabilitation AQ-1 | Pipeline Rehabilitation AQ-1 | B17151 | PUD Sewer | Design Bid Build | 4209510.1 | 5497985.6095 | FY19 | Q4 | FY20 | Q1
63 | Regional Arterial Guardrail Group 2 | Regional Arterial Guardrail Group 2 | B17155 | TSW | Job Order Contract | 289612 | 473374.59 | FY21 | Q1 | FY20 | Q4
64 | Sewer and AC Water Group 765 (W) | Sewer and AC Water Group 765 (W) | B17167 | PUD Water | Design Bid Build | 2841405.997 | 3771727.9949 | FY20 | Q3 | FY20 | Q4
65 | Mission Beach Water & Sewer Repl (W) | Mission Beach Water & Sewer Repl (W) | B17169 | PUD Water | Design Bid Build | 13035279.9536 | 15336195.9536 | FY20 | Q3 | FY20 | Q4
66 | Mission Beach Water & Sewer Repl (S) | Mission Beach Water & Sewer Repl (S) | B17170 | PUD Sewer | Design Bid Build | 2194514.9953 | 2641714.9953 | FY20 | Q3 | FY20 | Q4
67 | Canyonside CP AC System | Canyonside CP AC System | B17172 | Parks & Recreation Department | Job Order Contract | 550000 | 1114999.9994 | FY20 | Q4 | FY20 | Q4
68 | Casa de Balboa Fire Alarm System | Casa de Balboa Fire Alarm System | B17181 | Parks & Recreation Department | Design Bid Build | 1100000 | 1587999.9994 | FY19 | Q3 | FY20 | Q2
69 | AC Water & Sewer Group 1044 (S) | AC Water & Sewer Group 1044 (S) | B17185 | PUD Sewer | Design Bid Build | 316847.7997 | 583057.1096 | FY20 | Q1 | FY20 | Q2
70 | AC Water & Sewer Group 1044 (W) | AC Water & Sewer Group 1044 (W) | B17186 | PUD Water | Design Bid Build | 2311652.1977 | 3903693.8475 | FY20 | Q1 | FY20 | Q2
71 | Ultraviolet Disinfection System Replace | Ultraviolet Disinfection System Replace | B18031 | PUD Sewer | Design Bid Build | 3391636 | 4544155.9989 | FY19 | Q3 | FY20 | Q1
72 | PIPELINE REHABILITATION AV-1 | PIPELINE REHABILITATION AV-1 | B18062 | PUD Sewer | Design Bid Build | 3311831.5 | 4430331.9908 | FY20 | Q2 | FY20 | Q3
73 | Sewer & AC Water Group 841(W) | Sewer & AC Water Group 841(W) | B18072 | PUD Water | Design Bid Build | 1101094 | 1801836.953 | FY20 | Q1 | FY20 | Q2
74 | AC Water & Sewer Group 1053 (W) | AC Water & Sewer Group 1053 (W) | B18093 | PUD Water | Multiple Award Construction Contract | 5384300 | 6443300 | FY20 | Q2 | FY20 | Q4
75 | AC Water & Sewer Group 1053 (S) | AC Water & Sewer Group 1053 (S) | B18099 | PUD Sewer | Multiple Award Construction Contract | 4821300 | 5523299.813 | FY20 | Q2 | FY20 | Q4
76 | Alvarado TS Water Main Relocations | Alvarado TS Water Main Relocations | B18104 | PUD Water | Design Bid Build | 9999999.9134 | 10438399.9128 | FY20 | Q3 | FY20 | Q4
77 | Manzana Water Replacement | Manzana Water Replacement | B18109 | PUD Water | Design Bid Build | 660000 | 928995 | FY19 | Q3 | FY20 | Q1
78 | Street Paving Group 1902 | Street Paving Group 1902 | B18135 | TSW | Design Bid Build | 11000000 | 12550000 | FY20 | Q2 | FY20 | Q4
79 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | B18136 | Street Division | Design Bid Build | 190910 | 257729.04 | FY20 | Q3 | FY20 | Q4
80 | Wightman (Chamoune -Euclid) Rd Imp UU388 | Wightman (Chamoune -Euclid) Rd Imp UU388 | B18138 | Street Division | Design Bid Build | 123367.07 | 166545.54 | FY20 | Q3 | FY20 | Q4
81 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | B18140 | Street Division | Design Bid Build | 170777 | 230548.95 | FY20 | Q3 | FY20 | Q4
82 | Golfcrest(Jackson-Wandermere)Rd ImpUU584 | Golfcrest(Jackson-Wandermere)Rd ImpUU584 | B18149 | Street Division | Design Bid Build | 221988 | 299683.8 | FY20 | Q3 | FY20 | Q4
83 | Hilltop PH I(Boundary-Toyne)Rd Imp UU617 | Hilltop PH I(Boundary-Toyne)Rd Imp UU617 | B18153 | Street Division | Design Bid Build | 235392 | 317779.2 | FY20 | Q3 | FY20 | Q4
84 | Accelerated Pipeline Rehab Ref Group 846 | Accelerated Pipeline Rehab Ref Group 846 | B18185 | PUD Sewer | Design Bid Build | 1005500 | 1226200 | FY20 | Q4 | FY20 | Q4
85 | AC Water Group 1059 | AC Water Group 1059 | B18196 | PUD Water | Design Bid Build | 3112384.6 | 4351216.6477 | FY20 | Q1 | FY20 | Q3
86 | PIPELINE REHABILITATION AX-1 | PIPELINE REHABILITATION AX-1 | B18203 | PUD Sewer | Design Bid Build | 4754000 | 5798000 | FY20 | Q2 | FY20 | Q4
87 | N Bank SD Riv Bike Path & Park Lot Resur | N Bank SD Riv Bike Path & Park Lot Resur | B18221 | Parks & Recreation Department | Design Bid Build | 416232 | 43782.3333 | FY20 | Q2 | FY20 | Q3
88 | Bonita Cove West Playground Improvements | Bonita Cove West Playground Improvements | B18229 | Parks & Recreation Department | Design Bid Build | 2331480.3559 | 4200000.3538 | FY20 | Q1 | FY20 | Q2
89 | Bonita Cove West Comfort Station Improve | Bonita Cove West Comfort Station Improve | B18230 | Parks & Recreation Department | Design Bid Build | 999999.9995 | 1499999.9994 | FY20 | Q1 | FY20 | Q2
90 | Hotel Circle CI & AC Accelerated Repl | Hotel Circle CI & AC Accelerated Repl | B18235 | PUD Water | Design Bid Build | 2555262 | 3580844.29 | FY19 | Q4 | FY20 | Q1
91 | Concrete Panel Replacement Group 1940 | Concrete Panel Replacement Group 1940 | B19002 | TSW | Design Bid Build | 3585000 | 4024230.9991 | FY19 | Q3 | FY20 | Q4
92 | Miramar Ranch North Paving G1 | Miramar Ranch North Paving G1 | B19007 | Transportation and Storm Water Department - Street Division | Design Bid Build | 4535555.27 | 5080555.27 | FY20 | Q4 | FY20 | Q4
93 | SP17 JOC North Task 1 - Scripps Poway Parkway | SP17 JOC North Task 1 - Scripps Poway Parkway | B19007 | TSW | Job Order Contract | 5000000 | 5500000 | FY19 | Q4 | FY20 | Q4
94 | SP17 JOC North Task 2 - Pomerado/Poway Rd/Clairemont | SP17 JOC North Task 2 - Pomerado/Poway Rd/Clairemont | B19007 | TSW | Job Order Contract | 5000000 | 5500000 | FY20 | Q1 | FY20 | Q4
95 | Kensington Talmadge Paving G1 | Kensington Talmadge Paving G1 | B19008 | Transportation and Storm Water Department - Street Division | Design Bid Build | 4510343.13 | 5080343.13 | FY20 | Q1 | FY20 | Q4
96 | SP17 JOC South Task 1 - Fairmount Ave/Montezuma | SP17 JOC South Task 1 - Fairmount Ave/Montezuma | B19008 | TSW | Job Order Contract | 5000000 | 5500000 | FY19 | Q4 | FY20 | Q4
97 | SP17 JOC South Task 2 - Harbor Dr/Picador | SP17 JOC South Task 2 - Harbor Dr/Picador | B19008 | TSW | Job Order Contract | 5000000 | 5500000 | FY20 | Q2 | FY20 | Q4
98 | Trench Paving Group 1901 | Trench Paving Group 1901 | B19011 | Transportation and Storm Water Department - Street Division | Design Bid Build | 110000 | 110000 | FY19 | Q4 | FY20 | Q1
99 | Sidewalk Replacement Group 1901-NP & OB | Sidewalk Replacement Group 1901-NP & OB | B19012 | TSW | Design Bid Build | 888151.5 | 1643215.79 | FY20 | Q2 | FY20 | Q3
100 | PS 1 and 2 Cooling Tower Replacement | PS 1 and 2 Cooling Tower Replacement | B19050 | PUD Sewer | Job Order Contract | 795399.6 | 825399.6 | FY19 | Q1 | FY20 | Q2
101 | MOUNTAIN VIEW ACCELERATED (W) | MOUNTAIN VIEW ACCELERATED (W) | B19075 | PUD Water | Job Order Contract | 859499.9992 | 1106499.9992 | FY20 | Q1 | FY20 | Q1
102 | MOUNTAIN VIEW ACCELERATED (S) | MOUNTAIN VIEW ACCELERATED (S) | B19076 | PUD Sewer | Job Order Contract | 411099.9995 | 529199.9995 | FY20 | Q1 | FY20 | Q1
103 | Rancho Penasquitos Improv 1(W) | Rancho Penasquitos Improv 1(W) | B19093 | PUD Water | Multiple Award Construction Contract | 5835800 | 7179840.2757 | FY20 | Q2 | FY20 | Q4
104 | 30th Street Pipeline Replacement A | 30th Street Pipeline Replacement A | B19100 | PUD Water | Job Order Contract | 2005614.2831 | 3005289.713 | FY19 | Q4 | FY20 | Q1
105 | LaJolla Rec Center Bball Crt Resurfacing | LaJolla Rec Center Bball Crt Resurfacing | B19114 | Parks & Recreation Department | Minor Contract | 209999.9996 | 399999.9995 | FY19 | Q4 | FY20 | Q2
106 | 6500 Montezuma Rd SD Emergency | 6500 Montezuma Rd SD Emergency | B19126 | Transportation and Storm Water Department - Storm Water Division | Sole Source Emergency Project | 5500000 | 5900000 | FY19 | Q3 | FY20 | Q1
107 | 7980 Park Village Rd SD Emergency | 7980 Park Village Rd SD Emergency | B19127 | Transportation and Storm Water Department - Storm Water Division | Sole Source Emergency Project | 3000000 | 3900000 | FY19 | Q3 | FY20 | Q1
108 | 4196 Rochester Rd SD Emergency | 4196 Rochester Rd SD Emergency | B19131 | Transportation and Storm Water Department - Storm Water Division | Sole Source Emergency Project | 1707000 | 2900000 | FY19 | Q3 | FY20 | Q1
109 | National Avenue Complete Street | National Avenue Complete Street | B19137 | Transportation Engineering & Operations Division | Multiple Award Construction Contract | 19633 | 30000 | FY20 | Q2 | FY20 | Q4
110 | Downtown Complete St Impl Phase 2 | Downtown Complete St Impl Phase 2 | B19143 | TSW | Design Bid Build | 2500000 | 3375000 | FY20 | Q3 | FY20 | Q4
111 | 12362 Springhurst Dr. SD Emergency | 12362 Springhurst Dr. SD Emergency | B19146 | Transportation and Storm Water Department - Street Division | Sole Source Emergency Project | 1000000 | 1700000 | FY19 | Q3 | FY20 | Q1
112 | Accelerated TS Referral Group 1 South | Accelerated TS Referral Group 1 South | B19150 | PUD Sewer | Design Bid Build | 388556 | 427412 | FY19 | Q4 | FY20 | Q1
113 | Rosecrans Street Median Improvements | Rosecrans Street Median Improvements | B19165 | Transportation and Storm Water Department - Street Division | Job Order Contract | 554000 | 911000 | FY20 | Q3 | FY20 | Q4
114 | Street Resurfacing Mission Bay | Street Resurfacing Mission Bay | B19195 | TSW | Job Order Contract | 4973786.9929 | 6606816.9919 | FY20 | Q2 | FY20 | Q3
115 | Milton Street Pavement Replacement | Milton Street Pavement Replacement | B19198 | PUD Sewer | Sole Source | 0 | 110000 | FY19 | Q4 | FY20 | Q1
116 | Bay Ho Improv 2A (W) | Bay Ho Improv 2A (W) | B19202 | PUD Water | Design Bid Build | 3317041 | 4461119.2498 | FY20 | Q2 | FY20 | Q4
117 | Street Paving Group 1903 | Street Paving Group 1903 | B19211 | TSW | Design Bid Build | 11000000 | 12550000 | FY20 | Q2 | FY20 | Q4
118 | CMP Storm Drain Lining I | CMP Storm Drain Lining I | B20020 | Transportation and Storm Water Department - Storm Water Division | Job Order Contract | 385308.07 | 511015.13 | FY20 | Q1 | FY20 | Q1
119 | Park Villa Drive Water & Sewer Main Replacement (S) | Park Villa Drive Water & Sewer Main Replacement (S) | B20021 | PUD Sewer | Job Order Contract | 165716.12 | 240687.2 | FY20 | Q1 | FY20 | Q2
120 | Park Villa Drive Water & Sewer Main Replacement (W) | Park Villa Drive Water & Sewer Main Replacement (W) | B20022 | PUD Sewer | Job Order Contract | 422396 | 725067.88 | FY20 | Q1 | FY20 | Q2
121 | Coast Bl Sea Cave Emerg Stablz Project | Coast Bl Sea Cave Emerg Stablz Project | B20040 | Transportation and Storm Water Department - Street Division | Sole Source Emergency Project | 3500000 | 4016323.49 | FY20 | Q1 | FY20 | Q1
122 | Pacific Beach Pipeline Paving | Pacific Beach Pipeline Paving | B20083 | PUD Water | Design Bid Build | 1098557 | 43782.3333 | FY20 | Q2 | FY20 | Q3
123 | CMP Storm Drain Lining II | CMP Storm Drain Lining II | B20086 | Transportation and Storm Water Department - Storm Water Division | Job Order Contract | 1620799.9974 | 2391399.997 | FY20 | Q4 | FY20 | Q4
124 | CMP Storm Drain Lining III | CMP Storm Drain Lining III | B20087 | Transportation and Storm Water Department - Storm Water Division | Job Order Contract | 559200 | 827799.9999 | FY20 | Q4 | FY20 | Q4
125 | Gamma Street Mini-Park ADA Improvements | Gamma Street Mini-Park ADA Improvements | L16000.1 | Parks & Recreation Department | Design Bid Build | 607649 | 1449999.9981 | FY20 | Q2 | FY20 | Q4
126 | J Street Mini Park Improvement | J Street Mini Park Improvement | L16000.6 | Parks & Recreation Department | Design Bid Build | 545999.9998 | 1224999.9992 | FY20 | Q2 | FY20 | Q4
127 | Dennery Ranch Neighborhood Park | Dennery Ranch Neighborhood Park | S00636 | Planning Department | Agency/ Developer Managed Built - City Paid | 5069999.9685 | 15099999.9685 | FY20 | Q1 | FY20 | Q4
128 | Miramar Road I-805 Easterly Ramps | Miramar Road I-805 Easterly Ramps | S00880 | TSW | Design Bid Build | 1410603 | 8126074.7614 | FY20 | Q3 | FY20 | Q4
129 | FAIRBROOK NEIGHBORHOOD PARK - DEVELOPMEN | FAIRBROOK NEIGHBORHOOD PARK - DEVELOPMEN | S01083 | Parks & Recreation Department | Design Bid Build | 4142812.75 | 6045539.85 | FY20 | Q3 | FY20 | Q4
130 | North Park Mini-Park | North Park Mini-Park | S10050 | Parks & Recreation Department | Design Bid Build | 2759751 | 4641460.9963 | FY20 | Q1 | FY20 | Q3
131 | Montezuma PPL/Mid City Pipeline Ph 2 | Montezuma PPL/Mid City Pipeline Ph 2 | S11026 | PUD Water | Design Bid Build | 33639377.1456 | 46001751.8291 | FY19 | Q3 | FY20 | Q2
132 | Otay Mesa Truck Route Phase 4 | Otay Mesa Truck Route Phase 4 | S11060 | TSW | Design Bid Build | 9970150 | 16404743.9633 | FY20 | Q1 | FY20 | Q3
133 | Canyonside Community Park Improvements | Canyonside Community Park Improvements | S12004 | Development Services Department | Design Bid Build | 1041250 | 1751125.6455 | FY19 | Q3 | FY20 | Q1
134 | PACIFIC BEACH PIPELINE SOUTH (W) | PACIFIC BEACH PIPELINE SOUTH (W) | S12015 | PUD Water | Design Bid Build | 31380170.9702 | 39360749.9894 | FY20 | Q2 | FY20 | Q3
135 | Otay 1st/2nd PPL West of Highland Avenue | Otay 1st/2nd PPL West of Highland Avenue | S12016 | PUD Water | Design Bid Build | 20178901.64 | 29440499.9574 | FY20 | Q1 | FY20 | Q2
136 | La Jolla Village/I-805 Landscape Maint | La Jolla Village/I-805 Landscape Maint | S15017 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 358000 | 549999.9527 | FY20 | Q3 | FY20 | Q4
137 | Alvarado Trunk Sewer Phase IV | Alvarado Trunk Sewer Phase IV | S15019 | PUD Sewer | Design Bid Build | 54999999.949 | 66999999.4719 | FY20 | Q3 | FY20 | Q4
138 | Torrey Highlands Neighborhood Park Upgra | Torrey Highlands Neighborhood Park Upgra | S16036 | Parks & Recreation Department | Design Bid Build | 659999.9996 | 1027937.9996 | FY20 | Q2 | FY20 | Q4
139 | Villa Monserate Neigh Park Upgrades | Villa Monserate Neigh Park Upgrades | S16048 | Parks & Recreation Department | Design Bid Build | 887184 | 1707221.0378 | FY20 | Q2 | FY20 | Q3
140 | Market St-47th ST to Euclid Complete St | Market St-47th ST to Euclid Complete St | S16061 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 5505836 | 9115587.8536 | FY20 | Q3 | FY20 | Q4
141 | Balboa Pk Bud Kearns Aquatic Complex Imp | Balboa Pk Bud Kearns Aquatic Complex Imp | S17000 | Parks & Recreation Department | Design Bid Build | 2241187 | 3693999.9982 | FY20 | Q2 | FY20 | Q4
142 | Police Range Refurbishment Phase II | Police Range Refurbishment Phase II | S18005 | Police Department | Design Bid Build | 10998313 | 12599999.998 | FY19 | Q4 | FY20 | Q2
|  |  | 142 CIP Projects |  |  | 655999959.0638 | 871891476.9172

## Summary Table
Summary by Asset - Managing Departments
Asset - Managing Department | Estimated Construction Contract Award | Estimated Total Project Cost
Development Services Department | 1857376.6 | 3458024.4852
Library Department | 1002999.9976 | 1810165.9971
Parks & Recreation Department | 31352296.1043 | 45637942.564
Planning Department | 5069999.9685 | 15099999.9685
PUD Water | 172190525.5557 | 228069656.4273
PUD Sewer | 125581236.4675 | 160843546.8877
Police Department | 10998313 | 12599999.998
Transportation and Storm Water Department - Street Division | 51421043.5913 | 63707716.0433
TSW | 71806104.6621 | 98192595.3676
Transportation and Storm Water Department - Storm Water Division | 22914045.0479 | 32816634.9101
Transportation Engineering & Operations Division | 2371188.9989 | 3653276.6883
Public Utilities | 158026000 | 204100000
Street Division | 1408829.07 | 1901917.58
FY 2020 Total | 655999959.0638 | 871891476.9172

## Sheet1 (hidden)
Project Number | Project Name | Not on website | Column1
B20021 | Park Villa Drive Water & Sewer Main Replacement (S) | No
B20022 | Park Villa Drive Water & Sewer Main Replacement (W) | No
B12117 | PACIFIC BEACH PIPELINE SOUTH (S) | No
B17007 | Cass St (Grand-Pacific) SL UU143 | No
B13143 | 31st Street UUD (Market St - L St) | No
B15086 | Block 6H UUP | No
B15088 | 25th (SB) Street UUP (Coronado-SB to Gro | No
B16095 | ADACA Crown Point Missing Walkways GF 16 | No
B17008 | Coronado SB (27th-Madden) SL UU193 | No
B17095 | Asphalt Resurfacing Group 1702 (Option C | No | March data shows this wil be awarded in FY20, but Feb data shows FY21, do not include on this list
B19127 | 7980 Park Village Rd SD Emergency | No
B14007 | Ashley Falls Lg Scale Storm Flow Storage | No
B19011 | Trench Paving Group 1901 | No | Do not include per senior's request
B19198 | Milton Street Pavement Replacement | No
B18031 | Ultraviolet Disinfection System Replace | No
S12004 | Canyonside Community Park Improvements | No
B19146 | 12362 Springhurst Dr. SD Emergency | No
B15117 | AC Water & Sewer Group 1023 (S) | No
B18109 | Manzana Water Replacement | No
B19131 | 4196 Rochester Rd SD Emergency | No
B19126 | 6500 Montezuma Rd SD Emergency | No
B18235 | Hotel Circle CI & AC Accelerated Repl | No
B19100 | 30th Street Pipeline Replacement A | No
B17103 | San Diego Central Library-Boiler Replac | No
B19150 | Accelerated TS Referral Group 1 South | No
B15120 | AC Water & Sewer Group 1023 (W) | No
B16030 | Sidewalk Replacement Group 1604 | No
B20040 | Coast Bl Sea Cave Emerg Stablz Project | No
B17151 | Pipeline Rehabilitation AQ-1 | No
B17079 | Manzana Storm Drain Replacement | No
B17181 | Casa de Balboa Fire Alarm System | No
B17139 | Plaza De Panama Pipeline Replacement (W) | No
B17132 | Plaza De Panama Pipeline Replacement (S) | No
B17065 | 70th-Alvarado to Saranac-Sidewalk | No
B19114 | LaJolla Rec Center Bball Crt Resurfacing | No
S11026 | Montezuma PPL/Mid City Pipeline Ph 2 | No
B15127 | Off FHWA System Bridge Rehabilitation | No
B19075 | MOUNTAIN VIEW ACCELERATED (W) | No
21003600 | Block 4Y UUP | No
B15087 | Block 4Y UUP | No
B13152 | Block 4-J1 UUD (Mid City) | No
B19076 | MOUNTAIN VIEW ACCELERATED (S) | No
B20020 | CMP Storm Drain Lining I | No
B17018 | Bernardo Hts Py @ Calle Pueblito TS | No
B15128 | On System Bridge Rehabilitation | No
B17185 | AC Water & Sewer Group 1044 (S) | No
B17056 | Downtown Complete Streets Implementation | No
B19050 | PS 1 and 2 Cooling Tower Replacement | No
B17186 | AC Water & Sewer Group 1044 (W) | No
S18005 | Police Range Refurbishment Phase II | No
B14092 | Otay 2nd Pipeline Phase 1 | No
B18229 | Bonita Cove West Playground Improvements | No
B18230 | Bonita Cove West Comfort Station Improve | No
S12016 | Otay 1st/2nd PPL West of Highland Avenue | No
B17010 | Hughes St (58th St to Jodi St) SL UU101 | No
B16008 | Citywide Street Lights Group 1602 | No
B16037 | Sewer & AC Water Group 841(S) | No
B18072 | Sewer & AC Water Group 841(W) | No
B14120 | Alamo, Salvation, 68th Street Basins LID | No
B17150 | Pipeline Rehabilitation AR-1 | No
B18062 | PIPELINE REHABILITATION AV-1 | No
B18196 | AC Water Group 1059 | No
B19195 | Street Resurfacing Mission Bay | No
S10050 | North Park Mini-Park | No
S11060 | Otay Mesa Truck Route Phase 4 | No
S12015 | PACIFIC BEACH PIPELINE SOUTH (W) | No
21004648 | Mid-City and Bonita Pipeline | No
B19211 | Street Paving Group 1903 | No
B00409 | SEWER GJ 798C | No
B00721 | Fanuel St PI Archer to Tourmaline UUD | No
B00836 | District 1 Block 1-J UUD | No
B16144 | Sewer & AC Water Crown Point West (W) | No
B14099 | Water Group 968 | No
B15028 | Storm Drain Group 968 | No
B16145 | Sewer & AC Water Crown Point West (S) | No
B15090 | Baker St/Shawnee Rd UUP (Morena to Shawn | No
B15093 | Seminole Drive UUP (Stanley to Estelle) | No
21003599 | Block 8R UUP | No
B15142.1 | NCWRP Expansion (Pkg. 1) | No
B15142.2 | NCWRP Expansion (Pkg. 2) | No
B00369 | Sewer and AC Water Group 765 (S) | No
B13130 | SD Mission Rd w/o Fairmount Av Sdwk S/S | No
B16034 | Sewer Group 776A | No
B15097 | Block 8R UUP - CIP | No
B16108 | ADA Curb Ramp Winder & McKee | No
B15198 | Nimitz Bridge at NTC Rehabilitation | No
B16023 | Remaining Small Diameter CI Water Ph2 | No
B16107 | ADA S/W Group 4E College | No
B19008 | Kensington Talmadge Paving G1 | No | Project added in March, do not include on this list
B17025 | Adams Ave & 49th St Splitter Islands | No
B17052 | Market Street Water Pipe Replacement | No
B17054 | Market Street Sewer Pipe Replacement | No
B17071 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | No
B16007 | Citywide Street Lights Group 1601 | No
B17098 | San Vicente PH I-II Rd Imp UU505-UU506 | No
B17104 | Sewer & AC Water Group 1032 (S) | No
B17105 | Sewer & AC Water Group 1032 (W) | No
B17091 | Remaining Small Diameter CI Water Ph 3 | No
B17169 | Mission Beach Water & Sewer Repl (W) | No
B17170 | Mission Beach Water & Sewer Repl (S) | No
B17172 | Canyonside CP AC System | No
B17167 | Sewer and AC Water Group 765 (W) | No
B18075 | Water Group 970 CI | No
B18093 | AC Water & Sewer Group 1053 (W) | No
B18104 | Alvarado TS Water Main Relocations | No
B18134 | Asphalt Resurfacing Group 1901 | No
B18135 | Street Paving Group 1902 | No
B18136 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | No
B18138 | Wightman (Chamoune -Euclid) Rd Imp UU388 | No
B18140 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | No
B18149 | Golfcrest(Jackson-Wandermere)Rd ImpUU584 | No
B18153 | Hilltop PH I(Boundary-Toyne)Rd Imp UU617 | No
B18185 | Accelerated Pipeline Rehab Ref Group 846 | No
B18099 | AC Water & Sewer Group 1053 (S) | No
B19002 | Concrete Panel Replacement Group 1940 | No
B16118 | Loma Palisades SL Series Circuit Conv | No
B19007.1 | SP17 JOC North Task 1 - Scripps Poway Parkway | No
B19007.2 | SP17 JOC North Task 2 - Pomerado/Poway Rd/Clairemont | No
B18203 | PIPELINE REHABILITATION AX-1 | No
B19008.1 | SP17 JOC South Task 1 - Fairmount Ave/Montezuma | No
B19008.2 | SP17 JOC South Task 2 - Harbor Dr/Picador | No
B19093 | Rancho Penasquitos Improv 1(W) | No
B19125 | Citywide Street Lights 1950 | No | not in P6
B19137 | National Avenue Complete Street | No
B19143 | Downtown Complete St Impl Phase 2 | No
B19165 | Rosecrans Street Median Improvements | No
B19202 | Bay Ho Improv 2A (W) | No
B20086 | CMP Storm Drain Lining II | No
B20087 | CMP Storm Drain Lining III | No
L16000.1 | Gamma Street Mini-Park ADA Improvements | No
L16000.6 | J Street Mini Park Improvement | No
S00636 | Dennery Ranch Neighborhood Park | No
S15017 | La Jolla Village/I-805 Landscape Maint | No
S15019 | Alvarado Trunk Sewer Phase IV | No
S16048 | Villa Monserate Neigh Park Upgrades | No
S16061 | Market St-47th ST to Euclid Complete St | No
S17000 | Balboa Pk Bud Kearns Aquatic Complex Imp | No
S17012 | North City Water Reclamation Plant Electrial Upgrades | No
S17013 | MBC Equipment Upgrades | No
B17063 | TP South Golf Course Improvements | No
S16036 | Torrey Highlands Neighborhood Park Upgra | No
B19007 | Miramar Ranch North Paving G1 | No | Project added in March, do not include on this list

## Progress (hidden)
Project Number | Project Name (Text) | Asset Managing Department | Contract Type | Estimated Total Contract Cost ($) | Estimated Total Project Cost ($) | Contract Bid - Start (5010) | Fiscal Year Advertising | Quarter Advertising | LNTP (6010) | Fiscal Year Awarding | Quarter Awarding | Responsible Division | On FY21 Award List | Include in this list? | Design Section Head
B19126 | 6500 Montezuma Rd SD Emergency | Transportation and Storm Water Department - Storm Water Division | Sole Source Emergency Project | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Choi, Jong
B19127 | 7980 Park Village Rd SD Emergency | Transportation and Storm Water Department - Storm Water Division | Sole Source Emergency Project | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Choi, Jong
B19131 | 4196 Rochester Rd SD Emergency | Transportation and Storm Water Department - Storm Water Division | Sole Source Emergency Project | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Choi, Jong
B19146 | 12362 Springhurst Dr. SD Emergency | Transportation and Storm Water Department - Street Division | Sole Source Emergency Project | 1700000 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Choi, Jong
B20040 | Coast Bl Sea Cave Emerg Stablz Project | Transportation and Storm Water Department - Street Division | Sole Source Emergency Project | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Choi, Jong
21003600 | Block 4Y UUP | Transportation and Storm Water Department - Street Division | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Zhang, Dayue
B13152 | Block 4-J1 UUD (Mid City) | TSW | Job Order Contract | 0 | 0 | 2019-06-13 | FY19 | Q4 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Qasem, Labib
B14007 | Ashley Falls Lg Scale Storm Flow Storage | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Schroth-Nichols, Elizabeth
B14120 | Alamo, Salvation, 68th Street Basins LID | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Oriqat, Mahmoud
B15087 | Block 4Y UUP | Transportation and Storm Water Department - Street Division | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Zhang, Dayue
B15127 | Off FHWA System Bridge Rehabilitation | Transportation Engineering & Operations Division | Design Bid Build | 0 | 0 | 2019-04-23 | FY19 | Q4 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Nutter, Daniel
B15128 | On System Bridge Rehabilitation | Transportation Engineering & Operations Division | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Nutter, Daniel
B16030 | Sidewalk Replacement Group 1604 | TSW | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | TSW Streets | No | Y | Hoenes, Craig
B16037 | Sewer & AC Water Group 841(S) | PUD Water | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Bose, Sheila
B16095 | ADACA Crown Point Missing Walkways GF 16 | Development Services Department | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh
B17056 | Downtown Mobility Cycleway Improvement | Transportation and Storm Water Department - Street Division | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Zhang, Dayue
B17065 | 70th-Alvarado to Saranac-Sidewalk | Transportation Engineering & Operations Division | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Nutter, Daniel
B17079 | Manzana Storm Drain Replacement | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 0 | 0 | 2019-08-01 | FY20 | Q1 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Bose, Sheila
B17181 | Casa de Balboa Fire Alarm System | Parks & Recreation Department | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Lozano, Edgar
B17185 | AC Water & Sewer Group 1044 (S) | PUD Sewer | Design Bid Build | 0 | 0 | 2019-07-19 | FY20 | Q1 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex
B17186 | AC Water & Sewer Group 1044 (W) | PUD Water | Design Bid Build | 0 | 0 | 2019-07-19 | FY20 | Q1 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex
B18031 | Ultraviolet Disinfection System Replace | PUD Sewer | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian
B18062 | PIPELINE REHABILITATION AV-1 | PUD Sewer | Design Bid Build | 0 | 0 | 2019-10-08 | FY20 | Q2 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex
B18072 | Sewer & AC Water Group 841(W) | PUD Water | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Bose, Sheila
B18109 | Manzana Water Replacement | PUD Water | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Bose, Sheila
B18196 | AC Water Group 1059 | PUD Water | Design Bid Build | 0 | 0 | 2019-09-12 | FY20 | Q1 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Bose, Sheila
B18229 | Bonita Cove West Playground Improvements | Parks & Recreation Department | Design Bid Build | 0 | 0 | 2019-08-22 | FY20 | Q1 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Oliver, Kevin
B18230 | Bonita Cove West Comfort Station Improve | Parks & Recreation Department | Design Bid Build | 0 | 0 | 2019-08-22 | FY20 | Q1 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Oliver, Kevin
B18235 | Hotel Circle CI & AC Accelerated Repl | PUD Water | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian
B19198 | Milton Street Pavement Replacement | PUD Sewer | Sole Source | 110000 | 0 | 2019-06-10 | FY19 | Q4 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Jaro, Janice
B20020 | CMP Storm Drain Lining I | Transportation and Storm Water Department - Storm Water Division | Job Order Contract | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No | Y | Oriqat, Mahmoud
B20086 | CMP Storm Drain Lining II | Transportation and Storm Water Department - Storm Water Division | Job Order Contract | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No |  | Oriqat, Mahmoud
B20087 | CMP Storm Drain Lining III | Transportation and Storm Water Department - Storm Water Division | Job Order Contract | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Right-of-Way Division | No |  | Oriqat, Mahmoud
S11026 | Montezuma PPL/Mid City Pipeline Ph 2 | PUD Water | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian
S12004 | Canyonside Community Park Improvements | Development Services Department | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Oliver, Kevin
S12016 | Otay 1st/2nd PPL West of Highland Avenue | PUD Water | Design Bid Build | 0 | 0 | 2019-07-02 | FY20 | Q1 | 0 | FY00 | Q3 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian
B17063 | TP South Golf Course Improvements | Parks & Recreation Department | Multiple Award Construction Contract | 0 | 0 | 2019-08-28 | FY20 | Q1 | 2018-04-06 | FY18 | Q4 | Architectural Engineering & Parks Division | No |  | Oliver, Kevin
B19100 | 30th Street Pipeline Replacement A | PUD Water | Job Order Contract | 2005614.29 | 3005290 | 2019-06-24 08:00 | FY19 | Q4 | 2019-08-23 | FY20 | Q1 | Right-of-Way Division | No | Y | Bose, Sheila
B17103 | San Diego Central Library-Boiler Replac | Library Department | Job Order Contract | 1002999.9999 | 1810165.9994 | 2019-06-05 08:00 | FY19 | Q4 | 2019-08-29 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Lewis, Nikki
B17007 | Cass St (Grand-Pacific) SL UU143 | TSW | Job Order Contract | 64800 | 72000 | 2019-08-16 08:00 | FY20 | Q1 | 2019-09-04 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Qasem, Labib
B19150 | Accelerated TS Referral Group 1 South | PUD Sewer | Design Bid Build | 388555.92 | 427411.92 | 2019-04-22 | FY19 | Q4 | 2019-09-13 | FY20 | Q1 | Right-of-Way Division | No | Y | Sleiman, Alex
B19075 | MOUNTAIN VIEW ACCELERATED (W) | PUD Water | Job Order Contract | 859499.9992 | 1106499.9992 | 2019-09-06 08:00 | FY20 | Q1 | 2019-09-19 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Jaro, Janice
B19076 | MOUNTAIN VIEW ACCELERATED (S) | PUD Sewer | Job Order Contract | 411099.9995 | 529199.9995 | 2019-09-06 08:00 | FY20 | Q1 | 2019-09-19 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Jaro, Janice
B17018 | Bernardo Hts Py @ Calle Pueblito TS | TSW | Job Order Contract | 325000 | 495905 | 2019-07-22 08:00 | FY20 | Q1 | 2019-10-01 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib
B20021 | Park Villa Drive Water & Sewer Main Replacement (S) | PUD Sewer | Job Order Contract | 165716 | 240687 | 2019-08-08 | FY20 | Q1 | 2019-10-07 | FY20 | Q2 | Right-of-Way Division | No | Y | Bose, Sheila
B20022 | Park Villa Drive Water & Sewer Main Replacement (W) | PUD Water | Job Order Contract | 422396 | 725067.88 | 2019-08-08 | FY20 | Q1 | 2019-10-07 | FY20 | Q2 | Right-of-Way Division | No | Y | Bose, Sheila
B17132 | Plaza De Panama Pipeline Replacement (S) | PUD Sewer | Design Bid Build | 1102041.6193 | 1410102.7393 | 2019-01-18 08:00 | FY19 | Q3 | 2019-10-08 | FY20 | Q2 | Right-of-Way Division | No | Y | Bose, Sheila
B17139 | Plaza De Panama Pipeline Replacement (W) | PUD Water | Design Bid Build | 2046648.718 | 2598048.1778 | 2019-01-18 08:00 | FY19 | Q3 | 2019-10-08 | FY20 | Q2 | Right-of-Way Division | No | Y | Bose, Sheila
B19114 | LaJolla Rec Center Bball Crt Resurfacing | Parks & Recreation Department | Minor Contract | 210000 | 399999.9999 | 2019-06-03 08:00 | FY19 | Q4 | 2019-10-10 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Choi, Jong
B19008.2 | SP17 JOC South Task 2 - Harbor Dr/Picador | TBD | TBD | 5000000 | 5500000 | 2020-06-30 | FY20 | Q4 | 2019-10-20 | FY20 | Q2 | TBD | No |  | Lahmann, Joshua
B19050 | PS 1 and 2 Cooling Tower Replacement | PUD Sewer | Job Order Contract | 795399.6 | 825399.6 | 2018-08-15 08:00 | FY19 | Q1 | 2019-11-14 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Choi, Jong
B16007 | Citywide Street Lights Group 1601 | TSW | Job Order Contract | 363620 | 500000 | 2020-02-03 08:00 | FY20 | Q3 | 2019-11-15 | FY20 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib
B16008 | Citywide Street Lights Group 1602 | TSW | Job Order Contract | 363620 | 500000 | 2019-09-03 08:00 | FY20 | Q1 | 2019-11-15 | FY20 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib
B19007.2 | SP17 JOC North Task 2 - Pomerado/Poway Rd/Clairemont | TBD | TBD | 5000000 | 5500000 | 2020-06-30 | FY20 | Q4 | 2019-11-17 | FY20 | Q2 | TBD | No |  | Lahmann, Joshua
B18134 | Street Paving Group 1901 | TSW | Design Bid Build | 11000000 | 12550000 | 2019-10-21 | FY20 | Q2 | 2019-12-09 | FY20 | Q2 | TSW | No |  | Lahmann, Joshua
B17010 | Hughes St (58th St to Jodi St) SL UU101 | TSW | Job Order Contract | 125000 | 131999.9999 | 2020-04-06 08:00 | FY20 | Q4 | 2019-12-19 | FY20 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib
B18135 | Street Paving Group 1902 | TSW | Design Bid Build | 11000000 | 12550000 | 2019-10-30 | FY20 | Q2 | 2019-12-19 | FY20 | Q2 | TSW | No |  | Lahmann, Joshua
B13143 | 31st Street UUD (Market St - L St) | TSW | Job Order Contract | 68601.9931 | 79999.9929 | 2019-12-30 08:00 | FY20 | Q2 | 2020-02-03 | FY20 | Q3 | Right-of-Way Division | No | Y | Qasem, Labib
B15088 | 25th (SB) Street UUP (Coronado-SB to Gro | TSW | Job Order Contract | 84999.9997 | 125999.9997 | 2019-12-30 08:00 | FY20 | Q2 | 2020-02-03 | FY20 | Q3 | Right-of-Way Division | No | Y | Qasem, Labib
B17008 | Coronado SB (27th-Madden) SL UU193 | TSW | Job Order Contract | 54000 | 60000 | 2019-12-30 08:00 | FY20 | Q2 | 2020-02-03 | FY20 | Q3 | Right-of-Way Division | No | Y | Qasem, Labib
B16145 | Sewer & AC Water Crown Point West (S) | PUD Sewer | Design Bid Build | 10436000 | 13438691.1271 | 2019-03-25 08:00 | FY19 | Q3 | 2020-02-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex
B16144 | Sewer & AC Water Crown Point West (W) | PUD Sewer | Design Bid Build | 6403000 | 8586546.6182 | 2019-03-25 08:00 | FY19 | Q3 | 2020-02-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex
B12117 | PACIFIC BEACH PIPELINE SOUTH (S) | PUD Sewer | Design Bid Build | 0 | 0 | 2019-11-13 | FY20 | Q2 | 2020-02-11 | FY20 | Q3 | Right-of-Way Division | No | y | Jaro, Janice
B19195 | Street Resurfacing Mission Bay | TSW | Job Order Contract | 4975999.9929 | 6535999.9926 | 2019-11-13 | FY20 | Q2 | 2020-02-11 | FY20 | Q3 | Right-of-Way Division | No | Y | James, Alaine
S12015 | PACIFIC BEACH PIPELINE SOUTH (w) | PUD Water | Design Bid Build | 0 | 0 | 2019-11-13 | FY20 | Q2 | 2020-02-11 | FY20 | Q3 | Right-of-Way Division | No | Y | Jaro, Janice
B17150 | Pipeline Rehabilitation AR-1 | PUD Sewer | Design Bid Build | 3946999.996 | 4812999.996 | 2019-09-05 | FY20 | Q1 | 2020-02-26 | FY20 | Q3 | Right-of-Way Division | No | Y | Salem, Nicole
B19211 | Street Paving Group 1903 | TBD | TBD | 5000000 | 12550000 | 2019-12-30 | FY20 | Q2 | 2020-02-28 | FY20 | Q3 | TSW | No | Y | Lahmann, Joshua
B19137 | National Avenue Complete Street | Transportation Engineering & Operations Division | Multiple Award Construction Contract | 19633 | 30000 | 2020-02-03 08:00 | FY20 | Q3 | 2020-03-01 | FY20 | Q3 | Right-of-Way Division | No | Y | Bose, Sheila
B16118 | Loma Palisades SL Series Circuit Conv | TSW | Job Order Contract | 824799.9994 | 1296999.9994 | 2019-11-04 | FY20 | Q2 | 2020-03-02 | FY20 | Q3 | Right-of-Way Division | No | Y | Qasem, Labib
S11060 | Otay Mesa Truck Route Phase 4 | TSW | Design Bid Build | 9990149.3779 | 16404743.3194 | 2019-08-28 08:00 | FY20 | Q1 | 2020-03-02 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh
B17052 | Market Street Water Pipe Replacement | PUD Water | Design Bid Build | 1062131.999 | 1459701.999 | 2019-09-03 08:00 | FY20 | Q1 | 2020-03-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh
B17054 | Market Street Sewer Pipe Replacement | PUD Sewer | Design Bid Build | 326133.999 | 470551.999 | 2019-09-03 08:00 | FY20 | Q1 | 2020-03-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh
S16061 | Market St-47th ST to Euclid Complete St | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 5505836 | 9115587.8536 | 2019-05-01 08:00 | FY19 | Q4 | 2020-03-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh
S16036 | Torrey Highlands Neighborhood Park Upgra | Parks & Recreation Department | Design Bid Build | 659999.9996 | 1027937.9996 | 2019-10-02 08:00 | FY20 | Q2 | 2020-03-06 08:00 | FY20 | Q3 | Architectural Engineering & Parks Division | No | Y | Oliver, Kevin
S00636 | Dennery Ranch Neighborhood Park | Planning Department | Agency/ Developer Managed Built - City Paid | 5069999.9685 | 15099999.9685 | 2019-08-01 08:00 | FY20 | Q1 | 2020-03-16 08:00 | FY20 | Q3 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir
B19002 | Concrete Panel Replacement Group 1940 | TSW | Design Bid Build | 3585000 | 4024230.9991 | 2019-03-18 08:00 | FY19 | Q3 | 2020-03-17 08:00 | FY20 | Q3 | TSW Streets | No | Y | Lahmann, Joshua
B16023 | Remaining Small Diameter CI Water Ph2 | PUD Water | Design Bid Build | 7779750 | 11312799.9998 | 2019-09-03 08:00 | FY20 | Q1 | 2020-04-07 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian
B17025 | Adams Ave & 49th St Splitter Islands | Transportation and Storm Water Department - Street Division | Design Bid Build | 294600 | 871499.9994 | 2019-12-17 08:00 | FY20 | Q2 | 2020-04-15 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel
S17000 | Balboa Pk Bud Kearns Aquatic Complex Imp | Parks & Recreation Department | Design Bid Build | 2241187 | 3293999.9991 | 2019-11-12 08:00 | FY20 | Q2 | 2020-04-24 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Schroth-Nichols, Elizabeth
B17091 | Remaining Small Diameter CI Water Ph 3 | PUD Water | Design Bid Build | 3655000 | 5189999.9989 | 2020-01-02 07:00 | FY20 | Q3 | 2020-04-30 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian
B17172 | Canyonside CP AC System | Parks & Recreation Department | Design Bid Build | 550000 | 1114999.9994 | 2020-02-03 08:00 | FY20 | Q3 | 2020-04-30 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Lozano, Edgar
S16048 | Villa Monserate Neigh Park Upgrades | Parks & Recreation Department | Design Bid Build | 887184 | 1707221.0378 | 2019-10-29 08:00 | FY20 | Q2 | 2020-04-30 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir
B18093 | AC Water & Sewer Group 1053 (W) | PUD Water | Multiple Award Construction Contract | 5384300 | 6443300 | 2019-11-01 08:00 | FY20 | Q2 | 2020-05-01 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila
B18099 | AC Water & Sewer Group 1053 (S) | PUD Sewer | Multiple Award Construction Contract | 4821300 | 5523299.9925 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-01 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila
L16000.1 | Gamma Street Mini-Park ADA Improvements | Parks & Recreation Department | Design Bid Build | 607649 | 1488290.9982 | 2019-07-01 08:00 | FY20 | Q1 | 2020-05-06 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir
B15086 | Block 6H UUP | TSW | Job Order Contract | 450000 | 623000 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-07 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib
B15090 | Baker St/Shawnee Rd UUP (Morena to Shawn | TSW | Job Order Contract | 120000 | 168000 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-07 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib
B15093 | Seminole Drive UUP (Stanley to Estelle) | TSW | Design Bid Build | 38249.9997 | 44999.9997 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-07 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib
B18075 | Water Group 970 CI | PUD Water | Design Bid Build | 6154699.9178 | 9970644.9128 | 2019-10-11 08:00 | FY20 | Q2 | 2020-05-08 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice
B00721 | Fanuel St PI Archer to Tourmaline UUD | TSW | Job Order Contract | 90344 | 142047 | 2020-03-09 08:00 | FY20 | Q3 | 2020-05-11 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib
B18203 | PIPELINE REHABILITATION AX-1 | PUD Sewer | Design Bid Build | 4754000 | 5798000 | 2020-02-04 08:00 | FY20 | Q3 | 2020-05-15 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila
B17071 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | Street Division | Design Bid Build | 106912 | 144329 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
B17098 | San Vicente PH I-II Rd Imp UU505-UU506 | Street Division | Design Bid Build | 359483 | 485302.05 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
B18136 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | Street Division | Design Bid Build | 190910 | 257729.04 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
B18138 | Wightman (Chamoune -Euclid) Rd Imp UU388 | Street Division | Design Bid Build | 123367.07 | 166545.54 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
B18140 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | Street Division | Design Bid Build | 170777 | 230548.95 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
B18149 | Golfcrest(Jackson-Wandermere)Rd ImpUU584 | Street Division | Design Bid Build | 221988 | 299683.8 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
B18153 | Hilltop PH I(Boundary-Toyne)Rd Imp UU617 | Street Division | Design Bid Build | 235392 | 317779.2 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
L16000.6 | J Street Mini Park Improvement | Parks & Recreation Department | Design Bid Build | 545999.9998 | 1171669.9992 | 2019-07-22 08:00 | FY20 | Q1 | 2020-05-26 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir
21003599 | Block 8R UUP | Transportation and Storm Water Department - Street Division | Design Bid Build | 7929999.965 | 10705499.6271 | 2019-11-08 08:00 | FY20 | Q2 | 2020-05-27 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
B15097 | Block 8R UUP - CIP | Transportation and Storm Water Department - Street Division | Design Bid Build | 999999.997 | 1349999.9967 | 2019-11-08 08:00 | FY20 | Q2 | 2020-05-27 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
B19202 | Bay Ho Improv 2A (W) | PUD Water | Design Bid Build | 1870170 | 3080299.9996 | 2020-01-02 08:00 | FY20 | Q3 | 2020-05-28 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila
S15017 | La Jolla Village/I-805 Landscape Maint | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 385000 | 549999.9527 | 2020-04-01 | FY20 | Q4 | 2020-06-01 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel
B19093 | Rancho Penasquitos Improv 1(W) | PUD Water | Multiple Award Construction Contract | 5835800 | 7179840.2757 | 2019-10-11 17:00 | FY20 | Q2 | 2020-06-02 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Sleiman, Alex
B16034 | Sewer Group 776A | PUD Sewer | Design Bid Build | 4146513.9971 | 5771975.9146 | 2020-02-18 08:00 | FY20 | Q3 | 2020-06-08 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice
B15117 | AC Water & Sewer Group 1023 (S) | PUD Sewer | Design Bid Build | 464999.9987 | 783059.9583 | 2020-02-03 08:00 | FY20 | Q3 | 2020-06-09 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Sleiman, Alex
B15120 | AC Water & Sewer Group 1023 (W) | PUD Water | Design Bid Build | 4000512.2206 | 6007874.0666 | 2020-02-03 08:00 | FY20 | Q3 | 2020-06-09 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Sleiman, Alex
B00836 | District 1 Block 1-J UUD | TSW | Job Order Contract | 422808.85 | 521808.85 | 2020-02-03 08:00 | FY20 | Q3 | 2020-06-09 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib
B19165 | Rosecrans Street Median Improvements | Transportation and Storm Water Department - Street Division | Design Bid Build | 554000 | 911000 | 2020-02-15 | FY20 | Q3 | 2020-06-10 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel
B17167 | Sewer and AC Water Group 765 (W) | PUD Water | Design Bid Build | 2841405.997 | 3771727.9734 | 2020-01-07 08:00 | FY20 | Q3 | 2020-06-12 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila
B16107 | ADA S/W Group 4E College | Development Services Department | Design Bid Build | 755000 | 1181898.9997 | 2020-03-02 08:00 | FY20 | Q3 | 2020-06-15 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel
B19143 | Downtown Complete St Impl Phase 2 | TSW | Design Bid Build | 2500000 | 3375000 | 2020-03-03 | FY20 | Q3 | 2020-06-15 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue
B00369 | Sewer and AC Water Group 765 (S) | PUD Sewer | Design Bid Build | 2361197.9995 | 3347431.9825 | 2020-01-03 08:00 | FY20 | Q3 | 2020-06-15 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila
L16000.2 | Island Ave Mini Park Improvements | Parks & Recreation Department | Design Bid Build | 1135000 | 2231849.9994 | 2019-11-05 08:00 | FY20 | Q2 | 2020-06-17 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir
B15198 | Nimitz Bridge at NTC Rehabilitation | TSW | Design Bid Build | 348499.9997 | 838099.9989 | 2020-02-12 | FY20 | Q3 | 2020-06-18 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel
B19012 | Sidewalk Replacement Group 1901-NP & OB | TSW | Design Bid Build | 1450000 | 1643215.79 | 2020-03-03 08:00 | FY20 | Q3 | 2020-06-18 08:00 | FY20 | Q4 | TSW Streets | No | Y | Hoenes, Craig
B18104 | Alvarado TS Water Main Relocations | PUD Water | Design Bid Build | 9999999.9134 | 10438399.9128 | 2020-02-18 08:00 | FY20 | Q3 | 2020-06-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice
S15019 | Alvarado Trunk Sewer Phase IV | PUD Sewer | Design Bid Build | 54999999.949 | 66999999.5239 | 2020-02-18 08:00 | FY20 | Q3 | 2020-06-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice
B17104 | Sewer & AC Water Group 1032 (S) | PUD Sewer | Design Bid Build | 6389000 | 8517999.9989 | 2020-02-27 08:00 | FY20 | Q3 | 2020-06-24 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice
B17105 | Sewer & AC Water Group 1032 (W) | PUD Sewer | Design Bid Build | 7071000 | 9427999.9984 | 2020-02-27 08:00 | FY20 | Q3 | 2020-06-24 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice
B16108 | ADA Curb Ramp Winder & McKee | ADA Compliance & Accessibility | Design Bid Build | 360300 | 804999.9997 | 2020-02-13 08:00 | FY20 | Q3 | 2020-06-26 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh
B13130 | SD Mission Rd w/o Fairmount Av Sdwk S/S | TSW | Design Bid Build | 832776 | 1330575.9996 | 2020-03-24 | FY20 | Q3 | 2020-06-29 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel
B00409 | SEWER GJ 798C | PUD Sewer | Design Bid Build | 212419.9997 | 484379.9995 | 2020-05-07 08:00 | FY20 | Q4 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole
B15142.1 | NCWRP Expansion (Pkg. 1) | Public Utilities | Design Bid Build | 12313000 | 9734000 | 2019-05-09 | FY19 | Q4 | 2020-06-30 | FY20 | Q4 | PUD | No | Y | Barhoumi, Amer
B17169 | Mission Beach Water & Sewer Repl (W) | PUD Water | Design Bid Build | 10541817.9626 | 13142733.9626 | 2020-03-05 08:00 | FY20 | Q3 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole
B17170 | Mission Beach Water & Sewer Repl (S) | PUD Sewer | Design Bid Build | 1578149.9966 | 2025349.9966 | 2020-03-05 08:00 | FY20 | Q3 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole
B19007.1 | SP17 JOC North Task 1 - Scripps Poway Parkway | TSW | Job Order Contract | 5000000 | 5500000 | 2019-06-15 | FY19 | Q4 | 2020-06-30 | FY20 | Q4 | TSW | No | Y | Lahmann, Joshua
B19008.1 | SP17 JOC South Task 1 - Fairmount Ave/Montezuma | TSW | Job Order Contract | 5000000 | 5500000 | 2019-06-01 | FY19 | Q4 | 2020-06-30 | FY20 | Q4 | TSW | No | Y | Lahmann, Joshua
B18185 | Accelerated Pipeline Rehab Ref Group 846 | PUD Sewer | Design Bid Build | 1005500 | 1226200 | 2020-04-08 | FY20 | Q4 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole
B15028 | Storm Drain Group 968 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 131000 | 281000 | 2020-03-18 | FY20 | Q3 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole
B14099 | Water Group 968 | PUD Water | Design Bid Build | 2152300 | 3182499.9996 | 2020-03-18 | FY20 | Q3 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole
B17155 | Regional Arterial Guardrail Group 2 | TSW | Job Order Contract | 256612 | 381800 | 2020-06-10 08:00 | FY20 | Q4 | 2020-08-12 08:00 | FY21 | Q1 | Right-of-Way Division | No | Y | Qasem, Labib
B13155 | Block 8C UUD (Greater Golden Hill) | TSW | Job Order Contract | 480000 | 680000 | 2020-06-15 08:00 | FY20 | Q4 | 2020-09-17 08:00 | FY21 | Q1 | Right-of-Way Division | No | Y | Qasem, Labib
B17145 | Abbot Street Series Circuit | TSW | Design Bid Build | 275000 | 422500 | 2020-06-17 08:00 | FY20 | Q4 | 2020-09-21 08:00 | FY21 | Q1 | Right-of-Way Division | No | Y | Qasem, Labib
B17101 | Plumosa Park Series Circuit Conversion | TSW | Job Order Contract | 765000 | 1100000 | 2020-06-10 08:00 | FY20 | Q4 | 2020-11-16 08:00 | FY21 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib
B17100 | India St at West Palm St Hybrid Beacon | TSW | Design Bid Build | 237500 | 395400 | 2020-06-05 08:00 | FY20 | Q4 | 2020-11-30 08:00 | FY21 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib
B14092 | Otay 2nd Pipeline Phase 1 | PUD Water | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | Removed - Dec 1st | #VALUE! | #VALUE! | Architectural Engineering & Parks Division | No | Y | Ammerlahn, Parita
B17151 | Pipeline Rehabilitation AQ-1 | PUD Sewer | Design Bid Build | 0 | 0 | 2019-05-09 | FY19 | Q4 | Removed - Dec 1st | #VALUE! | #VALUE! | Right-of-Way Division | No | Y | Bose, Sheila
S18005 | Police Range Refurbishment Phase II | Police Department | Design Bid Build | 0 | 0 | 0 | FY00 | Q3 | Removed - Dec 1st | #VALUE! | #VALUE! | Architectural Engineering & Parks Division | No | Y | Schroth-Nichols, Elizabeth

## Not on FY21 Award List-hide (hidden)
Project Number | Project Name (Text) | Asset Managing Department | Contract Type | Estimated Total Contract Cost ($) | Estimated Total Project Cost ($) | Contract Bid - Start (5010) | Fiscal Year Advertising | Quarter Advertising | LNTP (6010) | Fiscal Year Awarding | Quarter Awarding | Responsible Division | On FY21 Award List | Include in FY20 Mid Year List? | Design Section Head | Status of Award per Master
B19146 | 12362 Springhurst Dr. SD Emergency | Transportation and Storm Water Department - Street Division | Sole Source Emergency Project | 1000000 | 1700000 | 2019-03-04 08:00 | FY19 | Q3 | 2019-07-23 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Choi, Jong | Awarded
B15088 | 25th (SB) Street UUP (Coronado-SB to Gro | TSW | Job Order Contract | 84999.9997 | 125999.9997 | 2019-12-30 08:00 | FY20 | Q2 | 2020-02-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Qasem, Labib | Awarded
B19100 | 30th Street Pipeline Replacement A | PUD Water | Job Order Contract | 2005614.29 | 3005290 | 2019-06-24 08:00 | FY19 | Q4 | 2019-08-23 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Bose, Sheila | Awarded
B13143 | 31st Street UUD (Market St - L St) | TSW | Job Order Contract | 68601.9931 | 79999.9929 | 2019-12-30 08:00 | FY20 | Q2 | 2020-02-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Qasem, Labib | Awarded
B19131 | 4196 Rochester Rd SD Emergency | Transportation and Storm Water Department - Storm Water Division | Sole Source Emergency Project | 1707000 | 2900000 | 2019-03-04 08:00 | FY19 | Q3 | 2019-08-12 08:00 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Choi, Jong | Awarded
B19126 | 6500 Montezuma Rd SD Emergency | Transportation and Storm Water Department - Storm Water Division | Sole Source Emergency Project | 5500000 | 5900000 | 2019-02-07 08:00 | FY19 | Q3 | 2019-08-13 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Choi, Jong | Awarded
B17065 | 70th-Alvarado to Saranac-Sidewalk | Transportation Engineering & Operations Division | Design Bid Build | 304425 | 647824.9998 | 2019-03-28 08:00 | FY19 | Q3 | 2019-10-10 | FY20 | Q2 | Right-of-Way Division | No | Y | Nutter, Daniel | Awarded
B19127 | 7980 Park Village Rd SD Emergency | Transportation and Storm Water Department - Storm Water Division | Sole Source Emergency Project | 3000000 | 3900000 | 2019-02-07 08:00 | FY19 | Q3 | 2019-07-03 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Choi, Jong | Awarded
B17145 | Abbot Street Series Circuit | TSW | Design Bid Build | 275000 | 422500 | 2020-06-17 08:00 | FY20 | Q4 | 2020-09-21 08:00 | FY21 | Q1 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
B15117 | AC Water & Sewer Group 1023 (S) | PUD Sewer | Design Bid Build | 464999.9987 | 783059.9583 | 2020-02-03 08:00 | FY20 | Q3 | 2020-06-09 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Sleiman, Alex | On Schedule
B15120 | AC Water & Sewer Group 1023 (W) | PUD Water | Design Bid Build | 4000512.2206 | 6007874.0666 | 2020-02-03 08:00 | FY20 | Q3 | 2020-06-09 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Sleiman, Alex | On Schedule
B17185 | AC Water & Sewer Group 1044 (S) | PUD Sewer | Design Bid Build | 316847.7997 | 583057.1096 | 2019-08-01 08:00 | FY20 | Q1 | 2019-11-04 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Sleiman, Alex | Awarded
B17186 | AC Water & Sewer Group 1044 (W) | PUD Water | Design Bid Build | 2311652.1977 | 3903693.8475 | 2019-08-01 08:00 | FY20 | Q1 | 2019-11-04 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Sleiman, Alex | Awarded
B18099 | AC Water & Sewer Group 1053 (S) | PUD Sewer | Multiple Award Construction Contract | 4821300 | 5523299.9925 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-01 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila | On Schedule
B18093 | AC Water & Sewer Group 1053 (W) | PUD Water | Multiple Award Construction Contract | 5384300 | 6443300 | 2019-11-01 08:00 | FY20 | Q2 | 2020-05-01 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila | On Schedule
B18196 | AC Water Group 1059 | PUD Water | Design Bid Build | 4177740.9995 | 5943200.9985 | 2019-10-31 08:00 | FY20 | Q2 | 2020-02-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Bose, Sheila | Awarded
B18185 | Accelerated Pipeline Rehab Ref Group 846 | PUD Sewer | Design Bid Build | 1005500 | 1226200 | 2020-04-08 | FY20 | Q4 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole | On Schedule
B19150 | Accelerated TS Referral Group 1 South | PUD Sewer | Design Bid Build | 388555.92 | 427411.92 | 2019-04-22 | FY19 | Q4 | 2019-09-13 | FY20 | Q1 | Right-of-Way Division | No | Y | Sleiman, Alex | Awarded
B16108 | ADA Curb Ramp Winder & McKee | ADA Compliance & Accessibility | Design Bid Build | 360300 | 804999.9997 | 2020-02-13 08:00 | FY20 | Q3 | 2020-06-26 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh | On Schedule
B16107 | ADA S/W Group 4E College | Development Services Department | Design Bid Build | 755000 | 1181898.9997 | 2020-03-02 08:00 | FY20 | Q3 | 2020-06-15 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel | On Schedule
B16095 | ADACA Crown Point Missing Walkways GF 16 | Development Services Department | Design Bid Build | 577500 | 920999.8399 | 2019-09-17 08:00 | FY20 | Q1 | 2020-03-16 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh | Awarded
B17025 | Adams Ave & 49th St Splitter Islands | Transportation and Storm Water Department - Street Division | Design Bid Build | 294600 | 871499.9994 | 2019-12-17 08:00 | FY20 | Q2 | 2020-04-15 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel | On Schedule
B14120 | Alamo, Salvation, 68th Street Basins LID | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 2532334 | 3539999.9977 | 2019-07-16 08:00 | FY20 | Q1 | 2019-12-03 | FY20 | Q2 | Right-of-Way Division | No | Y | Oriqat, Mahmoud | Awarded
S15019 | Alvarado Trunk Sewer Phase IV | PUD Sewer | Design Bid Build | 54999999.949 | 66999999.5239 | 2020-02-18 08:00 | FY20 | Q3 | 2020-06-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice | On Schedule
B18104 | Alvarado TS Water Main Relocations | PUD Water | Design Bid Build | 9999999.9134 | 10438399.9128 | 2020-02-18 08:00 | FY20 | Q3 | 2020-06-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice | On Schedule
B14007 | Ashley Falls Lg Scale Storm Flow Storage | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 761567 | 1649831.9788 | 2019-03-29 08:00 | FY19 | Q3 | 2019-07-09 08:00 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Schroth-Nichols, Elizabeth | Awarded
B15090 | Baker St/Shawnee Rd UUP (Morena to Shawn | TSW | Job Order Contract | 120000 | 168000 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-07 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
B17134 | Balboa Park Pipeline Repl Ph III (S) | PUD Sewer | Design Bid Build | 1213000 | 1998499.6189 | 2020-09-10 08:00 | FY21 | Q1 | 2021-01-04 08:00 | FY21 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex | Removed
B17141 | Balboa Park Pipeline Repl Ph III (W) | PUD Water | Design Bid Build | 3010000 | 5004135.2862 | 2020-10-02 08:00 | FY21 | Q2 | 2021-01-27 08:00 | FY21 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex | Removed
S17000 | Balboa Pk Bud Kearns Aquatic Complex Imp | Parks & Recreation Department | Design Bid Build | 2241187 | 3293999.9991 | 2019-11-12 08:00 | FY20 | Q2 | 2020-04-24 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Schroth-Nichols, Elizabeth | On Schedule
B19202 | Bay Ho Improv 2A (W) | PUD Water | Design Bid Build | 1870170 | 3080299.9996 | 2020-01-02 08:00 | FY20 | Q3 | 2020-05-28 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila | On Schedule
B17018 | Bernardo Hts Py @ Calle Pueblito TS | TSW | Job Order Contract | 325000 | 495905 | 2019-07-22 08:00 | FY20 | Q1 | 2019-10-01 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib | Awarded
B13152 | Block 4-J1 UUD (Mid City) | TSW | Job Order Contract | 517500 | 604999.998 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-07 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib | Awarded
21003600 | Block 4Y UUP | Transportation and Storm Water Department - Street Division | Design Bid Build | 13497898 | 18222161.9994 | 2019-05-16 08:00 | FY19 | Q4 | 2019-10-22 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Zhang, Dayue | Awarded
B15087 | Block 4Y UUP | Transportation and Storm Water Department - Street Division | Design Bid Build | 1348999.3296 | 1815854.3296 | 2019-05-16 08:00 | FY19 | Q4 | 2019-10-22 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Zhang, Dayue | Awarded
B15086 | Block 6H UUP | TSW | Job Order Contract | 450000 | 623000 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-07 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
B13155 | Block 8C UUD (Greater Golden Hill) | TSW | Job Order Contract | 480000 | 680000 | 2020-06-15 08:00 | FY20 | Q4 | 2020-09-17 08:00 | FY21 | Q1 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
21003599 | Block 8R UUP | Transportation and Storm Water Department - Street Division | Design Bid Build | 7929999.965 | 10705499.6271 | 2019-11-08 08:00 | FY20 | Q2 | 2020-05-27 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule
B15097 | Block 8R UUP - CIP | Transportation and Storm Water Department - Street Division | Design Bid Build | 999999.997 | 1349999.9967 | 2019-11-08 08:00 | FY20 | Q2 | 2020-05-27 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule
B18230 | Bonita Cove West Comfort Station Improve | Parks & Recreation Department | Design Bid Build | 1000000 | 1499999.9998 | 2019-10-03 08:00 | FY20 | Q2 | 2019-11-01 08:00 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Oliver, Kevin | Awarded
B18229 | Bonita Cove West Playground Improvements | Parks & Recreation Department | Design Bid Build | 2331480.36 | 4200000.3579 | 2019-08-09 08:00 | FY20 | Q1 | 2019-11-01 08:00 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Oliver, Kevin | Awarded
S12004 | Canyonside Community Park Improvements | Development Services Department | Design Bid Build | 1041250 | 1751125.6455 | 2019-03-08 08:00 | FY19 | Q3 | 2019-07-17 08:00 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Oliver, Kevin | Awarded
B17172 | Canyonside CP AC System | Parks & Recreation Department | Design Bid Build | 550000 | 1114999.9994 | 2020-02-03 08:00 | FY20 | Q3 | 2020-04-30 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Lozano, Edgar | On Schedule
B17181 | Casa de Balboa Fire Alarm System | Parks & Recreation Department | Design Bid Build | 1000000 | 1587999.9994 | 2019-03-27 08:00 | FY19 | Q3 | 2019-07-15 08:00 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Lozano, Edgar | Awarded
B17007 | Cass St (Grand-Pacific) SL UU143 | TSW | Job Order Contract | 64800 | 72000 | 2019-08-16 08:00 | FY20 | Q1 | 2019-09-04 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Qasem, Labib | Awarded
B16007 | Citywide Street Lights Group 1601 | TSW | Job Order Contract | 363620 | 500000 | 2020-02-03 08:00 | FY20 | Q3 | 2019-11-15 | FY20 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
B16008 | Citywide Street Lights Group 1602 | TSW | Job Order Contract | 363620 | 500000 | 2019-09-03 08:00 | FY20 | Q1 | 2019-11-15 | FY20 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib | Awarded
B20020 | CMP Storm Drain Lining I | Transportation and Storm Water Department - Storm Water Division | Job Order Contract | 385308 | 100000 | 2019-08-27 08:00 | FY20 | Q1 | 2019-09-26 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Oriqat, Mahmoud | Awarded
B20040 | Coast Bl Sea Cave Emerg Stablz Project | Transportation and Storm Water Department - Street Division | Sole Source Emergency Project | 3500000 | 4016323.49 | 2019-08-08 08:00 | FY20 | Q1 | 2019-08-12 08:00 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Choi, Jong | Awarded
S00605 | Famosa Slough Salt Marsh Creation | Transportation and Storm Water Department - Storm Water Division | Sole Source | 215000 | 487999.9998 | 2005-01-10 08:00 | FY05 | Q3 | 2019-10-31 08:00 | FY20 | Q2 | Capital Asset Management | No | N | Purcell, Carrie | Removed
B19002 | Concrete Panel Replacement Group 1940 | TSW | Design Bid Build | 3585000 | 4024230.9991 | 2019-03-18 08:00 | FY19 | Q3 | 2020-03-17 08:00 | FY20 | Q3 | TSW Streets | No | Y | Lahmann, Joshua | On Schedule
B17008 | Coronado SB (27th-Madden) SL UU193 | TSW | Job Order Contract | 54000 | 60000 | 2019-12-30 08:00 | FY20 | Q2 | 2020-02-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Qasem, Labib | Awarded
S00636 | Dennery Ranch Neighborhood Park | Planning Department | Agency/ Developer Managed Built - City Paid | 5069999.9685 | 15099999.9685 | 2019-08-01 08:00 | FY20 | Q1 | 2020-03-16 08:00 | FY20 | Q3 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir | On Schedule
B00836 | District 1 Block 1-J UUD | TSW | Job Order Contract | 422808.85 | 521808.85 | 2020-02-03 08:00 | FY20 | Q3 | 2020-06-09 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
B19143 | Downtown Complete St Impl Phase 2 | TSW | Design Bid Build | 2500000 | 3375000 | 2020-03-03 | FY20 | Q3 | 2020-06-15 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule
B17056 | Downtown Mobility Cycleway Improvement | Transportation and Storm Water Department - Street Division | Design Bid Build | 2306978.2041 | 8436978.2022 | 2019-06-26 08:00 | FY19 | Q4 | 2019-11-14 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Zhang, Dayue | Awarded
B17071 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | Street Division | Design Bid Build | 106912 | 144329 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule
B00721 | Fanuel St PI Archer to Tourmaline UUD | TSW | Job Order Contract | 90344 | 142047 | 2020-03-09 08:00 | FY20 | Q3 | 2020-05-11 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
L16000.1 | Gamma Street Mini-Park ADA Improvements | Parks & Recreation Department | Design Bid Build | 607649 | 1488290.9982 | 2019-07-01 08:00 | FY20 | Q1 | 2020-05-06 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir | On Schedule
B18149 | Golfcrest(Jackson-Wandermere)Rd ImpUU584 | Street Division | Design Bid Build | 221988 | 299683.8 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule
B18153 | Hilltop PH I(Boundary-Toyne)Rd Imp UU617 | Street Division | Design Bid Build | 235392 | 317779.2 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule
B18235 | Hotel Circle CI & AC Accelerated Repl | PUD Water | Design Bid Build | 2610262.5 | 3580844.29 | 2019-04-11 08:00 | FY19 | Q4 | 2019-08-15 08:00 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian | Awarded
B18136 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | Street Division | Design Bid Build | 190910 | 257729.04 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule
B17010 | Hughes St (58th St to Jodi St) SL UU101 | TSW | Job Order Contract | 118799.9999 | 131999.9999 | 2020-04-06 08:00 | FY20 | Q4 | 2020-06-04 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib | Awarded
B17100 | India St at West Palm St Hybrid Beacon | TSW | Design Bid Build | 237500 | 395400 | 2020-06-05 08:00 | FY20 | Q4 | 2020-11-30 08:00 | FY21 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
L16000.2 | Island Ave Mini Park Improvements | Parks & Recreation Department | Design Bid Build | 1135000 | 2231849.9994 | 2019-11-05 08:00 | FY20 | Q2 | 2020-06-17 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir | Removed
L16000.6 | J Street Mini Park Improvement | Parks & Recreation Department | Design Bid Build | 545999.9998 | 1171669.9992 | 2019-07-22 08:00 | FY20 | Q1 | 2020-05-26 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir | On Schedule
S15017 | La Jolla Village/I-805 Landscape Maint | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 385000 | 549999.9527 | 2020-04-01 | FY20 | Q4 | 2020-06-01 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel | On Schedule
B19114 | LaJolla Rec Center Bball Crt Resurfacing | Parks & Recreation Department | Minor Contract | 210000 | 399999.9999 | 2019-06-03 08:00 | FY19 | Q4 | 2019-10-10 08:00 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Choi, Jong | Awarded
B16118 | Loma Palisades SL Series Circuit Conv | TSW | Job Order Contract | 824799.9994 | 1296999.9994 | 2020-07-07 08:00 | FY21 | Q1 | 2021-01-04 08:00 | FY21 | Q3 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
B17079 | Manzana Storm Drain Replacement | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 852999.9999 | 1249999.9999 | 2019-03-14 08:00 | FY19 | Q3 | 2019-08-09 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Bose, Sheila | Awarded
B18109 | Manzana Water Replacement | PUD Water | Design Bid Build | 659999.9967 | 928994.9967 | 2019-03-14 08:00 | FY19 | Q3 | 2019-08-09 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Bose, Sheila | Awarded
S16061 | Market St-47th ST to Euclid Complete St | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 5505836 | 9115587.8536 | 2019-05-01 08:00 | FY19 | Q4 | 2020-03-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh | On Schedule
B17054 | Market Street Sewer Pipe Replacement | PUD Sewer | Design Bid Build | 326133.999 | 470551.999 | 2019-09-03 08:00 | FY20 | Q1 | 2020-03-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh | On Schedule
B17052 | Market Street Water Pipe Replacement | PUD Water | Design Bid Build | 1062131.999 | 1459701.999 | 2019-09-03 08:00 | FY20 | Q1 | 2020-03-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh | On Schedule
B19198 | Milton Street Pavement Replacement | PUD Sewer | Sole Source | 110000 | 123500 | 2019-07-10 08:00 | FY20 | Q1 | 2019-07-10 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Jaro, Janice | Awarded
B17170 | Mission Beach Water & Sewer Repl (S) | PUD Sewer | Design Bid Build | 1578149.9966 | 2025349.9966 | 2020-03-05 08:00 | FY20 | Q3 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole | On Schedule
B17169 | Mission Beach Water & Sewer Repl (W) | PUD Water | Design Bid Build | 10541817.9626 | 13142733.9626 | 2020-03-05 08:00 | FY20 | Q3 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole | On Schedule
B18140 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | Street Division | Design Bid Build | 170777 | 230548.95 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule
S11026 | Montezuma PPL/Mid City Pipeline Ph 2 | PUD Water | Design Bid Build | 33639377.2 | 46001751.8837 | 2019-03-28 08:00 | FY19 | Q3 | 2019-10-10 08:00 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian | Awarded
B19076 | MOUNTAIN VIEW ACCELERATED (S) | PUD Sewer | Job Order Contract | 411099.9995 | 529199.9995 | 2019-09-06 08:00 | FY20 | Q1 | 2019-09-19 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Jaro, Janice | Awarded
B19075 | MOUNTAIN VIEW ACCELERATED (W) | PUD Water | Job Order Contract | 859499.9992 | 1106499.9992 | 2019-09-06 08:00 | FY20 | Q1 | 2019-09-19 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Jaro, Janice | Awarded
B19137 | National Avenue Complete Street | Transportation Engineering & Operations Division | Multiple Award Construction Contract | 19633 | 30000 | 2020-02-03 08:00 | FY20 | Q3 | 2020-03-01 | FY20 | Q3 | Right-of-Way Division | No | Y | Bose, Sheila | On Schedule
B15142.1 | NCWRP Expansion (Pkg. 1) |  |  | 12313000 | 9734000 | 2019-05-09 | FY19 | Q4 | 2020-06-30 | FY20 | Q4 | #N/A | No | Y | Barhoumi, Amer | On Schedule
B15198 | Nimitz Bridge at NTC Rehabilitation | TSW | Design Bid Build | 348499.9997 | 838099.9989 | 2020-02-12 | FY20 | Q3 | 2020-06-18 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel | On Schedule
B15127 | Off FHWA System Bridge Rehabilitation | Transportation Engineering & Operations Division | Design Bid Build | 270367.46 | 506121.8 | 2019-04-23 | FY19 | Q4 | 2019-10-22 | FY20 | Q2 | Right-of-Way Division | No | Y | Nutter, Daniel | Awarded
S10051 | Olive St Park Acquisition and Develpment | Parks & Recreation Department | Design Bid Build | 1659493.9984 | 3271584.998 | 2020-04-30 | FY20 | Q4 | 2020-06-30 | FY20 | Q4 | Architectural Engineering & Parks Division | Yes | Y | Oliver, Kevin | #N/A
B15128 | On System Bridge Rehabilitation | Transportation Engineering & Operations Division | Design Bid Build | 1776763.54 | 2469329.8896 | 2019-04-23 | FY19 | Q4 | 2019-10-22 | FY20 | Q2 | Right-of-Way Division | No | Y | Nutter, Daniel | Awarded
S12016 | Otay 1st/2nd PPL West of Highland Avenue | PUD Water | Design Bid Build | 20178901.6013 | 29440499.9072 | 2019-03-15 08:00 | FY19 | Q3 | 2019-11-13 08:00 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian | Awarded
B14092 | Otay 2nd Pipeline Phase 1 | PUD Water | Design Bid Build | 10770054 | 14590261.6987 | 2019-04-02 08:00 | FY19 | Q4 | 2019-11-22 08:00 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Ammerlahn, Parita | Awarded
S11060 | Otay Mesa Truck Route Phase 4 | TSW | Design Bid Build | 9990149.3779 | 16404743.3194 | 2019-08-28 08:00 | FY20 | Q1 | 2020-03-02 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Ashrafzadeh, Mastaneh | Awarded
B20021 | Park Villa Drive Water & Sewer Main Replacement (S) | PUD Sewer | Job Order Contract | 165716 | 240687 | 2019-08-08 | FY20 | Q1 | 2019-10-07 | FY20 | Q2 | #N/A | No | Y | Bose, Sheila | Awarded
B20022 | Park Villa Drive Water & Sewer Main Replacement (W) | PUD Water | Job Order Contract | 422396 | 725067.88 | 2019-08-08 | FY20 | Q1 | 2019-10-07 | FY20 | Q2 | #N/A | No | Y | Bose, Sheila | Awarded
B17151 | Pipeline Rehabilitation AQ-1 | PUD Sewer | Design Bid Build | 4209510.1 | 5497985.6095 | 2019-05-09 08:00 | FY19 | Q4 | 2019-09-30 08:00 | FY20 | Q1 | Right-of-Way Division | No | Y | Bose, Sheila | Awarded
B17150 | Pipeline Rehabilitation AR-1 | PUD Sewer | Design Bid Build | 3946999.996 | 4812999.996 | 2019-09-05 | FY20 | Q1 | 2020-02-26 | FY20 | Q3 | Right-of-Way Division | No | Y | Salem, Nicole | Awarded
B18062 | PIPELINE REHABILITATION AV-1 | PUD Sewer | Design Bid Build | 4325000 | 5277500 | 2019-05-14 08:00 | FY19 | Q4 | 2020-02-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex | Awarded
B18203 | PIPELINE REHABILITATION AX-1 | PUD Sewer | Design Bid Build | 4754000 | 5798000 | 2020-02-04 08:00 | FY20 | Q3 | 2020-05-15 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila | On Schedule
B17132 | Plaza De Panama Pipeline Replacement (S) | PUD Sewer | Design Bid Build | 1102041.6193 | 1410102.7393 | 2019-01-18 08:00 | FY19 | Q3 | 2019-10-08 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Bose, Sheila | Awarded
B17139 | Plaza De Panama Pipeline Replacement (W) | PUD Water | Design Bid Build | 2046648.718 | 2598048.1778 | 2019-01-18 08:00 | FY19 | Q3 | 2019-10-08 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Bose, Sheila | Awarded
B17101 | Plumosa Park Series Circuit Conversion | TSW | Job Order Contract | 765000 | 1100000 | 2020-06-10 08:00 | FY20 | Q4 | 2020-11-16 08:00 | FY21 | Q2 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
S18005 | Police Range Refurbishment Phase II | Police Department | Design Bid Build | 11008312.9846 | 12600999.9826 | 2019-05-31 08:00 | FY19 | Q4 | 2019-11-21 08:00 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Schroth-Nichols, Elizabeth | Awarded
B19050 | PS 1 and 2 Cooling Tower Replacement | PUD Sewer | Job Order Contract | 795399.6 | 825399.6 | 2018-08-15 08:00 | FY19 | Q1 | 2019-11-14 08:00 | FY20 | Q2 | Architectural Engineering & Parks Division | No | Y | Choi, Jong | Awarded
B19093 | Rancho Penasquitos Improv 1(W) | PUD Water | Multiple Award Construction Contract | 5835800 | 7179840.2757 | 2019-10-11 17:00 | FY20 | Q2 | 2020-06-02 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Sleiman, Alex | On Schedule
B17155 | Regional Arterial Guardrail Group 2 | TSW | Job Order Contract | 256612 | 381800 | 2020-06-10 08:00 | FY20 | Q4 | 2020-08-12 08:00 | FY21 | Q1 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
B17091 | Remaining Small Diameter CI Water Ph 3 | PUD Water | Design Bid Build | 3655000 | 5189999.9989 | 2020-01-02 07:00 | FY20 | Q3 | 2020-04-30 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian | On Schedule
B16023 | Remaining Small Diameter CI Water Ph2 | PUD Water | Design Bid Build | 7779750 | 11312799.9998 | 2019-09-03 08:00 | FY20 | Q1 | 2020-04-07 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian | On Schedule
B19165 | Rosecrans Street Median Improvements | Transportation and Storm Water Department - Street Division | Design Bid Build | 554000 | 911000 | 2020-02-15 | FY20 | Q3 | 2020-06-10 | FY20 | Q4 | #N/A | No | Y | Nutter, Daniel | On Schedule
B17103 | San Diego Central Library-Boiler Replac | Library Department | Job Order Contract | 1002999.9999 | 1810165.9994 | 2019-06-05 08:00 | FY19 | Q4 | 2019-08-29 08:00 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Lewis, Nikki | Awarded
B17098 | San Vicente PH I-II Rd Imp UU505-UU506 | Street Division | Design Bid Build | 359483 | 485302.05 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule
B19067 | Mingei Museum Dome Waterproofing | Real Estate Assets Department | Minor Contract | 162000 | 239000 | 2019-09-18 08:00 | FY20 | Q1 | 2020-02-28 08:00 | FY20 | Q3 | Architectural Engineering & Parks Division | No | N, per senior | Choi, Jong | Removed
B11057 | Beta Street and 37th Street Green Alley | Transportation and Storm Water Department - Storm Water Division | Job Order Contract | 1086201 | 1428059.9997 | 2019-07-11 08:00 | FY20 | Q1 | 2020-03-20 08:00 | FY20 | Q3 | Architectural Engineering & Parks Division | No | N, U Turned | Lewis, Nikki | Removed
S10050 | North Park Mini-Park | Parks & Recreation Department | Design Bid Build | 2348900.4187 | 3484002.9972 | 2019-09-03 08:00 | FY20 | Q1 | 2021-01-05 08:00 | FY21 | Q3 | Architectural Engineering & Parks Division | No | N | Oliver, Kevin | Awarded
B15141.1 | Morena Conveyance Southern Segment - B1 |  |  | 56551939 | 70689924 | 2021-03-24 | FY21 | Q3 | 2021-08-20 | FY22 | Q1 | #N/A | No | N | Batta, Nabil | Removed
B15141.2 | Morena Conveyance Middle Segment - B2 |  |  | 44564193 | 55705241 | 2021-07-15 | FY22 | Q1 | 2022-01-10 | FY22 | Q3 | #N/A | No | N | Batta, Nabil | Removed
B13137 | 4th Ave & Date St Traffic Signal | TSW | Design Bid Build | 214588.9973 | 274999.9972 | 2020-06-08 08:00 | FY20 | Q4 | 2020-10-27 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B13150 | Via De La Valle UUD (Highland Cv/City Li | TSW | Job Order Contract | 60000 | 81000 | 2020-06-04 08:00 | FY20 | Q4 | 2020-09-08 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B14015 | Beyer Bl @ Smythe Ave Traffic Signal | TSW | Job Order Contract | 530000.01 | 925000 | 2019-02-20 08:00 | FY19 | Q3 | 2019-06-20 08:00 | FY19 | Q4 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B15005 | 32nd & Norman Scott Rd TS Upgrade | TSW | Job Order Contract | 319999.9999 | 606299.9968 | 2019-04-04 08:00 | FY19 | Q4 | 2019-06-04 08:00 | FY19 | Q4 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B15014 | 31st St & Market St School Traffic Sgnal | TSW | Design Bid Build | 294000 | 376999.9999 | 2020-03-06 08:00 | FY20 | Q3 | 2020-09-14 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B16099 | ADA APS Group 2E Washington St & Normal | ADA Compliance & Accessibility | Job Order Contract | 276000 | 415042 | 2019-02-11 08:00 | FY19 | Q3 | 2019-06-05 08:00 | FY19 | Q4 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B16119 | Pacific Beach 1 SL Series Circuit Conv | TSW | Design Bid Build | 4067299.9971 | 6160999.9971 | 2021-06-28 08:00 | FY21 | Q4 | 2021-12-29 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Qasem, Labib | #N/A
B17016 | Governor Dr @ Lakewood St Traffic Signal | TSW | Design Bid Build | 275700 | 460000 | 2020-11-20 08:00 | FY21 | Q2 | 2021-03-29 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B17019 | 31st St @ National Ave Traffic Signal | TSW | Design Bid Build | 399000 | 624800 | 2020-12-04 08:00 | FY21 | Q2 | 2021-06-09 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Qasem, Labib | #N/A
B17146 | Kensington Hts #2 Series Circuit Upgrade | TSW | Design Bid Build | 2040999.995 | 2499999.995 | 2020-06-10 08:00 | FY20 | Q4 | 2020-12-03 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B18069 | Ash Street Signal Mods | TSW | Design Bid Build | 435042 | 767552.9998 | 2020-12-03 08:00 | FY21 | Q2 | 2021-06-03 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Qasem, Labib | #N/A
B18083 | Center City - New Traffic Signals | TSW | Design Bid Build | 1345350 | 2152799.9993 | 2020-11-19 08:00 | FY21 | Q2 | 2021-06-02 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B18162 | Downtown Audibles O4th & E S29 | Transportation Engineering & Operations Division | Design Bid Build | 385099.9967 | 616399.9965 | 2021-06-02 08:00 | FY21 | Q4 | 2021-12-02 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Qasem, Labib | #N/A
B18201 | Regional Arterial Guardrail Group 2a | Transportation and Storm Water Department - Street Division | Design Bid Build | 116700 | 211499.9999 | 2020-07-22 08:00 | FY21 | Q1 | 2021-01-19 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Qasem, Labib | Removed
B13130 | SD Mission Rd w/o Fairmount Av Sdwk S/S | TSW | Design Bid Build | 832776 | 1330575.9996 | 2020-03-24 | FY20 | Q3 | 2020-06-29 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Nutter, Daniel | On Schedule
B19057 | Aquarius & Camino Ruiz Traff. Signal | Transportation Engineering & Operations Division | Design Bid Build | 299000 | 499399.9999 | 2021-03-03 08:00 | FY21 | Q3 | 2021-09-01 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Qasem, Labib | #N/A
B19060 | El Cajon & Kansas - Traffic Signal | Transportation Engineering & Operations Division | Design Bid Build | 458199.9998 | 797299.9996 | 2021-02-03 08:00 | FY21 | Q3 | 2021-08-05 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Qasem, Labib | #N/A
B19079 | Reo Drive New Streetlights | Transportation and Storm Water Department - Street Division | Design Bid Build | 261700 | 402499.9999 | 2021-01-14 08:00 | FY21 | Q3 | 2021-06-28 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Qasem, Labib | #N/A
B18034 | MYF Electrical System Upgrade | Airports Department | Design Bid Build | 252439.5074 | 419999.5072 | 2019-02-04 08:00 | FY19 | Q3 | 2019-06-24 08:00 | FY19 | Q4 | Architectural Engineering & Parks Division | No | N | Grani, Jason | Removed
B19068 | City Heights Pool Reconstruction | Parks & Recreation Department | Design Bid Build | 2909329 | 4188781.9984 | 2019-08-29 08:00 | FY20 | Q1 | 2020-08-17 08:00 | FY21 | Q1 | Architectural Engineering & Parks Division | No | N | Ammerlahn, Parita | Removed
B15142 | NCWRP Expansion | PUD Water | Design Bid Build | 123741147.975 | 159419445.6406 | 2020-12-11 08:00 | FY21 | Q2 | 2021-06-23 08:00 | FY21 | Q4 | PUD Pure Water | No | N | Barhoumi, Amer | #N/A
B00429 | Buchanan Canyon Sewer B (UP) | PUD Sewer | Design Bid Build | 3487493 | 5420517.963 | 2020-09-04 08:00 | FY21 | Q1 | 2021-02-16 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B11048 | Water Group Job 952 | PUD Water | Design Bid Build | 5299999.9954 | 7393193.991 | 2020-05-04 08:00 | FY20 | Q4 | 2020-10-05 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Bose, Sheila | Removed
B12040 | Maple Canyon Restoration - Phase 1 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 4265781.8225 | 8182960.7954 | 2020-08-26 08:00 | FY21 | Q1 | 2021-03-09 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Bose, Sheila | Removed
B16006 | La Jolla Farms Outfall Repair | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 754000 | 1271200 | 2020-06-17 08:00 | FY20 | Q4 | 2020-12-22 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Bose, Sheila | Removed
B16111 | Green Infrastructure Group 1012 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 2025000 | 2999999.9994 | 2020-02-19 08:00 | FY20 | Q3 | 2020-08-26 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Bose, Sheila | Removed
B17153 | AC Water Group 1038 | PUD Water | Design Bid Build | 22286634.0071 | 29568478.0033 | 2020-09-18 08:00 | FY21 | Q1 | 2021-06-04 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Bose, Sheila | Removed
B18181 | AC Water & Sewer Group 1056 (W) | PUD Water | Design Bid Build | 8535299.9968 | 11045699.9968 | 2020-12-21 08:00 | FY21 | Q2 | 2021-06-18 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B18182 | AC Water & Sewer Group 1056 (S) | PUD Sewer | Design Bid Build | 181799.9999 | 241699.9999 | 2020-12-21 08:00 | FY21 | Q2 | 2021-06-18 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B20014 | Pipeline Rehabilitation BA-1 | PUD Sewer | Design Bid Build | 5137000 | 6788299.9989 | 2021-01-13 08:00 | FY21 | Q3 | 2021-06-09 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
S14017 | Fire Station No. 51 Skyline Hills | Fire-Rescue Department (Lifeguard) | Design Build | 10972000 | 13890956.9999 | 2019-06-20 08:00 | FY19 | Q4 | 2021-01-29 08:00 | FY21 | Q3 | Architectural Engineering & Parks Division | No | N | Grani, Jason | Removed
21003798 | Browns Field CBP Modular Structure | Real Estate Assets Department | Design Build | 1204000 | 1877999.9656 | 2019-03-26 08:00 | FY19 | Q3 | 2020-09-30 08:00 | FY21 | Q1 | Capital Asset Management | No | N | James, Alaine | Removed
B18192 | Mountain View Sports Courts | Parks & Recreation Department | Job Order Contract | 455000 | 786999.9998 | 2020-04-06 08:00 | FY20 | Q4 | 2020-07-31 08:00 | FY21 | Q1 | Capital Asset Management | No | N | James, Alaine | Removed
B19162 | Playa Pacifica No Parking Lot Imprvemts | Parks & Recreation Department | Design Bid Build | 1867999.9998 | 2790999.9993 | 2020-06-30 08:00 | FY20 | Q4 | 2020-10-01 08:00 | FY21 | Q2 | Capital Asset Management | No | N | James, Alaine | Removed
B19163 | Rose Marie Starns Parking Lot Imprvemts | Parks & Recreation Department | Design Bid Build | 1921999.9998 | 2869999.9993 | 2020-07-15 08:00 | FY21 | Q1 | 2020-11-02 08:00 | FY21 | Q2 | Capital Asset Management | No | N | James, Alaine | Removed
B17095 | Asphalt Resurfacing Group 1702 (Option C | Transportation and Storm Water Department - Street Division | Design Bid Build | 4756087 | 5500000 | 2019-09-04 08:00 | FY20 | Q1 | 2021-01-08 16:55 | FY21 | Q3 | TSW Streets | No | N | Lahmann, Joshua | Awarded
B20064 | Balboa Park Golf Course- Bathroom Remodel | Parks & Recreation Department | Job Order Contract | 61999.9999 | 128999.9999 | 2021-01-04 08:00 | FY21 | Q3 | 2021-05-03 08:00 | FY21 | Q4 | Architectural Engineering & Parks Division | No | N | Lewis, Nikki | #N/A
B18006 | Sherman Heights Com Center Playground | Parks & Recreation Department | Design Bid Build | 366699.9998 | 619999.9996 | 2020-03-05 08:00 | FY20 | Q3 | 2020-08-28 08:00 | FY21 | Q1 | Architectural Engineering & Parks Division | No | N | Lozano, Edgar | Removed
B18019 | Howard Ave-Village Pine to Iris Sidewalk | Transportation and Storm Water Department - Street Division | Design Bid Build | 676000 | 1192999.9997 | 2020-12-01 08:00 | FY21 | Q2 | 2021-06-01 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Nutter, Daniel | #N/A
S00880 | Miramar Road I-805 Easterly Ramps | TSW | Design Bid Build | 1285603 | 7981074.7156 | 2020-02-04 08:00 | FY20 | Q3 | 2020-08-03 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Nutter, Daniel | Removed
B10161 | Laurel Ridge Court Storm Drain | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 794500 | 1463558.9999 | 2020-06-12 08:00 | FY20 | Q4 | 2020-09-14 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B12031 | Rue Cheaumont (12275) Storm Drain Replac | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 8848.9999 | 663180.7464 | 2020-02-06 08:00 | FY20 | Q3 | 2020-08-14 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B13016 | Campus Point Dr (9900) Storm Drain Repl | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 740000 | 1641278.9999 | 2020-08-07 08:00 | FY21 | Q1 | 2021-02-18 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B13116 | Lobrico Ct (615) Storm Drain | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 700999.9999 | 1632093.9998 | 2020-05-06 08:00 | FY20 | Q4 | 2020-11-12 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B14078 | Jamacha Drainage Channel Upgrade | TSW | Design Bid Build | 2567999.8398 | 3529999.8397 | 2020-07-15 08:00 | FY21 | Q1 | 2020-12-09 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B14108 | Uptown Storm Drain Replacement | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 3419000 | 4374999.9999 | 2020-11-02 08:00 | FY21 | Q2 | 2021-05-10 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Oriqat, Mahmoud | #N/A
B15029 | Navajo Storm Drains | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 1587999.9898 | 2839245 | 2020-06-17 16:00 | FY20 | Q4 | 2020-12-24 16:00 | FY21 | Q2 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B15051 | Logan Heights LID (South) | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 2705000 | 4315999.9999 | 2020-03-05 08:00 | FY20 | Q3 | 2020-09-01 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B15063 | Storm Drain Group 1013 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 696000 | 1784999.9997 | 2020-11-09 08:00 | FY21 | Q2 | 2021-04-29 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Oriqat, Mahmoud | #N/A
B15165 | Golden Hill & South Park SD Replacement | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 838200 | 1358500 | 2020-06-25 08:00 | FY20 | Q4 | 2021-01-05 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B15197 | North Park SD Replacement (North) | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 2185999.9994 | 3373999.9994 | 2020-10-05 08:00 | FY21 | Q2 | 2021-03-05 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Oriqat, Mahmoud | #N/A
B15212 | Scripps Ranch SD Repl (South) | Pollution Prevention Division | Design Bid Build | 3473000 | 4964455 | 2020-09-30 08:00 | FY21 | Q1 | 2021-02-08 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B15213 | Cherokee Point South SD & GI (SD) | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 798925 | 1818349.9973 | 2020-08-13 08:00 | FY21 | Q1 | 2021-02-24 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B15214 | Cherokee Point South SD & GI (GI) | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 900914.9998 | 1986649.9969 | 2020-08-13 08:00 | FY21 | Q1 | 2021-02-24 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B16089 | Jamacha Lomita Green Infrastructure | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 755000 | 1638000 | 2020-09-01 08:00 | FY21 | Q1 | 2021-03-02 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B16094 | Jamacha Lomita Storm Drain | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 2263000 | 3314999.9984 | 2020-06-12 08:00 | FY20 | Q4 | 2020-12-09 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B16175 | Mira Mesa South Storm Drain Replacement | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 787067.9999 | 1479567.9998 | 2020-07-16 08:00 | FY21 | Q1 | 2020-12-03 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B17143 | Storm Drain Group 763 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 546000 | 939999.9997 | 2020-08-19 08:00 | FY21 | Q1 | 2020-10-21 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Oriqat, Mahmoud | #N/A
B18117 | South Mission Beach SD Replacement | PUD Water | Design Bid Build | 10182999.9898 | 10902319.9893 | 2020-02-21 08:00 | FY20 | Q3 | 2020-07-07 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B18118 | South Mission Beach GI | PUD Water | Design Bid Build | 4473999.9955 | 5269999.9955 | 2020-02-21 08:00 | FY20 | Q3 | 2020-07-07 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Oriqat, Mahmoud | Removed
B15030 | Redwood Village Standpipe Main Replcm. | PUD Water | Design Bid Build | 1064424 | 1350919.9994 | 2020-12-09 08:00 | FY21 | Q2 | 2021-02-04 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Salem, Nicole | #N/A
B15103 | Green Infrastructure Group 1027 | PUD Sewer | Design Bid Build | 1105000 | 1609000 | 2020-08-14 08:00 | FY21 | Q1 | 2021-02-09 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Salem, Nicole | Removed
B10089 | La Jolla Pkwy/Mt Soledad Erosion Control | Parks & Recreation Department | Design Bid Build | 1519920 | 2584522.9997 | 2020-08-04 08:00 | FY21 | Q1 | 2020-12-30 08:00 | FY21 | Q2 | Architectural Engineering & Parks Division | No | N | Schroth-Nichols, Elizabeth | Removed
B17110 | Bermuda Ave Coastal Access Replacement | Parks & Recreation Department | Design Bid Build | 599999.9988 | 1499999.9984 | 2020-08-20 08:00 | FY21 | Q1 | 2020-12-11 08:00 | FY21 | Q2 | Architectural Engineering & Parks Division | No | N | Schroth-Nichols, Elizabeth | #N/A
B19001 | MLK Rec Center Moisture Intrusion | Parks & Recreation Department | Design Bid Build | 1020093 | 1868351.9994 | 2020-03-30 08:00 | FY20 | Q3 | 2020-08-10 08:00 | FY21 | Q1 | Architectural Engineering & Parks Division | No | N | Schroth-Nichols, Elizabeth | Removed
B00395 | Sewer & AC Water Group 794 (S) | PUD Sewer | Design Bid Build | 6326130 | 7326453.9997 | 2020-09-17 08:00 | FY21 | Q1 | 2021-03-15 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B00406 | Sewer Group 806 | PUD Sewer | Design Bid Build | 1224988.9999 | 1941557.9969 | 2020-06-11 08:00 | FY20 | Q4 | 2020-12-15 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Sleiman, Alex | Removed
B13232 | Sewer Group 836 | PUD Sewer | Design Bid Build | 2999999.9992 | 5106565.9989 | 2020-10-08 08:00 | FY21 | Q2 | 2021-01-14 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B15099 | Serra Mesa Storm Drain & GI (SD) | Pollution Prevention Division | Design Bid Build | 2557999.9988 | 3374796.9983 | 2020-10-05 08:00 | FY21 | Q2 | 2021-03-04 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Sleiman, Alex | Removed
B15100 | Serra Mesa Storm Drain & GI (GI) | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 1529999.9993 | 2050426.4636 | 2020-07-08 08:00 | FY21 | Q1 | 2020-12-02 08:00 | FY21 | Q2 | Right-of-Way Division | No | N | Sleiman, Alex | Removed
B16041 | Sewer & AC Water Group 794 (W) | PUD Sewer | Design Bid Build | 1179000 | 1427999.9998 | 2020-09-17 08:00 | FY21 | Q1 | 2021-03-15 08:00 | FY21 | Q3 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B19199 | AC Water Group 1023A | PUD Water | Design Bid Build | 799999.9981 | 995999.9979 | 2020-09-03 08:00 | FY21 | Q1 | 2021-04-02 08:00 | FY21 | Q4 | Right-of-Way Division | No | N | Sleiman, Alex | Removed
B17082 | Lakeside Valve Station Replacement | PUD Water | Design Bid Build | 10955999.8608 | 17906999.8503 | 2021-01-04 08:00 | FY21 | Q3 | 2021-07-01 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Ammerlahn, Parita | #N/A
B15209 | Torrey Highlands & Rancho PQ SD Repl | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 2700000 | 4174999.9998 | 2021-01-21 08:00 | FY21 | Q3 | 2021-07-27 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Ashrafzadeh, Mastaneh | #N/A
B18017 | 73rd St-El Cajon Bl to Saranac-Sidewalk | Transportation Engineering & Operations Division | Design Bid Build | 275000 | 525195.9998 | 2021-05-25 08:00 | FY21 | Q4 | 2021-10-25 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Ashrafzadeh, Mastaneh | #N/A
S16027 | Morena Pipeline | PUD Water | Design Bid Build | 27058955.955 | 38173391.9332 | 2021-05-17 08:00 | FY21 | Q4 | 2021-10-14 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Batta, Nabil | Removed
B16022 | College Areas Swr & AC Wtr Main Repl (W) | PUD Water | Design Bid Build | 896283.9993 | 1414183.999 | 2021-05-03 08:00 | FY21 | Q4 | 2021-11-01 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B16025 | College Areas Swr & AC Wtr Main Repl (S) | PUD Sewer | Design Bid Build | 2645301.9987 | 3707426.9983 | 2021-05-03 08:00 | FY21 | Q4 | 2021-11-01 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B18071 | Sewer & AC Water Group 765A (W) | PUD Water | Design Bid Build | 5580141.986 | 7395141.9854 | 2021-04-30 08:00 | FY21 | Q4 | 2021-11-01 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B18073 | Sewer & AC Water Group 765A (S) | PUD Sewer | Design Bid Build | 6907707.9827 | 9121707.982 | 2021-04-30 08:00 | FY21 | Q4 | 2021-11-01 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B18089 | AC Water & Sewer Group 1049 (W) | PUD Water | Design Bid Build | 8503100 | 12634199.9949 | 2021-07-15 08:00 | FY22 | Q1 | 2021-12-23 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B18090 | AC Water & Sewer Group 1050 (W) | PUD Water | Design Bid Build | 5121200 | 7511199.9987 | 2021-02-01 08:00 | FY21 | Q3 | 2021-08-02 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B18094 | AC Water & Sewer Group 1050 (S) | PUD Sewer | Design Bid Build | 2346300 | 3441199.9994 | 2021-02-01 08:00 | FY21 | Q3 | 2021-08-02 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B18097 | AC Water & Sewer Group 1049 (S) | PUD Sewer | Design Bid Build | 2399400 | 3471999.9987 | 2021-07-15 08:00 | FY22 | Q1 | 2021-12-23 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Bose, Sheila | #N/A
B19120 | La Jolla Improv 1 (W) | PUD Water | Design Bid Build | 2863100 | 4199300 | 2021-10-15 08:00 | FY22 | Q2 | 2022-04-28 08:00 | FY22 | Q4 | Capital Asset Management | No | N | Diab, Joseph | #N/A
S10119 | North Pacific Beach Lifeguard Station | Fire-Rescue Department (Lifeguard) | Design Bid Build | 6397599.9963 | 7257599.9941 | 2021-01-29 08:00 | FY21 | Q3 | 2021-08-09 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Grani, Jason | #N/A
B18080 | Mira Mesa Library HVAC and Foundation | Library Department | Design Build | 356999.9997 | 627999.9995 | 2021-04-27 08:00 | FY21 | Q4 | 2021-11-02 08:00 | FY22 | Q2 | Capital Asset Management | No | N | James, Alaine | #N/A
B19161 | Santa Clara Pt South Prkng Lot Imprvemts | Parks & Recreation Department | Design Bid Build | 984000 | 1629999.9996 | 2021-05-03 08:00 | FY21 | Q4 | 2021-09-01 08:00 | FY22 | Q1 | Capital Asset Management | No | N | James, Alaine | Removed
L18001 | Chollas Lake Improvements | Parks & Recreation Department | Design Bid Build | 421080 | 739999.9998 | 2021-01-27 08:00 | FY21 | Q3 | 2021-07-26 08:00 | FY22 | Q1 | Capital Asset Management | No | N | James, Alaine | #N/A
B16090 | Kearny Mesa East Green Infrastructure | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 2145000 | 3334336.9493 | 2021-04-12 08:01 | FY21 | Q4 | 2021-09-29 08:01 | FY22 | Q1 | Right-of-Way Division | No | N | Jaro, Janice | #N/A
B18092 | AC Water & Sewer Group 1052 (W) | PUD Water | Design Bid Build | 4694999.953 | 6572999.9523 | 2021-05-05 08:00 | FY21 | Q4 | 2021-11-03 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Jaro, Janice | #N/A
B18096 | AC Water & Sewer Group 1052 (S) | PUD Sewer | Design Bid Build | 3546999.9399 | 4965799.9393 | 2021-05-05 08:00 | FY21 | Q4 | 2021-11-03 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Jaro, Janice | #N/A
B18215 | Damon Ave Water Main Extension & AC Repl | PUD Water | Design Bid Build | 662000 | 1340199.9996 | 2021-02-05 08:00 | FY21 | Q3 | 2021-08-11 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Jaro, Janice | #N/A
S13008 | Mohnike Adobe and Barn Restoration | Parks & Recreation Department | Design Bid Build | 1950000 | 2697000 | 2021-06-01 08:00 | FY21 | Q4 | 2021-11-01 08:00 | FY22 | Q2 | Architectural Engineering & Parks Division | No | N | Lewis, Nikki | #N/A
S16032 | Solana Highlands NP-Comfort Station | Parks & Recreation Department | Design Bid Build | 967000 | 1650266 | 2021-01-04 08:00 | FY21 | Q3 | 2021-07-02 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Lewis, Nikki | Removed
S16033 | Carmel Knoll NP-Comfort Station | Parks & Recreation Department | Design Bid Build | 572499.9998 | 978728.9996 | 2021-01-04 08:00 | FY21 | Q3 | 2021-07-02 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Lewis, Nikki | Removed
S16038 | Carmel Grove NP-Comfort Station | Parks & Recreation Department | Design Bid Build | 940999.9993 | 1561531.9988 | 2021-01-04 08:00 | FY21 | Q3 | 2021-07-02 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Lewis, Nikki | Removed
S16039 | Carmel Mission NP Comfort Station Develo | Parks & Recreation Department | Design Bid Build | 572498.9997 | 978728.9993 | 2021-01-04 08:00 | FY21 | Q3 | 2021-07-01 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Lewis, Nikki | Removed
B18234 | North Cove Comfort Station Imp | Parks & Recreation Department | Design Bid Build | 680020 | 1226999.9997 | 2021-03-18 08:00 | FY21 | Q3 | 2021-09-14 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Lozano, Edgar | #N/A
B17102 | North Park Mini Park Ped Improvements | Transportation and Storm Water Department - Street Division | Design Bid Build | 1699899.9958 | 2844166.9946 | 2020-05-01 08:00 | FY20 | Q4 | 2021-08-31 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Nutter, Daniel | Removed
B18157 | Thermal Ave-Donax Av to Palm Ave Sidwlk | Transportation and Storm Water Department - Street Division | Design Bid Build | 1172499.9998 | 1609099.9998 | 2021-03-01 08:00 | FY21 | Q3 | 2021-09-01 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Nutter, Daniel | #N/A
B19016 | Tecolote South Playground Improvements | Parks & Recreation Department | Design Bid Build | 1598400 | 3026999.9984 | 2020-01-02 08:00 | FY20 | Q3 | 2021-09-20 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Oliver, Kevin | Removed
L16002.1 | Mira Mesa Pool & Skate Plaza Ph2 | Parks & Recreation Department | Design Bid Build | 19024999.9886 | 29682999.9789 | 2021-02-22 08:00 | FY21 | Q3 | 2021-08-23 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Oliver, Kevin | #N/A
B18015 | University Avenue Culvert Reconstruction | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 700000 | 1129999.9999 | 2021-09-15 08:00 | FY22 | Q1 | 2022-03-28 08:00 | FY22 | Q3 | Right-of-Way Division | No | N | Oriqat, Mahmoud | #N/A
B12096 | Highland & Monroe Aves Storm Drain Repl | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 1585999.9492 | 2168870.8734 | 2020-01-21 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | N, per senior | Oriqat, Mahmoud | Removed
B19132 | Hard Court (basketball) Repaving 6 Locs | Parks & Recreation Department | Design Bid Build | 1028699.9996 | 1455999.9992 | 2021-06-01 08:00 | FY21 | Q4 | 2022-01-03 08:00 | FY22 | Q3 | Architectural Engineering & Parks Division | No | N | Schroth-Nichols, Elizabeth | #N/A
L14005.1 | Demolition of Loma Land Structures | Parks & Recreation Department | Design Bid Build | 319999.9993 | 834999.9958 | 2020-12-30 08:00 | FY21 | Q2 | 2021-07-01 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Schroth-Nichols, Elizabeth | #N/A
L14005.2 | Hillside Drainage Improvements | Parks & Recreation Department | Design Bid Build | 2399999.9995 | 3999999.9993 | 2021-01-04 08:00 | FY21 | Q3 | 2021-07-06 08:00 | FY22 | Q1 | Architectural Engineering & Parks Division | No | N | Schroth-Nichols, Elizabeth | Removed
S15034 | Junipero Serra Museum ADA Improvements | Parks & Recreation Department | To Be Determined | 1169104 | 2267766.9991 | 2021-05-25 08:00 | FY21 | Q4 | 2021-10-13 08:00 | FY22 | Q2 | Architectural Engineering & Parks Division | No | N | Schroth-Nichols, Elizabeth | #N/A
B00032 | Water Group 525C | PUD Water | Multiple Award Construction Contract | 3020000 | 4132073.8949 | 2020-12-28 08:00 | FY21 | Q2 | 2021-11-02 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B15093 | Seminole Drive UUP (Stanley to Estelle) | TSW | Design Bid Build | 38249.9997 | 44999.9997 | 2020-02-03 08:00 | FY20 | Q3 | 2020-05-07 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Qasem, Labib | On Schedule
B16145 | Sewer & AC Water Crown Point West (S) | PUD Sewer | Design Bid Build | 10436000 | 13438691.1271 | 2019-03-25 08:00 | FY19 | Q3 | 2020-02-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex | On Schedule
B16144 | Sewer & AC Water Crown Point West (W) | PUD Sewer | Design Bid Build | 6403000 | 8586546.6182 | 2019-03-25 08:00 | FY19 | Q3 | 2020-02-03 08:00 | FY20 | Q3 | Right-of-Way Division | No | Y | Sleiman, Alex | On Schedule
B17104 | Sewer & AC Water Group 1032 (S) | PUD Sewer | Design Bid Build | 6389000 | 8517999.9989 | 2020-02-27 08:00 | FY20 | Q3 | 2020-06-24 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice | On Schedule
B17105 | Sewer & AC Water Group 1032 (W) | PUD Sewer | Design Bid Build | 7071000 | 9427999.9984 | 2020-02-27 08:00 | FY20 | Q3 | 2020-06-24 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice | On Schedule
B16037 | Sewer & AC Water Group 841(S) | PUD Water | Design Bid Build | 1708355.9498 | 2819294.5727 | 2019-07-25 08:00 | FY20 | Q1 | 2019-12-09 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Bose, Sheila | Awarded
B18072 | Sewer & AC Water Group 841(W) | PUD Water | Design Bid Build | 1101094 | 1801836.9525 | 2019-07-25 | FY20 | Q1 | 2019-12-09 08:00 | FY20 | Q2 | Right-of-Way Division | No | Y | Bose, Sheila | Awarded
B00369 | Sewer and AC Water Group 765 (S) | PUD Sewer | Design Bid Build | 2361197.9995 | 3347431.9825 | 2020-01-03 08:00 | FY20 | Q3 | 2020-06-15 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila | On Schedule
B17167 | Sewer and AC Water Group 765 (W) | PUD Water | Design Bid Build | 2841405.997 | 3771727.9734 | 2020-01-07 08:00 | FY20 | Q3 | 2020-06-12 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Bose, Sheila | On Schedule
B00409 | SEWER GJ 798C | PUD Sewer | Design Bid Build | 212419.9997 | 484379.9995 | 2020-05-07 08:00 | FY20 | Q4 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole | On Schedule
B16034 | Sewer Group 776A | PUD Sewer | Design Bid Build | 4146513.9971 | 5771975.9146 | 2020-02-18 08:00 | FY20 | Q3 | 2020-06-08 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice | On Schedule
B16030 | Sidewalk Replacement Group 1604 | TSW | Design Bid Build | 820594 | 1390209.9599 | 2019-05-31 08:00 | FY19 | Q4 | 2019-09-25 08:00 | FY20 | Q1 | TSW Streets | No | Y | Hoenes, Craig | Awarded
B00131 | Water Group 525E | PUD Water | Multiple Award Construction Contract | 3000000 | 4112655.015 | 2020-12-28 08:00 | FY21 | Q2 | 2021-11-02 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B18088 | AC Water & Sewer Group 1048 (W) | PUD Water | Design Bid Build | 0 | 574799.9996 | 2021-02-01 08:00 | FY21 | Q3 | 2021-08-02 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B18095 | AC Water & Sewer Group 1048 (S) | PUD Sewer | Design Bid Build | 4537799.9848 | 6655499.9832 | 2021-02-01 08:00 | FY21 | Q3 | 2021-08-02 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B18204 | Scripps Ranch Improv 1 (S) | PUD Sewer | Design Bid Build | 2035300 | 3052499.9995 | 2021-03-24 08:00 | FY21 | Q3 | 2021-09-27 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B18208 | Scripps Ranch Improv 1 (W) | PUD Water | Design Bid Build | 2313800 | 3516999.9994 | 2021-03-24 08:00 | FY21 | Q3 | 2021-09-27 08:00 | FY22 | Q1 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B19086 | University City Improv 1 (W) | PUD Water | Design Bid Build | 3982800 | 5256399.999 | 2021-06-01 08:00 | FY21 | Q4 | 2021-12-01 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B19087 | University City Improv 1 (S) | PUD Sewer | Design Bid Build | 3503600 | 4951799.9993 | 2021-06-01 08:00 | FY21 | Q4 | 2021-12-01 08:00 | FY22 | Q2 | Right-of-Way Division | No | N | Sleiman, Alex | #N/A
B15073 | Bonita Direct Transfer PS | PUD Water | Design Bid Build | 8139999.8028 | 13315372.799 | 2021-12-30 08:00 | FY22 | Q2 | 2022-05-31 08:00 | FY22 | Q4 | Architectural Engineering & Parks Division | No | N | Van Martin, Debbie | Removed
B16113 | Mission Hills NE Storm Drain Replacement | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 3035723.9986 | 5133730.9986 | 2021-03-30 08:00 | FY21 | Q3 | 2022-10-10 08:00 | FY23 | Q2 | Right-of-Way Division | No | N | Bose, Sheila | Removed
B19106 | Bay Ho Improv 2 (W) | PUD Water | Design Bid Build | 5131400 | 7033599.9995 | 2022-07-01 08:00 | FY23 | Q1 | 2022-12-30 08:00 | FY23 | Q2 | Capital Asset Management | No | N | Diab, Joseph | #N/A
S19003 | UCSD Fire Station and ROW Improvements | Fire-Rescue Department (FS) | Design Build | 16435000 | 21820997.5466 | 2021-05-03 08:00 | FY21 | Q4 | 2022-08-29 08:00 | FY23 | Q1 | Architectural Engineering & Parks Division | No | N | Grani, Jason | Removed
S15027 | La Jolla View Reservoir | PUD Water | Design Bid Build | 18200000.069 | 27000313.7339 | 2022-04-04 08:00 | FY22 | Q4 | 2022-09-22 08:00 | FY23 | Q1 | Architectural Engineering & Parks Division | No | N | Van Martin, Debbie | #N/A
B19011 | Trench Paving Group 1901 | Transportation and Storm Water Department - Street Division | Design Bid Build | 110000 | 123500 | 2019-07-10 08:00 | FY20 | Q1 | 2019-07-10 08:00 | FY20 | Q1 | Right-of-Way Division | No | N, not CIP project per senior | Zhang, Dayue | Awarded
B19125 | Citywide Street Lights 1950 |  |  | 1365000 | 1570000 | 2019-10-21 | FY20 | Q2 | 2019-12-16 | FY20 | Q2 | TSW | No | N, this project is no longer active in P6 | Hoenes, Craig | On Schedule
S12022 | Convention Center Phase III Expansion | Special Promotional Programs | Construction Manager at Risk | 0 | 0 | 2020-02-03 08:00 | FY20 | Q3 | 2020-02-03 08:00 | FY20 | Q3 | Capital Asset Management | No | N | Cetin, Elif | Removed
B19012 | Sidewalk Replacement Group 1901-NP & OB | TSW | Design Bid Build | 1450000 | 1643215.79 | 2020-03-03 08:00 | FY20 | Q3 | 2020-06-18 08:00 | FY20 | Q4 | TSW Streets | No | Y | Hoenes, Craig | On Schedule
B19007.1 | SP17 JOC North Task 1 - Scripps Poway Parkway | TSW | Job Order Contract | 5000000 | 5500000 | 2019-06-15 | FY19 | Q4 | 2020-06-30 | FY20 | Q4 | TSW | No | Y | Lahmann, Joshua | On Schedule
B19007.2 | SP17 JOC North Task 2 - Pomerado/Poway Rd/Clairemont |  |  | 5000000 | 5500000 | 2020-06-30 | FY20 | Q4 | 2019-11-17 | FY20 | Q2 | #N/A | No | Y | Lahmann, Joshua | On Schedule
B19008.1 | SP17 JOC South Task 1 - Fairmount Ave/Montezuma | TSW | Job Order Contract | 5000000 | 5500000 | 2019-06-01 | FY19 | Q4 | 2020-06-30 | FY20 | Q4 | TSW | No | Y | Lahmann, Joshua | On Schedule
B19008.2 | SP17 JOC South Task 2 - Harbor Dr/Picador |  |  | 5000000 | 5500000 | 2020-06-30 | FY20 | Q4 | 2019-10-20 | FY20 | Q2 | #N/A | No | Y | Lahmann, Joshua | On Schedule
B15028 | Storm Drain Group 968 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 131000 | 281000 | 2020-03-18 | FY20 | Q3 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole | On Schedule
B18134 | Street Paving Group 1901 | TSW | Design Bid Build | 11000000 | 12550000 | 2019-10-21 | FY20 | Q2 | 2019-12-09 | FY20 | Q2 | #N/A | No | Y | Lahmann, Joshua | On Schedule
B18135 | Street Paving Group 1902 | TSW | Design Bid Build | 11000000 | 12550000 | 2019-10-30 | FY20 | Q2 | 2019-12-19 | FY20 | Q2 | #N/A | No | Y | Lahmann, Joshua | On Schedule
B18220 | DeAnza North Parking Lot Improvements | Parks & Recreation Department | Design Bid Build | 579000 | 870166.9999 | 2020-05-28 08:00 | FY20 | Q4 | 2020-07-09 08:00 | FY21 | Q1 | Architectural Engineering & Parks Division | No | N | Lewis, Nikki | Removed
B19211 | Street Paving Group 1903 |  |  | 11000000 | 12550000 | 2019-12-30 | FY20 | Q2 | 2020-02-28 | FY20 | Q3 | #N/A | No | Y | Lahmann, Joshua | On Schedule
B19195 | Street Resurfacing Mission Bay | TSW | Job Order Contract | 4975999.9929 | 6535999.9926 | 2019-11-13 | FY20 | Q2 | 2020-02-11 | FY20 | Q3 | Capital Asset Management | No | Y | James, Alaine | Awarded
B17150 | Pipeline Rehabilitation AR-1 | PUD Sewer | Design Bid Build | 3946999.996 | 4812999.996 | 2019-10-02 | FY20 | Q2 | 2020-09-10 08:00 | FY21 | Q1 | Right-of-Way Division | No | N | Salem, Nicole | Awarded
S16036 | Torrey Highlands Neighborhood Park Upgra | Parks & Recreation Department | Design Bid Build | 659999.9996 | 1027937.9996 | 2019-10-02 08:00 | FY20 | Q2 | 2020-03-06 08:00 | FY20 | Q3 | Architectural Engineering & Parks Division | No | Y | Oliver, Kevin | On Schedule
B18031 | Ultraviolet Disinfection System Replace | PUD Sewer | Design Bid Build | 3391636 | 4544155.9989 | 2019-02-01 08:00 | FY19 | Q3 | 2019-07-22 08:00 | FY20 | Q1 | Architectural Engineering & Parks Division | No | Y | Vitelle, Brian | Awarded
S16048 | Villa Monserate Neigh Park Upgrades | Parks & Recreation Department | Design Bid Build | 887184 | 1707221.0378 | 2019-10-29 08:00 | FY20 | Q2 | 2020-04-30 08:00 | FY20 | Q4 | Architectural Engineering & Parks Division | No | Y | Mahmalji, Samir | On Schedule
B14099 | Water Group 968 | PUD Water | Design Bid Build | 2152300 | 3182499.9996 | 2020-03-18 | FY20 | Q3 | 2020-06-30 | FY20 | Q4 | Right-of-Way Division | No | Y | Salem, Nicole | On Schedule
B18075 | Water Group 970 CI | PUD Water | Design Bid Build | 6154699.9178 | 9970644.9128 | 2019-10-11 08:00 | FY20 | Q2 | 2020-05-08 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Jaro, Janice | On Schedule
B18138 | Wightman (Chamoune -Euclid) Rd Imp UU388 | Street Division | Design Bid Build | 123367.07 | 166545.54 | 2020-01-13 08:00 | FY20 | Q3 | 2020-05-22 08:00 | FY20 | Q4 | Right-of-Way Division | No | Y | Zhang, Dayue | On Schedule

## On FY21 Award List-hide (hidden)
Project Number | Project Name (Text) | Asset Managing Department | Contract Type | Estimated Total Contract Cost ($) | Estimated Total Project Cost ($) | Contract Bid - Start (5010) | Fiscal Year Advertising | Quarter Advertising | LNTP (6010) | Fiscal Year Awarding | Quarter Awarding | Responsible Division | On FY21 Award List | Include in FY20 Mid Year List? | Design Section Head
B18036 | Intelligent Cities Outdoor Lightng Proj2 | Sustainability Department | Design Bid Build | 9000000 | 30000000 | 2019-11-13 | FY20 | Q2 | 2020-09-01 | FY21 | Q1 | #N/A | Yes | N | Sayed, Arwa
B19204 | AC Water & Sewer Group 1023B | PUD Water | Design Bid Build | 199999.9995 | 325999.9994 | 2020-03-30 | FY20 | Q3 | 2020-07-30 | FY21 | Q1 | Right-of-Way Division | Yes | N | Sleiman, Alex
B19205 | AC Water & Sewer Group 1023B | PUD Water | Design Bid Build | 1999999.9953 | 2940999.9951 | 2020-03-30 | FY20 | Q3 | 2020-07-30 | FY21 | Q1 | Right-of-Way Division | Yes | N | Sleiman, Alex
240033324 | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | #N/A | Architectural Engineering & Parks Division | No | N | #N/A
B00156 | Pomerado Park Reservoir Upgrade | PUD Water | Design Bid Build | 4875000 | 6888000 | 2020-09-04 | FY21 | Q1 | 2021-03-08 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Van Martin, Debbie
B00374 | Sewer & AC Water Group 763 (S) | PUD Water | Design Bid Build | 4080279.9898 | 5720816.9895 | 2020-06-01 | FY20 | Q4 | 2020-12-01 | FY21 | Q2 | Right-of-Way Division | Yes | N | Jaro, Janice
B00394 | Sewer and AC Water Group 793 (S) | PUD Sewer | Design Bid Build | 5305291 | 6624610.9997 | 2020-10-23 | FY21 | Q2 | 2021-03-24 | FY21 | Q3 | Right-of-Way Division | Yes | N | Bose, Sheila
B00426 | Sewer and AC Water Group 812 (S) | PUD Water | Design Bid Build | 3047000 | 4030000 | 2020-09-14 | FY21 | Q1 | 2021-03-18 | FY21 | Q3 | Right-of-Way Division | Yes | N | Bose, Sheila
B00431 | MISSION CTR CNYN A SMR | PUD Sewer | Design Bid Build | 2164499.9958 | 3188599.9951 | 2020-06-03 | FY20 | Q4 | 2020-11-27 | FY21 | Q2 | Right-of-Way Division | Yes | N | Bose, Sheila
B00434 | SEWER GROUP 828 | PUD Sewer | Design Bid Build | 4807950 | 6744100.4581 | 2020-12-01 | FY21 | Q2 | 2021-04-30 | FY21 | Q4 | Right-of-Way Division | Yes | N | Sleiman, Alex
B12001 | Stlight Design & Install 30th St - Ocean | TSW | Job Order Contract | 107100 | 125999.9996 | 2020-06-09 | FY20 | Q4 | 2020-09-11 | FY21 | Q1 | Right-of-Way Division | Yes | N | Qasem, Labib
B12048 | Water & Sewer Group 965 (S) | PUD Sewer | Design Bid Build | 1855399.9945 | 2932599.9942 | 2020-10-08 | FY21 | Q2 | 2021-04-21 | FY21 | Q4 | Right-of-Way Division | Yes | N | Sleiman, Alex
B12057 | Water & Sewer Group 965 (W) | PUD Water | Design Bid Build | 1769499.9913 | 2934599.991 | 2020-10-08 | FY21 | Q2 | 2021-04-21 | FY21 | Q4 | Right-of-Way Division | Yes | N | Sleiman, Alex
B13010 | Signal Mods in Barrio Logan | TSW | Design Bid Build | 190899.9986 | 299999.9985 | 2020-03-06 | FY20 | Q3 | 2020-09-14 | FY21 | Q1 | Right-of-Way Division | Yes | N | Qasem, Labib
B13102 | Adams Ave (1620) Storm Drain Replacement | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 499999.9832 | 867999.9832 | 2020-09-11 | FY21 | Q1 | 2021-03-16 | FY21 | Q3 | Right-of-Way Division | Yes | N | Oriqat, Mahmoud
B15047 | Division St & Osborn St Traffic Signal | TSW | Design Bid Build | 212199.9986 | 274999.9986 | 2021-02-02 | FY21 | Q3 | 2021-06-30 | FY21 | Q4 | Right-of-Way Division | Yes | N | Qasem, Labib
B15065 | Pacific Beach TS Interconnect Upgrade | Transportation and Storm Water Department - Street Division | Job Order Contract | 933030 | 1841618.999 | 2020-02-03 | FY20 | Q3 | 2020-07-30 | FY21 | Q1 | Right-of-Way Division | Yes | N | Qasem, Labib
B15070 | Sewer and AC Water Group 793 (W) | PUD Water | Design Bid Build | 677900 | 964699.9999 | 2020-10-23 | FY21 | Q2 | 2021-03-24 | FY21 | Q3 | Right-of-Way Division | Yes | N | Bose, Sheila
B15084 | Block 1M1 UUP (La Jolla) | TSW | Job Order Contract | 252449.9994 | 296999.9994 | 2020-06-08 | FY20 | Q4 | 2020-09-10 | FY21 | Q1 | Right-of-Way Division | Yes | N | Qasem, Labib
B15096 | Hancock Street UUP (Witherby to Tourquoi | TSW | Job Order Contract | 53550 | 63000 | 2020-06-08 | FY20 | Q4 | 2020-09-10 | FY21 | Q1 | Right-of-Way Division | Yes | N | Qasem, Labib
B15098 | Block 2S2 UUP | TSW | Job Order Contract | 260100 | 306000 | 2020-06-12 | FY20 | Q4 | 2020-09-16 | FY21 | Q1 | Right-of-Way Division | Yes | N | Qasem, Labib
B15139 | North City Pure Water Facility | Public Utilities | Design Bid Build | 388927000 | 493083000 | 2020-08-07 | FY21 | Q1 | 2021-02-09 | FY21 | Q3 | PUD Pure Water | Yes | N | Barhoumi, Amer
B15140 | North City Pure Water Pump Station | PUD Water | Design Bid Build | 12709200 | 19997559 | 2020-08-07 | FY21 | Q1 | 2021-02-18 | FY21 | Q3 | PUD Pure Water | Yes | N | Llagas, Margaret
B15141 | NC Morena Blvd Pump Stations & Pipelines | PUD Water | Design Bid Build | 90000000 | 100000000 | 2020-09-08 | FY21 | Q1 | 2021-02-01 | FY21 | Q3 | Right-of-Way Division | Yes | N | Batta, Nabil
B15141.3 | Morena Conveyance Northern Segment - B3 | PUD Water | Design Bid Build | 98047703 | 122559629 | 2020-08-07 | FY21 | Q1 | 2021-01-10 | FY21 | Q3 | #N/A | Yes | N | Batta, Nabil
B15142.2 | NCWRP Expansion (Pkg. 2) | Public Utilities | Design Bid Build | 148300000 | 192790000 | 2020-12-11 | FY21 | Q2 | 2021-06-07 | FY21 | Q4 | #N/A | Yes | N | Barhoumi, Amer
B15203 | Tecolote Cyn GC Water Conn | PUD Water | Design Bid Build | 228999.9983 | 277999.9983 | 2020-11-13 | FY21 | Q2 | 2021-05-10 | FY21 | Q4 | Right-of-Way Division | Yes | N | Salem, Nicole
B16017 | Pressure Reducing Stations Upgrades Phs1 | PUD Water | Design Bid Build | 3739999.9907 | 6289999.9889 | 2020-11-16 | FY21 | Q2 | 2021-02-17 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Vitelle, Brian
B16035 | North City Pure Water Pipeline | PUD Water | Design Bid Build | 80421961 | 121995876 | 2020-11-27 | FY21 | Q2 | 2021-04-08 | FY21 | Q4 | PUD Pure Water | Yes | N | Llagas, Margaret
B16100 | ADA S/W Group 3E W Point Loma | Development Services Department | Design Bid Build | 538000 | 1139502 | 2020-06-30 | FY19 | Q4 | 2020-12-31 | FY20 | Q2 | Right-of-Way Division | Yes | N | Ashrafzadeh, Mastaneh
B16112 | Southcrest Green Infrastructure (GI) | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 3007000 | 4500000 | 2020-07-14 | FY21 | Q1 | 2021-01-13 | FY21 | Q3 | Right-of-Way Division | Yes | N | Bose, Sheila
B16140 | NCPWF Influent Pump Station and Pipeline | Public Utilities | Design Bid Build | 27400000 | 39000000 | 2020-12-11 | FY21 | Q2 | 2021-06-07 | FY21 | Q4 | PUD Pure Water | Yes | N | Barhoumi, Amer
B16155 | Storm Drain Group 828 | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 1840150 | 3000000.272 | 2020-12-01 | FY21 | Q2 | 2021-04-30 | FY21 | Q4 | Right-of-Way Division | Yes | N | Sleiman, Alex
B16158 | Otay 2nd Pipeline Phase 3 | PUD Water | Design Bid Build | 10115999.9984 | 12635999.9984 | 2020-09-23 | FY21 | Q1 | 2021-03-30 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Ammerlahn, Parita
B17003 | El Cajon Bl-Highland-58th Improv | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 643000 | 1215050 | 2020-05-31 | FY20 | Q4 | 2020-12-01 | FY21 | Q2 | Right-of-Way Division | Yes | N | Nutter, Daniel
B17005 | Murphy Canyon Trunk Sewer Repair/Rehab | PUD Sewer | Design Bid Build | 12378316.9778 | 16393109.958 | 2020-10-21 | FY21 | Q2 | 2021-03-22 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Vitelle, Brian
B17006 | San Diego NC-MBC Improvements | Public Utilities | Design Bid Build | 2410800 | 3262000 | 2020-12-29 | FY21 | Q2 | 2021-06-07 | FY21 | Q4 | PUD Pure Water | Yes | N | Barhoumi, Amer
B17012 | Mt Acadia (Mt Alifan-Mt Burnham)SL UU621 | TSW | Job Order Contract | 205200 | 228000 | 2020-08-13 | FY21 | Q1 | 2020-09-15 | FY21 | Q1 | Right-of-Way Division | Yes | N | Qasem, Labib
B17013 | Seminole PH2 (El Cajon-Stanley) SL UU630 | TSW | Job Order Contract | 108000 | 120000 | 2020-08-12 | FY21 | Q1 | 2020-09-14 | FY21 | Q1 | Right-of-Way Division | Yes | N | Qasem, Labib
B17050 | Citywide Street Lights Group 1701 | TSW | Design Bid Build | 419499.9997 | 700599.9991 | 2020-06-24 | FY20 | Q4 | 2021-01-04 | FY21 | Q3 | Right-of-Way Division | Yes | N | Qasem, Labib
B17051 | Citywide Street Lights Group 1702 | TSW | Design Bid Build | 441199.9997 | 731499.9997 | 2020-06-24 | FY20 | Q4 | 2021-01-04 | FY21 | Q3 | Right-of-Way Division | Yes | N | Qasem, Labib
B17087 | Clairemont Mesa Sewer Pipe Replacement | PUD Sewer | Design Bid Build | 153799.9998 | 228399.9998 | 2020-08-17 | FY21 | Q1 | 2020-12-23 | FY21 | Q2 | Right-of-Way Division | Yes | N | Salem, Nicole
B17114 | Curb Ramp Improvement Group 1701 | Transportation and Storm Water Department - Street Division | Design Bid Build | 3138799.9785 | 4137599.9783 | 2020-04-15 | FY20 | Q4 | 2020-08-17 | FY21 | Q1 | Right-of-Way Division | Yes | N | Zhang, Dayue
B17115 | Sewer and AC Water Group 812 (W) | PUD Water | Design Bid Build | 1916000 | 2554999.9994 | 2020-09-14 | FY21 | Q1 | 2021-03-18 | FY21 | Q3 | Right-of-Way Division | Yes | N | Bose, Sheila
B17116 | Sewer and AC Water Group 763 (W) | PUD Water | Design Bid Build | 1349999.9972 | 1686012.9972 | 2020-06-01 | FY20 | Q4 | 2020-12-01 | FY21 | Q2 | Right-of-Way Division | Yes | N | Jaro, Janice
B17128 | Mid-City & Eastern Area Signal Mods | TSW | Design Bid Build | 389085.999 | 629859.9987 | 2021-02-18 | FY21 | Q3 | 2021-06-30 | FY21 | Q4 | Right-of-Way Division | Yes | N | Qasem, Labib
B17133 | Balboa Park Pipeline Repl Ph II (S) | PUD Sewer | Design Bid Build | 1851999.9979 | 3043650.9961 | 2020-10-30 | FY21 | Q2 | 2021-04-30 | FY21 | Q4 | Right-of-Way Division | Yes | N | Sleiman, Alex
B17140 | Balboa Park Pipeline Repl Ph II (W) | PUD Water | Design Bid Build | 3789999.9957 | 6319546.9956 | 2020-10-30 | FY21 | Q2 | 2021-04-30 | FY21 | Q4 | Right-of-Way Division | Yes | N | Sleiman, Alex
B17152 | Torrey Pines Gf-Repr Storm Drain Outfall | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 2135000 | 3359999.9977 | 2020-07-31 | FY21 | Q1 | 2020-12-31 | FY21 | Q2 | Architectural Engineering & Parks Division | Yes | N | Vitelle, Brian
B17163 | Palm Ave Storm Drain | Transportation and Storm Water Department - Storm Water Division | Job Order Contract | 288700 | 502700 | 2020-04-15 | FY20 | Q4 | 2020-08-01 | FY21 | Q1 | Right-of-Way Division | Yes | N | Ashrafzadeh, Mastaneh
B17188 | Street Reconstruction Group 1801 | Street Division | Design Bid Build | 8200000 | 12709999.997 | 2020-10-01 | FY21 | Q2 | 2021-04-02 | FY21 | Q4 | Right-of-Way Division | Yes | N | Ashrafzadeh, Mastaneh
B17189 | Sewer Group 843 | PUD Sewer | Design Bid Build | 4224399.99 | 5719299.9897 | 2020-07-07 | FY21 | Q1 | 2020-11-30 | FY21 | Q2 | Right-of-Way Division | Yes | N | Jaro, Janice
B18005 | John F Kennedy Neighborhood Park Improve | Parks & Recreation Department | Design Bid Build | 1859668 | 3079618.9988 | 2020-03-03 | FY20 | Q3 | 2020-08-15 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Mahmalji, Samir
B18063 | Sewer & AC Water Group 1034 (S) | PUD Sewer | Design Bid Build | 4968399.9574 | 6806399.9566 | 2020-11-23 | FY21 | Q2 | 2021-03-01 | FY21 | Q3 | Right-of-Way Division | Yes | N | Salem, Nicole
B18064 | Sewer & AC Water Group 1034 (W) | PUD Water | Design Bid Build | 6959099.9761 | 9201599.9754 | 2020-11-20 | FY21 | Q2 | 2021-04-30 | FY21 | Q4 | Right-of-Way Division | Yes | N | Salem, Nicole
B18087 | Convert Bldg 619 @ NTC into Rec Center | Parks & Recreation Department | Design Bid Build | 3578999.9926 | 6227999.9895 | 2020-07-02 | FY21 | Q1 | 2021-01-04 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Schroth-Nichols, Elizabeth
B18091 | AC Water & Sewer Group 1051 (W) | PUD Sewer | Design Bid Build | 776299.9962 | 1004599.9962 | 2020-10-15 | FY21 | Q2 | 2021-04-15 | FY21 | Q4 | Right-of-Way Division | Yes | N | Bose, Sheila
B18098 | AC Water & Sewer Group 1051 (S) | PUD Sewer | Design Bid Build | 3136599.9908 | 4059099.9908 | 2020-10-15 | FY21 | Q2 | 2021-04-15 | FY21 | Q4 | Right-of-Way Division | Yes | N | Bose, Sheila
B18121 | AC Water & Sewer Group 1036 (W) | PUD Sewer | Design Bid Build | 3322800 | 4300100 | 2020-12-22 | FY21 | Q2 | 2021-06-22 | FY21 | Q4 | Right-of-Way Division | Yes | N | Salem, Nicole
B18123 | AC Water & Sewer Group 1036 (S) | PUD Sewer | Design Bid Build | 525900 | 652800 | 2020-10-28 | FY21 | Q2 | 2021-05-28 | FY21 | Q4 | Right-of-Way Division | Yes | N | Salem, Nicole
B18137 | Coronado SB (27th SB-Madden)Rd Imp UU193 | TSW | Design Bid Build | 268212.8 | 337203 | 2020-09-15 | FY21 | Q1 | 2021-01-25 | FY21 | Q3 | Right-of-Way Division | Yes | N | Zhang, Dayue
B18141 | 32nd St PHII (Market-Imp.) Rd Imp UU17 | TSW | Design Bid Build | 268212.8 | 337203 | 2020-09-15 | FY21 | Q1 | 2021-01-25 | FY21 | Q3 | Right-of-Way Division | Yes | N | Zhang, Dayue
B18142 | Block 6DD1 (Clairemont Mesa)Rd Imp UU410 | TSW | Design Bid Build | 1473215 | 1884015.9994 | 2020-09-15 | FY21 | Q1 | 2021-01-25 | FY21 | Q3 | Right-of-Way Division | Yes | N | Zhang, Dayue
B18144 | 32nd St PH I (Market-F St) Rd Imp UU386 | TSW | Design Bid Build | 124122.35 | 154689 | 2020-09-15 | FY21 | Q1 | 2021-01-25 | FY21 | Q3 | Right-of-Way Division | Yes | N | Zhang, Dayue
B18147 | 31st Street (Market-L ST) Rd Imp UU11 | TSW | Design Bid Build | 286745 | 366701.9999 | 2020-09-15 | FY21 | Q1 | 2021-01-25 | FY21 | Q3 | Right-of-Way Division | Yes | N | Zhang, Dayue
B18148 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 | TSW | Design Bid Build | 109924 | 140575 | 2020-09-15 | FY21 | Q1 | 2021-01-25 | FY21 | Q3 | Right-of-Way Division | Yes | N | Zhang, Dayue
B18150 | 25th (SB) (Coronado-Grove) Rd Imp UU995 | TSW | Design Bid Build | 88173 | 112761 | 2020-09-15 | FY21 | Q1 | 2021-01-25 | FY21 | Q3 | Right-of-Way Division | Yes | N | Zhang, Dayue
B18151 | Hughes St (58th St-Jodi St) Rd Imp UU101 | TSW | Design Bid Build | 208247 | 266316.9999 | 2020-09-15 | FY21 | Q1 | 2021-01-25 | FY21 | Q3 | Right-of-Way Division | Yes | N | Zhang, Dayue
B18155 | Block 1M (La Jolla 4) Rd Imp UU659 | TSW | Design Bid Build | 817563 | 1087358 | 2020-09-15 | FY21 | Q1 | 2021-01-25 | FY21 | Q3 | #N/A | Yes | N | Zhang, Dayue
B18158 | 54th-Market to Santa margarita Sidwlk | Transportation and Storm Water Department - Street Division | Design Bid Build | 394900 | 694099.9998 | 2020-08-17 | FY21 | Q1 | 2021-02-26 | FY21 | Q3 | Right-of-Way Division | Yes | N | Ashrafzadeh, Mastaneh
B18159 | ADACA Woodman St-Cielo to Pagel Pl Sidwl | Transportation and Storm Water Department - Storm Water Division | Design Bid Build | 525261 | 926799.9998 | 2020-10-02 | FY21 | Q2 | 2021-05-03 | FY21 | Q4 | Right-of-Way Division | Yes | N | Ashrafzadeh, Mastaneh
B18197 | Talmadge AC Water Main Replacement | PUD Water | Design Bid Build | 814100 | 1194099.9997 | 2020-11-01 | FY21 | Q2 | 2021-05-03 | FY21 | Q4 | Right-of-Way Division | Yes | N | Bose, Sheila
B18200 | Clairemont Mesa E Improv 1 (W) | PUD Water | Design Bid Build | 2194500 | 2927199.9998 | 2021-02-11 | FY21 | Q3 | 2021-06-25 | FY21 | Q4 | Right-of-Way Division | Yes | N | Bose, Sheila
B18202 | Clairemont Mesa E Improv 1 (S) | PUD Sewer | Design Bid Build | 4017500 | 5327699.9996 | 2021-02-11 | FY21 | Q3 | 2021-06-25 | FY21 | Q4 | Right-of-Way Division | Yes | N | Bose, Sheila
B18212 | Pipeline Rehabilitation AY-1 | PUD Sewer | Design Bid Build | 6561800 | 7841500 | 2020-05-04 | FY20 | Q4 | 2020-10-30 | FY21 | Q2 | Right-of-Way Division | Yes | N | Bose, Sheila
B18223 | Adult Fitness Course East Shore | Parks & Recreation Department | Design Bid Build | 1059999.997 | 1953999.9962 | 2020-06-22 | FY20 | Q4 | 2020-09-22 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
B18231 | Tecolote North Parking Lot Improvements | Parks & Recreation Department | Design Bid Build | 443999.9987 | 868999.9983 | 2020-06-22 | FY20 | Q4 | 2020-09-22 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
B18232 | Tecolote North Playground Improvements | Parks & Recreation Department | Design Bid Build | 1269009.997 | 1779999.997 | 2020-06-22 | FY20 | Q4 | 2020-09-22 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
B18233 | Tecolote North Comfort Station Imp | Parks & Recreation Department | Design Bid Build | 1032299.9971 | 1962999.9961 | 2020-06-22 | FY20 | Q4 | 2020-09-22 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
B19000 | OB Dog Beach Accessibility Improvements | Parks & Recreation Department | Job Order Contract | 759805.6666 | 1143305.6661 | 2020-04-20 | FY20 | Q4 | 2020-09-08 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Schroth-Nichols, Elizabeth
B19013 | Sidewalk Replacement Group 1902-CM & LJ | TSW | Design Bid Build | 2500000 | 3000000 | 2020-05-11 | FY20 | Q4 | 2020-07-25 | FY21 | Q1 | TSW Streets | Yes | N | Hoenes, Craig
B19014 | Sidewalk Replacement Group 1903-SE & CH | TSW | Design Bid Build | 1000000 | 1400000 | 2020-06-12 | FY20 | Q4 | 2020-08-10 | FY21 | Q1 | TSW Streets | Yes | N | Hoenes, Craig
B19015 | Tecolote South Comfort Station Imp | Parks & Recreation Department | Design Bid Build | 1012320 | 1930999.999 | 2020-06-22 | FY20 | Q4 | 2020-09-22 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
B19017 | Tecolote South Parking Lot Improvements | Parks & Recreation Department | Design Bid Build | 263624.9999 | 527999.9996 | 2020-06-22 | FY20 | Q4 | 2020-09-22 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
B19021 | Crown Point Playground Improvements | Parks & Recreation Department | Design Bid Build | 1077924 | 1960000 | 2020-08-03 | FY21 | Q1 | 2021-01-02 | FY21 | Q3 | Capital Asset Management | Yes | N | Lozano, Edgar
B19022 | Crown Point Parking Lot Improvements | Parks & Recreation Department | Design Bid Build | 907500 | 1557000 | 2020-08-03 | FY21 | Q1 | 2021-01-02 | FY21 | Q3 | Capital Asset Management | Yes | N | Lozano, Edgar
B19029 | Santa Clara Playground Improvements | Parks & Recreation Department | Design Bid Build | 1377008.9948 | 1959999.9948 | 2020-06-01 | FY20 | Q4 | 2020-11-02 | FY21 | Q2 | Architectural Engineering & Parks Division | Yes | N | Lozano, Edgar
B19032 | Santa Clara Comfort Station Improvements | Parks & Recreation Department | Design Bid Build | 506136.9989 | 749999.9989 | 2020-06-01 | FY20 | Q4 | 2020-11-02 | FY21 | Q2 | Architectural Engineering & Parks Division | Yes | N | Lozano, Edgar
B19066 | SBWRP Variable Frequency Drive Repl | PUD Sewer | Design Bid Build | 104000 | 955500 | 2020-05-28 | FY20 | Q4 | 2021-03-02 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Ammerlahn, Parita
B19088 | Bay Ho Improv 1 (S) | PUD Sewer | Design Bid Build | 5068300 | 8464999.9983 | 2020-06-30 | FY20 | Q4 | 2020-12-31 | FY21 | Q2 | Right-of-Way Division | Yes | N | Jaro, Janice
B19097 | Accelerated MH Referral Group 1 | PUD Sewer | Design Bid Build | 690745 | 913547.9999 | 2020-08-17 | FY21 | Q1 | 2020-12-22 | FY21 | Q2 | Right-of-Way Division | Yes | N | Salem, Nicole
B19145 | Sewer Rehab 1051A | PUD Sewer | Design Bid Build | 126199.9994 | 178199.9993 | 2020-11-02 | FY21 | Q2 | 2021-05-03 | FY21 | Q4 | Right-of-Way Division | Yes | N | Bose, Sheila
B19159 | Sunset Point Parking Lot Improvements | Parks & Recreation Department | Job Order Contract | 249999.9992 | 449999.9992 | 2021-01-04 | FY21 | Q3 | 2021-04-06 | FY21 | Q4 | Architectural Engineering & Parks Division | Yes | N | Lewis, Nikki
B19166 | AC Water and Sewer Group 1052A (W) | PUD Water | Multiple Award Construction Contract | 3502400 | 5182899.6178 | 2020-10-01 | FY21 | Q2 | 2021-04-01 | FY21 | Q4 | Architectural Engineering & Parks Division | Yes | N | Ammerlahn, Parita
B19169 | AC Water & Sewer Group 1052A (S) | PUD Sewer | Multiple Award Construction Contract | 1923000 | 2814099.7928 | 2020-10-01 | FY21 | Q2 | 2021-04-01 | FY21 | Q4 | Architectural Engineering & Parks Division | Yes | N | Ammerlahn, Parita
B19197 | Storm Drain at MBC | PUD Sewer | Design Bid Build | 2260800 | 3481800 | 2021-01-31 | FY21 | Q3 | 2021-04-30 | FY21 | Q4 | Architectural Engineering & Parks Division | Yes | N | Vitelle, Brian
B20046 | Concrete Street Panel Repl - Coast Bl | Transportation and Storm Water Department - Street Division | Design Bid Build | 1052685.8481 | 1437263.8475 | 2020-04-15 | FY20 | Q4 | 2020-09-03 | FY21 | Q1 | Right-of-Way Division | Yes | N | Schultz, Louis
B20076 | Coast Cave SD Accelerated Replacement | Transportation and Storm Water Department - Street Division | Design Bid Build | 223094.9995 | 313422.9995 | 2020-04-15 | FY20 | Q4 | 2020-09-03 | FY21 | Q1 | Right-of-Way Division | Yes | N | Schultz, Louis
L14002.3 | Chollas Large Car Washes | Fleet Services | Design Bid Build | 1650000 | 2748369.9978 | 2020-11-02 | FY21 | Q2 | 2021-02-01 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Grani, Jason
L14002.4 | Chollas Crane Replacement | Fleet Services | Design Bid Build | 300000 | 554999.9995 | 2020-07-08 | FY21 | Q1 | 2020-09-29 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Grani, Jason
L14002.5 | Chollas Paint Booth | Fleet Services | Design Bid Build | 303000 | 665999.9994 | 2020-09-01 | FY21 | Q1 | 2021-02-01 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Grani, Jason
L14002.6 | PD Substation Small Carwashes | Fleet Services | Design Bid Build | 2200000 | 3488515.9976 | 2020-10-26 | FY21 | Q2 | 2021-02-01 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Grani, Jason
L16000.5 | Clay Street Mini Park Improvement | Parks & Recreation Department | Design Bid Build | 662999.9995 | 1228929.9993 | 2020-02-03 | FY20 | Q3 | 2020-08-12 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Mahmalji, Samir
S00319 | EMTS Boat Dock Esplanade | PUD Sewer | Design Bid Build | 2160379.9969 | 3332999.9954 | 2020-04-01 | FY20 | Q4 | 2020-10-01 | FY21 | Q2 | Architectural Engineering & Parks Division | Yes | N | Choi, Jong
S00751 | Hickman Fields Athletic Area | Parks & Recreation Department | Design Bid Build | 6689999.56 | 8928713.5599 | 2020-03-23 | FY20 | Q3 | 2020-08-05 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
S00811 | SCRIPPS MIRAMAR RANCH LIB | Library Department | Design Bid Build | 4270000 | 6076376.9181 | 2020-12-07 | FY21 | Q2 | 2021-05-24 | FY21 | Q4 | Architectural Engineering & Parks Division | Yes | N | Lozano, Edgar
S00915 | University Ave Mobility Plan | Transportation and Storm Water Department - Street Division | Design Bid Build | 5751376 | 9533349 | 2020-05-30 | FY20 | Q4 | 2020-11-15 | FY21 | Q2 | Right-of-Way Division | Yes | N | Ashrafzadeh, Mastaneh
S00951 | Coastal Rail Trail | TSW | Design Bid Build | 15284458.253 | 24467997.7001 | 2020-07-01 | FY21 | Q1 | 2021-01-04 | FY21 | Q3 | Right-of-Way Division | Yes | N | Nutter, Daniel
S01083 | FAIRBROO K NEIGHBORHOOD PARK - DEVELOPMEN | Parks & Recreation Department | Design Bid Build | 4366673 | 6045539 | 2020-04-13 | FY20 | Q4 | 2020-07-30 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
S01090 | MBGC Clubhouse Demo/Prtbl Building Instl | Parks & Recreation Department | Design Bid Build | 4770578 | 6463815.7999 | 2020-03-23 | FY20 | Q3 | 2020-07-23 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
S10008 | El Monte Pipeline No. 2 | PUD Water | Design Bid Build | 17900000 | 24499999.9871 | 2020-09-01 | FY21 | Q1 | 2021-03-01 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Ammerlahn, Parita
S10051 | Olive St Park Acquisition and Develpment | Parks & Recreation Department | Design Bid Build | 1659494 | 3271585 | 2021-04-16 | FY21 | Q4 | 2021-06-30 | FY21 | Q4 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
S11010 | MBGC Irrigation & Electrical Upgrades | Parks & Recreation Department | Design Bid Build | 2807051 | 4459999.7998 | 2020-03-05 | FY20 | Q3 | 2020-07-31 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
S11103 | La Paz Mini Park | Parks & Recreation Department | Design Bid Build | 1502338 | 2603753.9997 | 2020-03-16 | FY20 | Q3 | 2020-09-10 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Mahmalji, Samir
S12012 | Cielo & Woodman Pump Station | PUD Water | Design Bid Build | 4678000 | 6677999.9978 | 2020-02-11 | FY20 | Q3 | 2020-08-13 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Ammerlahn, Parita
S12013 | Alvarado 2nd Extension Pipeline | PUD Water | Design Bid Build | 65209999.9674 | 80498530.9061 | 2020-10-09 | FY21 | Q2 | 2021-04-22 | FY21 | Q4 | Right-of-Way Division | Yes | N | Bose, Sheila
S14006 | El Cuervo Adobe Improvements | Parks & Recreation Department | Job Order Contract | 273480 | 606000 | 2020-11-02 | FY21 | Q2 | 2021-05-11 | FY21 | Q4 | Architectural Engineering & Parks Division | Yes | N | Lewis, Nikki
S14007 | Salk Neighborhood Park & Joint Use Devel | Parks & Recreation Department | Design Bid Build | 4376685.8246 | 6036685.8245 | 2020-06-02 | FY20 | Q4 | 2020-11-27 | FY21 | Q2 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
S14023 | Pacific Highlands Ranch Branch Library | Library Department | Design Bid Build | 17443915 | 26164178 | 2020-06-08 | FY20 | Q4 | 2020-12-08 | FY21 | Q2 | Architectural Engineering & Parks Division | Yes | N | Lozano, Edgar
S15007 | Wangenheim Joint Use Facility | Parks & Recreation Department | Design Bid Build | 6386395.9986 | 9190352.9986 | 2020-04-24 | FY20 | Q4 | 2020-10-16 | FY21 | Q2 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
S15020 | Tecolote Canyon Trunk Sewer Improvement | PUD Sewer | Design Bid Build | 32826000 | 35555000 | 2020-08-04 | FY21 | Q1 | 2021-02-10 | FY21 | Q3 | Right-of-Way Division | Yes | N | Salem, Nicole
S15028 | Olive Grove Community Park ADA Improveme | Parks & Recreation Department | Design Bid Build | 1049999.9996 | 1617848.9996 | 2020-04-10 | FY20 | Q4 | 2020-08-28 | FY21 | Q1 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
S15031 | Egger/South Bay Comm Pk ADA Improvements | Parks & Recreation Department | Design Bid Build | 1969144.998 | 2730144.9976 | 2020-11-18 | FY21 | Q2 | 2021-05-25 | FY21 | Q4 | Architectural Engineering & Parks Division | Yes | N | Mahmalji, Samir
S16029 | Carmel Valley CP - Turf Upgrades | Parks & Recreation Department | Design Bid Build | 2504999.9969 | 4274120.994 | 2020-08-28 | FY21 | Q1 | 2021-03-08 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Lozano, Edgar
S16031 | Ocean Air CP Comfort Station & Park Impr | Parks & Recreation Department | Design Bid Build | 1066999.9987 | 1881792.9972 | 2020-08-28 | FY21 | Q1 | 2021-03-08 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Lozano, Edgar
S16034 | Carmel Del Mar NP Comfort Station - Dev | Parks & Recreation Department | Design Bid Build | 1519563.9997 | 2330563.9995 | 2020-05-21 | FY19 | Q4 | 2020-11-19 | FY20 | Q2 | Architectural Engineering & Parks Division | Yes | N | Lewis, Nikki
S16035 | Sage Canyon NP Concession Bldg-Develop | Parks & Recreation Department | Job Order Contract | 767499.9995 | 1310499.9989 | 2020-08-26 | FY21 | Q1 | 2021-03-09 | FY21 | Q3 | Architectural Engineering & Parks Division | Yes | N | Lewis, Nikki
S16047 | Cañon Street Pocket Park | Parks & Recreation Department | Design Bid Build | 1224349.9996 | 2567314.8994 | 2020-04-24 | FY19 | Q4 | 2020-08-25 | FY20 | Q2 | Architectural Engineering & Parks Division | Yes | N | Oliver, Kevin
S17001 | Talmadge Traffic Calming Infrastructure | Parks & Recreation Department | Design Bid Build | 173937.9998 | 309956.9997 | 2020-11-30 | FY21 | Q2 | 2021-04-30 | FY21 | Q4 | Right-of-Way Division | Yes | N | Ashrafzadeh, Mastaneh
S17012 | North City Water Reclamation Plant Electrical Upgrades | Public Utilities | Design Bid Build | 26500000 | 34450000 | 2020-12-29 | FY21 | Q2 | 2021-06-07 | FY21 | Q4 | #N/A | Yes | N | Barhoumi, Amer
S17013 | MBC Equipment Upgrades | Public Utilities | Design Bid Build | 30109800 | 39956000 | 2020-12-11 | FY21 | Q2 | 2021-06-07 | FY21 | Q4 | #N/A | Yes | N | Barhoumi, Amer
S18001 | University Ave Complete Street | Transportation and Storm Water Department - Street Division | Design Bid Build | 4330300 | 6718400 | 2021-01-30 | FY21 | Q3 | 2021-06-01 | FY21 | Q4 | Right-of-Way Division | Yes | N | Ashrafzadeh, Mastaneh
S18006 | Harbor Drive Trunk Sewer Replacement | PUD Sewer | Design Bid Build | 14699999.945 | 21044999.938 | 2020-07-31 | FY21 | Q1 | 2020-12-31 | FY21 | Q2 | Architectural Engineering & Parks Division | Yes | N | Vitelle, Brian
S18007 | Fire-Rescue Air Ops Facility - PH II | Fire-Rescue Department (FS) | Design Bid Build | 13000000 | 15000000 | 2019-10-01 | FY20 | Q2 | 2020-10-13 | FY21 | Q2 | Architectural Engineering & Parks Division | Yes | N | Grani, Jason
L17000.6 | Miramar Landfill Trailer Replacements | Environmental Services | Sole Source | 1500000 | 2000000 | 2020-12-31 | FY21 | Q2 | 2020-12-31 | FY21 | Q2 | #N/A | Yes | N | Fergusson, Craig
L18002.3 | Miramar Landfill Storm Water Basin Improvements | Environmental Services | Design Bid Build | 6000000 | 8000000 | 2021-09-30 | FY22 | Q1 | 2021-03-31 | FY21 | Q3 | #N/A | Yes | N | Fergusson, Craig
|  |  |  | #N/A | #N/A

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only