## Forecast of Projects
Line Number | Project Name | Project Name (Text) | Project Number | Asset Managing Department | Contract Type | Estimated Total Contract Cost ($) | Estimated Total Project Cost ($) | Fiscal Year Advertising | Quarter Advertising | Fiscal Year Awarding | Quarter Awarding
1 | Signal Mods in Barrio Logan | Signal Mods in Barrio Logan | B13010 | Transportation | Job Order Contract | 1287091.83 | 2151900.63 | FY25 | Q2 | FY26 | Q2
2 | Beyer Bl @ Smythe Ave Traffic Signal | Beyer Bl @ Smythe Ave Traffic Signal | B14015 | Transportation | Job Order Contract | 1814900 | 2498377 | FY26 | Q3 | FY26 | Q4
3 | Pacific Beach TS Interconnect Upgrade | Pacific Beach TS Interconnect Upgrade | B15065 | Transportation | Job Order Contract | 1907076 | 3721865 | FY26 | Q2 | FY26 | Q4
4 | Pressure Reducing Stations Upgrades Phs1 | Pressure Reducing Stations Upgrades Phs1 | B16017 | Public Utilities | Design Bid Build | 8600000 | 12305000 | FY26 | Q2 | FY26 | Q4
5 | Jamacha Lomita Storm Drain | Jamacha Lomita Storm Drain | B16094 | Stormwater | Design Bid Build | 4227242.25 | 6839000 | FY25 | Q3 | FY26 | Q1
6 | Green Infrastructure Group 1012 | Green Infrastructure Group 1012 | B16111 | Stormwater | Design Bid Build | 1958595.56 | 4768034.6 | FY26 | Q2 | FY26 | Q4
7 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | B17071 | Transportation | Design Bid Build | 650000 | 1150134.29 | FY26 | Q2 | FY26 | Q4
8 | Storm Drain Group 763 | Storm Drain Group 763 | B17143 | Stormwater | Design Bid Build | 817305.25 | 2679869 | FY25 | Q3 | FY26 | Q1
9 | University Avenue Culvert Reconstruction | University Avenue Culvert Reconstruction | B18015 | Stormwater | Design Bid Build | 871516.25 | 2408660.57 | FY26 | Q2 | FY26 | Q3
10 | Narragansett Avenue Access | Narragansett Avenue Access | B18026 | Parks & Recreation | Job Order Contract | 598314 | 2205771.98 | FY25 | Q4 | FY26 | Q3
11 | Sewer & AC Water Group 1055 (S) | Sewer & AC Water Group 1055 (S) | B18112 | Public Utilities | Design Bid Build | 4475700 | 7357093.04 | FY26 | Q2 | FY26 | Q4
12 | Sewer & AC Water Group 1055 (W) | Sewer & AC Water Group 1055 (W) | B18115 | Public Utilities | Design Bid Build | 2509000 | 4953046.26 | FY26 | Q2 | FY26 | Q4
13 | Block 7T - Allied Gardens SL UU65 | Block 7T - Allied Gardens SL UU65 | B18129 | Transportation | Job Order Contract | 1235700 | 1759000 | FY26 | Q2 | FY26 | Q3
14 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | B18136 | Transportation | Design Bid Build | 1321000 | 1896500.66 | FY26 | Q2 | FY26 | Q4
15 | Coronado SB (27th SB-Madden)Rd Imp UU193 | Coronado SB (27th SB-Madden)Rd Imp UU193 | B18137 | Transportation | Design Bid Build | 1245000 | 1672754.07 | FY26 | Q2 | FY26 | Q4
16 | Wightman (Chamoune -Euclid) Rd Imp UU388 | Wightman (Chamoune -Euclid) Rd Imp UU388 | B18138 | Transportation | Design Bid Build | 1720000 | 2240000 | FY26 | Q2 | FY26 | Q4
17 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | B18140 | Transportation | Design Bid Build | 980000 | 1669552 | FY26 | Q1 | FY26 | Q3
18 | Block 6DD1 (Clairemont Mesa)Rd Imp UU410 | Block 6DD1 (Clairemont Mesa)Rd Imp UU410 | B18142 | Transportation | Design Bid Build | 2032250 | 2896061 | FY26 | Q2 | FY26 | Q4
19 | 32nd St PH I (Market-F St) Rd Imp UU386 | 32nd St PH I (Market-F St) Rd Imp UU386 | B18144 | Transportation | Design Bid Build | 476500 | 1031096 | FY26 | Q2 | FY26 | Q4
20 | 31st Street (Market-L St) Rd Imp UU11 | 31st Street (Market-L St) Rd Imp UU11 | B18147 | Transportation | Design Bid Build | 1090000 | 1597595.78 | FY26 | Q2 | FY26 | Q4
21 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 | B18148 | Transportation | Design Bid Build | 762066.57 | 1278990.67 | FY26 | Q1 | FY26 | Q3
22 | 25th (SB) (Coronado-Grove) Rd Imp UU995 | 25th (SB) (Coronado-Grove) Rd Imp UU995 | B18150 | Transportation | Design Bid Build | 368000 | 850213 | FY26 | Q2 | FY26 | Q4
23 | Downtown Audibles 04th & E S29 | Downtown Audibles 04th & E S29 | B18162 | Transportation | Design Bid Build | 485000 | 888500 | FY25 | Q3 | FY26 | Q1
24 | Accelerated Sewer Referral Group 847 | Accelerated Sewer Referral Group 847 | B18183 | Public Utilities | Design Bid Build | 3687264 | 6855331.32 | FY25 | Q3 | FY26 | Q1
25 | Camino Del Rio West & Moore St Median | Camino Del Rio West & Moore St Median | B19049 | Transportation | Design Bid Build | 1872242 | 2615627 | FY26 | Q2 | FY26 | Q4
26 | Torrey Pines Rd, Prospect-Coast Walk GR | Torrey Pines Rd, Prospect-Coast Walk GR | B19056 | Transportation | Design Bid Build | 1288535 | 2729982.9 | FY26 | Q2 | FY26 | Q4
27 | Traffic Signal Mods Grp 19-01 | Traffic Signal Mods Grp 19-01 | B19069 | Transportation | Design Bid Build | 2438000 | 3637100 | FY26 | Q2 | FY26 | Q4
28 | Pacific Beach Improv 1 (W) | Pacific Beach Improv 1 (W) | B19142 | Public Utilities | Design Bid Build | 6060100 | 8710558 | FY26 | Q2 | FY26 | Q4
29 | Rose Marie Starns Parking Lot Imprvemts | Rose Marie Starns Parking Lot Imprvemts | B19163 | Parks & Recreation | Job Order Contract | 2000473.9 | 4044832 | FY26 | Q1 | FY26 | Q1
30 | Mission Valley West Improv 1 (W) | Mission Valley West Improv 1 (W) | B19196 | Public Utilities | Design Bid Build | 4730087.8 | 7853875.98 | FY26 | Q2 | FY26 | Q4
31 | Mission Valley West Improv 1 (S) | Mission Valley West Improv 1 (S) | B19206 | Public Utilities | Design Bid Build | 1463637.39 | 1814057.21 | FY26 | Q2 | FY26 | Q4
32 | Colina Del Sol Improv 1 (S) | Colina Del Sol Improv 1 (S) | B20008 | Public Utilities | Design Bid Build | 10144735 | 15471795 | FY26 | Q2 | FY26 | Q4
33 | Colina Del Sol Improv 1 (W) | Colina Del Sol Improv 1 (W) | B20010 | Public Utilities | Design Bid Build | 7444700 | 11538138 | FY26 | Q2 | FY26 | Q4
34 | La Jolla Improv 3 (W) | La Jolla Improv 3 (W) | B20023 | Public Utilities | Design Bid Build | 5000000 | 7210067 | FY26 | Q2 | FY26 | Q4
35 | Chollas Creek Improv 1 (S) | Chollas Creek Improv 1 (S) | B20038 | Public Utilities | Job Order Contract | 3478000 | 5108359.72 | FY26 | Q1 | FY26 | Q2
36 | Chollas Creek Improv 1 (W) | Chollas Creek Improv 1 (W) | B20039 | Public Utilities | Job Order Contract | 7297091 | 9818519 | FY26 | Q1 | FY26 | Q2
37 | Chicano Park Improvements Phase III | Chicano Park Improvements Phase III | B20060 | Parks & Recreation | Job Order Contract | 1202064.94 | 2024320.94 | FY26 | Q3 | FY26 | Q4
38 | Willie Henderson Sports Complex Imp | Willie Henderson Sports Complex Imp | B20096 | Parks & Recreation | Design Bid Build | 13393226 | 18775465 | FY26 | Q2 | FY26 | Q4
39 | Ruffin Canyon Trail | Ruffin Canyon Trail | B20104 | Parks & Recreation | Minor Contract | 90000 | 311981 | FY25 | Q4 | FY26 | Q1
40 | SBWRP Reverse Osmosis System | SBWRP Reverse Osmosis System | B20122 | Public Utilities | Design Bid Build | 19000000 | 28238384 | FY26 | Q2 | FY26 | Q3
41 | Mississippi St @ El Cajon Blvd T/Signal | Mississippi St @ El Cajon Blvd T/Signal | B20140 | Transportation | Design Bid Build | 1250000 | 2300000 | FY26 | Q2 | FY26 | Q4
42 | NCWRP - Chiller Replacement | NCWRP - Chiller Replacement | B20148 | Public Utilities | Design Bid Build | 1600000 | 3300000 | FY26 | Q1 | FY26 | Q2
43 | Mt View Sports Courts ADA Improvements | Mt View Sports Courts ADA Improvements | B21114 | Parks & Recreation | Design Bid Build | 458026 | 1233329 | FY26 | Q2 | FY26 | Q4
44 | SV Dam Low Level Outlet Improvements | SV Dam Low Level Outlet Improvements | B22002 | Public Utilities | Design Bid Build | 2500000 | 5366554.94 | FY26 | Q2 | FY26 | Q3
45 | Chollas View Improv 1 (S) | Chollas View Improv 1 (S) | B22008 | Public Utilities | Design Bid Build | 5501610 | 8724500 | FY26 | Q2 | FY26 | Q4
46 | Old Salt Pool Access Stairs | Old Salt Pool Access Stairs | B22012 | Parks & Recreation | Job Order Contract | 853807.73 | 1707193.77 | FY25 | Q4 | FY26 | Q3
47 | Via De La Valle Pipeline | Via De La Valle Pipeline | B22015 | Public Utilities | Design Build | 6788293 | 10023393 | FY26 | Q2 | FY26 | Q3
48 | South Chollas Landfill Gas Collection System Improvements | South Chollas Landfill Gas Collection System Improvements | B22031 | Environmental Services | Design Bid Build | 2000000 | 3000000 | FY26 | Q3 | FY26 | Q3
49 | Otay WTP Raw Water PS Switchboard Replac | Otay WTP Raw Water PS Switchboard Replac | B22037 | Public Utilities | Design Bid Build | 1100000 | 2500000 | FY25 | Q4 | FY26 | Q2
50 | Hard Court Improvements | Hard Court Improvements | B22045 | Parks & Recreation | Job Order Contract | 810000 | 1200000 | FY25 | Q4 | FY26 | Q2
51 | Dr. Bertha O. Pendleton Park Improvement | Dr. Bertha O. Pendleton Park Improvement | B22047 | Parks & Recreation | Design Bid Build | 5451882 | 7852573 | FY25 | Q3 | FY26 | Q1
52 | AC Water & Sewer Group 1029 (P) | AC Water & Sewer Group 1029 (P) | B22062 | Transportation | Job Order Contract | 540360 | 900600 | FY23 | Q2 | FY26 | Q3
53 | Police HQ Security Fencing | Police HQ Security Fencing | B22080 | General Services | Design Bid Build | 1793081.75 | 3014350 | FY25 | Q4 | FY26 | Q1
54 | PW Genesee Avenue Median Improv | PW Genesee Avenue Median Improv | B22085 | Public Utilities | Design Bid Build | 3604165.04 | 4425849.49 | FY25 | Q3 | FY26 | Q2
55 | Golden Hill Improv 2 (S) | Golden Hill Improv 2 (S) | B22091 | Public Utilities | Design Bid Build | 2820220 | 4520020 | FY26 | Q3 | FY26 | Q4
56 | Golden Hill Improv 2 (W) | Golden Hill Improv 2 (W) | B22093 | Public Utilities | Design Bid Build | 16842000 | 21332400 | FY26 | Q3 | FY26 | Q4
57 | Center City Traffic Signals-15th Street | Center City Traffic Signals-15th Street | B22111 | Transportation | Design Bid Build | 1700000 | 2534981.36 | FY25 | Q3 | FY26 | Q1
58 | Crespo Dr (Mecca-Soledad) Improv (P) | Crespo Dr (Mecca-Soledad) Improv (P) | B22138 | Transportation | Design Bid Build | 458800 | 688400 | FY26 | Q2 | FY26 | Q4
59 | Scripps Miramar Ranch Library Roof Repl | Scripps Miramar Ranch Library Roof Repl | B22139 | General Services | Job Order Contract | 2292271 | 3267971 | FY25 | Q2 | FY26 | Q2
60 | Installation of City Owned SL 2201 (NSG) | Installation of City Owned SL 2201 (NSG) | B22149 | Transportation | Job Order Contract | 800000 | 1157000 | FY25 | Q3 | FY26 | Q1
61 | Terminal Parking Lot East Rehabilitation | Terminal Parking Lot East Rehabilitation | B22157 | Economic Development | Job Order Contract | 885967 | 1558347 | FY25 | Q3 | FY26 | Q2
62 | West Miramar Central Basin Expansion | West Miramar Central Basin Expansion | B23000 | Environmental Services | Design Bid Build | 2900000 | 3750000 | FY26 | Q2 | FY26 | Q3
63 | Willie Henderson Lighting Upgrades | Willie Henderson Lighting Upgrades | B23011 | Parks & Recreation | Design Bid Build | 1300000 | 2132550 | FY25 | Q3 | FY26 | Q1
64 | Miramar WTP Caustic Pumping System | Miramar WTP Caustic Pumping System | B23014 | Public Utilities | Design Bid Build | 1317300 | 2853250.41 | FY25 | Q4 | FY26 | Q2
65 | Miramar WTP Interim Solids Management | Miramar WTP Interim Solids Management | B23049 | Public Utilities | Design Bid Build | 4409785 | 5612453 | FY26 | Q1 | FY26 | Q3
66 | Balboa Park Golf Course Improvements | Balboa Park Golf Course Improvements | B23071 | Parks & Recreation | Design Build | 3300000 | 6400000 | FY25 | Q4 | FY26 | Q3
67 | Miramar Valve No2 Replacement | Miramar Valve No2 Replacement | B23075 | Public Utilities | Job Order Contract | 1200000 | 2067521 | FY26 | Q2 | FY26 | Q4
68 | Black Mountain Reservoir Spillway Stairs | Black Mountain Reservoir Spillway Stairs | B23110 | Public Utilities | Design Bid Build | 639666.02 | 1200000 | FY25 | Q4 | FY26 | Q2
69 | CMP SD Lining IV | CMP SD Lining IV | B23117 | Stormwater | Job Order Contract | 1453177 | 3190409 | FY26 | Q2 | FY26 | Q4
70 | 47th St & Hartley St HAWK | 47th St & Hartley St HAWK | B23145 | Transportation | Design Bid Build | 528480 | 992500 | FY26 | Q2 | FY26 | Q4
71 | Northern Garage Dorm Repl | Northern Garage Dorm Repl | B24015 | General Services | Minor Contract | 50000 | 362000 | FY25 | Q4 | FY26 | Q1
72 | Mission Blvd South Loring Overlay | Mission Blvd South Loring Overlay | B24135 | Transportation | Design Bid Build | 902293 | 1393000 | FY26 | Q1 | FY26 | Q3
73 | Roswell Street Overlay | Roswell Street Overlay | B24137 | Transportation | Job Order Contract | 400000 | 710000 | FY26 | Q1 | FY26 | Q3
74 | AC Overlay Group 2507 | AC Overlay Group 2507 | B25007 | Transportation | Design Bid Build | 6700000 | 8295000 | FY26 | Q1 | FY26 | Q3
75 | AC Water & Sewer Group 1033 North (W) | AC Water & Sewer Group 1033 North (W) | B25014 | Public Utilities | Design Bid Build | 15202839 | 18302568.3 | FY26 | Q2 | FY26 | Q4
76 | Pump Station H ATS Emergency | Pump Station H ATS Emergency | B25036 | Stormwater | Emergency (City Forces) | 228187 | 300000 | FY00 | Q3 | FY26 | Q2
77 | AC Overlay Group 2511 | AC Overlay Group 2511 | B25049 | Transportation | Job Order Contract | 3344019.56 | 4070169.56 | FY25 | Q4 | FY26 | Q1
78 | Brown Field Terminal Roof Replacement | Brown Field Terminal Roof Replacement | B25063 | Economic Development | Design Bid Build | 700000 | 1000000 | FY26 | Q2 | FY26 | Q4
79 | AC Overlay Group 2511A | AC Overlay Group 2511A | B25067 | Transportation | Design Bid Build | 632643 | 1000000 | FY25 | Q4 | FY26 | Q1
80 | AC Overlay Group 2511B | AC Overlay Group 2511B | B25068 | Transportation | Design Bid Build | 623000 | 920000 | FY25 | Q4 | FY26 | Q2
81 | AC Overlay Group 2511C | AC Overlay Group 2511C | B25069 | Transportation | Design Bid Build | 608000 | 910000 | FY25 | Q4 | FY26 | Q2
82 | AC Overlay Group 2520 UUP | AC Overlay Group 2520 UUP | B25083 | Transportation | Design Bid Build | 523329 | 523329 | FY26 | Q1 | FY26 | Q3
83 | 4918/4980 Canterbury Dr SD Emergency | 4918/4980 Canterbury Dr SD Emergency | B25096 | Stormwater | Emergency (As-needed) | 4750000 | 6000000 | FY26 | Q1 | FY26 | Q1
84 | Pump Station 64 Valve Replacement | Pump Station 64 Valve Replacement | B26000 | Public Utilities | Design Bid Build | 1400000 | 2500000 | FY26 | Q2 | FY26 | Q3
85 | Sidewalk Replacement Group 2530 - U & MM | Sidewalk Replacement Group 2530 - U & MM | B26003 | Transportation | Design Bid Build | 1700000 | 3100000 | FY25 | Q3 | FY26 | Q4
86 | Jamacha Lomita Storm Drain (P) | Jamacha Lomita Storm Drain (P) | B26015 | Transportation | Design Bid Build | 197881.1 | 197881.1 | FY25 | Q3 | FY26 | Q1
87 | Carmel Mountain TS Emergency | Carmel Mountain TS Emergency | B26039 | Transportation | Sole Source Emergency | 2200000 | 2500000 | FY26 | Q1 | FY26 | Q1
88 | Office Trailers Replacement | Office Trailers Replacement | L17000.7 | Environmental Services | Design Build | 4500000 | 5000000 | FY25 | Q3 | FY26 | Q1
89 | Rancho Bernardo CP Dog Park | Rancho Bernardo CP Dog Park | L20000.2 | Parks & Recreation | Design Bid Build | 3428000 | 5700000 | FY25 | Q4 | FY26 | Q2
90 | Palm Avenue Interstate 805 Interchange | Palm Avenue Interstate 805 Interchange | S00869 | Transportation | Agency/ Developer Managed Built - City Paid | 31500000 | 51730633.53 | FY25 | Q4 | FY26 | Q3
91 | HIDDEN TRAILS NEIGHBORHOOD PARK | HIDDEN TRAILS NEIGHBORHOOD PARK | S00995 | Parks & Recreation | Design Bid Build | 8685000 | 12577229.6 | FY25 | Q4 | FY26 | Q1
92 | El Cuervo Adobe Improvements | El Cuervo Adobe Improvements | S14006 | Parks & Recreation | Design Bid Build | 292315 | 956000.4 | FY26 | Q3 | FY26 | Q4
93 | Solana Highlands NP-Comfort Station | Solana Highlands NP-Comfort Station | S16032 | Parks & Recreation | Design Bid Build | 4461200 | 6133600 | FY26 | Q2 | FY26 | Q2
94 | Chollas Creek Oak Park Trail | Chollas Creek Oak Park Trail | S20012 | Parks & Recreation | Design Build | 2380000 | 4111500 | FY00 | Q3 | FY26 | Q4
95 | Ocean Beach Branch Library | Ocean Beach Branch Library | S20015 | Library | Design Build | 8195649 | 12751489 | FY26 | Q2 | FY26 | Q3
96 | Rancho Bernardo Industrial Pump Stn Repl | Rancho Bernardo Industrial Pump Stn Repl | S21004 | Public Utilities | Design Bid Build | 9308762 | 15511809 | FY26 | Q2 | FY26 | Q4
97 | MTRP Trail System Management | MTRP Trail System Management | S23010 | Parks & Recreation | Minor Contract | 90000 | 200000 | FY25 | Q4 | FY26 | Q1
98 | City Hts Library Performance Annex Imp | City Hts Library Performance Annex Imp | S23013 | Library | Design Build | 5417724 | 6532680 | FY25 | Q3 | FY26 | Q1
99 | Paradise Hills Community Park Trail | Paradise Hills Community Park Trail | S24013 | Parks & Recreation | Minor Contract | 700000 | 750000 | FY26 | Q2 | FY26 | Q3
|  |  | 99 CIP Projects |  |  | 328242147.94 | 500422445.08

## Summary Table
Summary by Asset - Managing Departments
Asset - Managing Department | Estimated Construction Contract Award | Estimated Total Project Cost
Library | 13613373 | 19284169
Parks & Recreation | 49494309.57 | 78316346.69
Public Utilities | 158124955.25 | 235474543.67
Environmental Services | 9400000 | 11750000
Stormwater | 14306023.31 | 26185973.17
Transportation | 77582167.06 | 120208744.55
General Services | 4135352.75 | 6644321
Economic Development | 1585967 | 2558347
FY 2025 Total | 328242147.94 | 500422445.08

## CIPASF - Oct p6 Master (hidden)
| SAP | Oct | Oct | SAP | SAP | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct | Oct |  | Oct |  | Aug | [8 empty] | FY26 | Oct | Oct | [8 empty] | FY26 | Oct | Oct |  | FY26 | Oct | Oct |  |  |  |  | Oct |  | Oct | [12 empty] | Oct
Entered | SAP BO | P6 | P6 | SAP BO | SAP BO | P6 | P6 | P6 | P6 | P6 | P6 | P6 | P6 | P6 | Entered | Entered | Entered | Entered | Entered | Entered | Entered | Entered | Entered | Entered | Entered | Entered | P6 | Override | Dashboard | P6 | Published | Published | P6 | P6 | Override | Override | Dashboard | Dashboard | Entered | P6 | Override | Dashboard | Published | Published | P6 | P6 | Override | Override | Dashboard | Dashboard | Published List | P6 | Override | Dashboard | Published List | P6 | Override | Dashboard | Aug Goal | Aug Goal | Published List - Aug Goal | P6 | Published List - Aug Goal | P6 |  | Published List | Published List | Published List | Published List | Published List | Published List | Published List | Published List | Published List | Published List |  | Entered
|  |  | 2025-10-01 | [15 empty] | Year Moved To | Reason for Removal |  |  | Year Moved to | Reason for Removal | [28 empty] | Entered |  | Entered
WBS | Parent | Project Name | Data Date | Annual Allocation Project | Annual Allocation Subproject | Council Districts | Asset Type Group (PC) | Construction Contract Type | Asset Managing Department | Responsible Division | Responsible Manager | Design Section Head | Project Manager | Charter and/or Charter Amendment | Status of Award | Status of Advertise | Advertising/Awarding | Added to Current FY Award List | Removed from Current FY Award List | Reason for Removal (Award) | Month Removed (Award) | Added to Current FY Advertise List | Removed from Current FY Advertise List | Reason for Removal (Advertise) | Month Removed (Advertise) | ECP LNTP (Published) | LNTP (6010) | ECP LNTP (Override) | LNTP | LNTP BL (BL 6010) | Fiscal Year Awarding (Published) | Quarter Awarding (Published) | Fiscal Year Awarding (Actual/ Projection) P6 | Quarter Awarding (Actual/ Projection) P6 | Fiscal Year Awarding (Actual/ Projection) Override | Quarter Awarding (Actual/ Projection) Override | Fiscal Year Awarding (Actual/ Projection) | Quarter Awarding (Actual/ Projection) | ECP Contract Bid (Published) | Contract Bid - Start (5010) | Contract Bid - Start (Override) | Contract Bid - Start | Fiscal Year Advertising (Published) | Quarter Advertising (Published) | Fiscal Year Advertising (Actual/Projection) P6 | Quarter Advertising (Actual/Projection) P6 | Fiscal Year Advertising (Actual/Projection) Override | Quarter Advertising (Actual/Projection) Override | Fiscal Year Advertising (Actual/Projection) | Quarter Advertising (Actual/Projection) | Total Construction Cost (Published) | Est Construction Cost (730) | Total Construction Cost (Override) | Total Construction Cost | Total Project Cost (Published) | Planned Total Cost | Total Project Cost (Override) | Total Project Cost | Est Construction Cost (730) (Goal) | Planned Total Cost (Goal) | Total Water Mileage (Published) | Total Water Mileage | Total Sewer Mileage (Published) | Total Sewer Mileage | Current FY Published List | FY25 Published List | FY24 Published List | FY23 Published List | FY22 Published List | FY21 Published List | FY20 Published List | FY19 Published List | FY18 Published List | FY17 Published List | FY16 Published List | P6 Exists | Comments
B13010 | AIL00005 | Signal Mods in Barrio Logan | 2025-10-01 | Traffic Signals - Modify & Modernize / AIL00005 | Signal Mods in Barrio Logan / B13010 | 8 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter & Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-07-31 | 2025-10-30 |  | 2025-10-30 | 2021-01-15 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 2024-10-04 | 2024-10-04 |  | 2024-10-04 | FY25 | Q2 | FY25 | Q2 |  |  | FY25 | Q2 | 1287092 | 1287091.83 |  | 1287091.83 | 2151901 | 2151900.63 |  | 2151900.63 | 282800 | 1775300.63 | 0 | 0 | 0 | 0 |  | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | Yes
B14015 | AIL00004 | Beyer Bl @ Smythe Ave Traffic Signal | 2025-10-01 | Traffic Signals - Citywide / AIL00004 | Beyer Bl @ Smythe Ave Traffic Signal / B14015 | 8 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-06-12 |  | 2026-06-12 | 2019-05-30 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2026-01-07 |  | 2026-01-07 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 1814900 |  | 1814900 |  | 2498377 |  | 2498377 | 235300 | 2176477 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | Yes | Yes | Yes | Yes | No | Yes
B15065 | AIL00002 | Pacific Beach TS Interconnect Upgrade | 2025-10-01 | Install T/S Interconnect Systems / AIL00002 | Pacific Beach TS Interconnect Upgrade / B15065 | 1, 7, 2 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-05 | 2026-04-08 |  | 2026-04-08 | 2020-06-02 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-08-28 | 2025-12-01 |  | 2025-12-01 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 1907076 | 1907076 |  | 1907076 | 3721865 | 3721865 |  | 3721865 | 933030 | 1880246 | 0 | 0 | 0 | 0 |  | No | No | Yes | Yes | Yes | No | No | No | No | No | Yes
B16017 | AKA00002 | Pressure Reducing Stations Upgrades Phs1 | 2025-10-01 | Pressure Reduction Upgrade / AKA00002 | Pressure Reducing Stations Upgrades Phs1 / B16017 | 1, 3, 6, 7, 9 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Torres, Gabriel | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-12-01 | 2026-04-15 |  | 2026-04-15 | 2022-05-02 | FY26 | Q2 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-02 | 2025-10-02 |  | 2025-10-02 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 8600000 | 8600000 |  | 8600000 | 12305000 | 12305000 |  | 12305000 | 3740000 | 6015000 | 0 | 0 | 0 | 0 |  | Yes | No | No | Yes | Yes | Yes | No | No | No | No | Yes
B16094 | ACA00001 | Jamacha Lomita Storm Drain | 2025-10-01 | Flood Resilience Infrastructure / ACA00001 | Jamacha Lomita Storm Drain / B16094 | 4 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Shamoun, Ikhlass | Charter Only | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-08-29 | 2025-08-13 | 2025-08-05 | 2025-08-05 | 2019-07-01 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-01-21 | 2025-01-21 |  | 2025-01-21 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 4150242 | 4020140.65 | 4227242.25 | 4227242.25 | 6839000 | 6839000 |  | 6839000 | 0 | 5653898.3 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B16111 | ACC00001 | Green Infrastructure Group 1012 | 2025-10-01 | Stormwater Green Infrastructure / ACC00001 | Green Infrastructure Group 1012 / B16111 | 4 | Storm Water Drainage | Design Bid Build | Stormwater | Storm Water | SWD | Dastgheibi, Sara | Hosseini Shakib, Iman | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-06-24 |  | 2026-06-24 | 2025-12-24 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-12-11 |  | 2025-12-11 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 1958595.56 |  | 1958595.56 |  | 4768034.6 |  | 4768034.6 | 1958596 | 290818.6 | 0 | 0 | 0 | 0 |  | No | Yes | No | No | No | No | No | No | No | No | Yes
B17071 | AID00001 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 / B17071 | 1 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-29 | 2026-05-15 |  | 2026-05-15 | 2020-06-01 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-21 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 400000 | 650000 |  | 650000 | 900134 | 1150134.29 |  | 1150134.29 | 106912 | 755805.29 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | Yes | Yes | Yes | No | No | No | No | Yes
B17143 | ACA00001 | Storm Drain Group 763 | 2025-10-01 | Flood Resilience Infrastructure / ACA00001 | Storm Drain Group 763 / B17143 | 7 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Bourojerdi, Neda | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-04 | 2025-09-25 | 2025-09-24 | 2025-09-24 | 2020-12-01 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-01-17 | 2025-01-17 |  | 2025-01-17 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 832305 | 832305.25 | 817305.25 | 817305.25 | 2679869 | 2679869 |  | 2679869 | 5000 | 2385569 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18015 | ACA00001 | University Avenue Culvert Reconstruction | 2025-10-01 | Flood Resilience Infrastructure / ACA00001 | University Avenue Culvert Reconstruction / B18015 | 9 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Bourojerdi, Neda | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-02-11 |  | 2026-02-11 | 2020-02-12 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-12-02 |  | 2025-12-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 871516.25 |  | 871516.25 |  | 2408660.57 |  | 2408660.57 | 0 | 1958661 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18026 | AGF00006 | Narragansett Avenue Access | 2025-10-01 | Coastal Erosion and Access / AGF00006 | Narragansett Avenue Access / B18026 | 2 | Parks | Job Order Contract | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | Afagh, Negin | Charter Only | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-03 | 2026-01-02 |  | 2026-01-02 | 2024-08-26 | FY26 | Q1 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-06-12 | 2025-06-16 |  | 2025-06-16 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 806135 | 598314 |  | 598314 | 2200772 | 2205771.98 |  | 2205771.98 | 134000 | 1407771.9953 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18112 | AJA00001 | Sewer & AC Water Group 1055 (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Sewer & AC Water Group 1055 (S) / B18112 | 3 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-04-23 | 2026-06-09 |  | 2026-06-09 | 2023-07-03 | FY26 | Q4 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-10-10 | 2025-11-26 |  | 2025-11-26 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 4475700 | 4475700 |  | 4475700 | 7357093 | 7357093.04 |  | 7357093.04 | 4475700 | 710593.04 | 0 | 0 | 1.98 | 1.98 |  | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B18115 | AKB00003 | Sewer & AC Water Group 1055 (W) | 2025-10-01 | Main Replacements / AKB00003 | Sewer & AC Water Group 1055 (W) / B18115 | 3 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-04-23 | 2026-06-09 |  | 2026-06-09 | 2023-07-03 | FY26 | Q4 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-10-10 | 2025-11-26 |  | 2025-11-26 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 2509000 | 2509000 |  | 2509000 | 4953046 | 4953046.26 |  | 4953046.26 | 2509000 | 1227146.26 | 1.19 | 1.19 | 0 | 0 |  | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B18129 | AID00001 | Block 7T - Allied Gardens SL UU65 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | Block 7T - Allied Gardens SL UU65 / B18129 | 7 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Xiao, Jie | Charter Only | On Schedule | On Schedule | [5 empty] | Added - Aug 1st |  |  |  |  | 2026-02-04 |  | 2026-02-04 | 2025-07-16 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-12-01 |  | 2025-12-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 1235700 |  | 1235700 |  | 1759000 |  | 1759000 | 1235700 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18136 | AID00001 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 / B18136 | 3 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-29 | 2026-05-15 |  | 2026-05-15 | 2019-12-02 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-21 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 921000 | 1321000 |  | 1321000 | 1496501 | 1896500.66 |  | 1896500.66 | 190910 | 1238771.62 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | Yes | Yes | Yes | No | No | No | No | Yes
B18137 | AID00001 | Coronado SB (27th SB-Madden)Rd Imp UU193 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | Coronado SB (27th SB-Madden)Rd Imp UU193 / B18137 | 8 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-29 | 2026-05-15 |  | 2026-05-15 | 2020-12-01 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-21 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 665000 | 1245000 |  | 1245000 | 1092754 | 1672754.07 |  | 1672754.07 | 268212.8 | 755551.07 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B18138 | AID00001 | Wightman (Chamoune -Euclid) Rd Imp UU388 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | Wightman (Chamoune -Euclid) Rd Imp UU388 / B18138 | 9 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-29 | 2026-05-15 |  | 2026-05-15 | 2020-06-01 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-21 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 920000 | 1720000 |  | 1720000 | 1440000 | 2240000 |  | 2240000 | 123367.07 | 1273454.46 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | Yes | Yes | Yes | No | No | No | No | Yes
B18140 | AID00001 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | Mission Bl(Loring-Turquoise) Rd Imp UU30 / B18140 | 1 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | Charter & Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2026-01-05 | 2026-01-15 |  | 2026-01-15 | 2020-06-01 | FY26 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-07-28 | 2025-08-07 | 2025-08-07 | 2025-08-07 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 980000 | 980000 |  | 980000 | 1419552 | 1669552 |  | 1669552 | 170777 | 1189003.05 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | Yes | Yes | Yes | No | No | No | No | Yes
B18142 | AID00001 | Block 6DD1 (Clairemont Mesa)Rd Imp UU410 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | Block 6DD1 (Clairemont Mesa)Rd Imp UU410 / B18142 | 2 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-29 | 2026-05-15 |  | 2026-05-15 | 2020-12-01 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-21 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 1032250 | 2032250 |  | 2032250 | 1896061 | 2896061 |  | 2896061 | 1473215 | 12045 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | Yes | Yes | No | No | No | No | No | Yes
B18144 | AID00001 | 32nd St PH I (Market-F St) Rd Imp UU386 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | 32nd St PH I (Market-F St) Rd Imp UU386 / B18144 | 9 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-29 | 2026-05-15 |  | 2026-05-15 | 2020-12-01 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-21 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 256500 | 476500 |  | 476500 | 811096 | 1031096 |  | 1031096 | 124122.35 | 656407 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B18147 | AID00001 | 31st Street (Market-L St) Rd Imp UU11 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | 31st Street (Market-L St) Rd Imp UU11 / B18147 | 9 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-29 | 2026-05-15 |  | 2026-05-15 | 2020-12-01 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-21 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 570000 | 1090000 |  | 1090000 | 1077596 | 1597595.78 |  | 1597595.78 | 286745 | 710893.78 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B18148 | AID00001 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 / B18148 | 1 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | Charter Only | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2026-01-05 | 2026-01-15 |  | 2026-01-15 | 2020-12-01 | FY26 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-07-28 | 2025-08-07 | 2025-08-07 | 2025-08-07 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 912067 | 762066.57 |  | 762066.57 | 1528991 | 1278990.67 |  | 1278990.67 | 109924 | 1388415.67 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B18150 | AID00001 | 25th (SB) (Coronado-Grove) Rd Imp UU995 | 2025-10-01 | Utilities Undergrounding Program / AID00001 | 25th (SB) (Coronado-Grove) Rd Imp UU995 / B18150 | 8 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-29 | 2026-05-15 |  | 2026-05-15 | 2020-12-01 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-21 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 168000 | 368000 |  | 368000 | 650213 | 850213 |  | 850213 | 88173 | 537452 | 0 | 0 | 0 | 0 |  | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B18162 | AIL00005 | Downtown Audibles 04th & E S29 | 2025-10-01 | Traffic Signals - Modify & Modernize / AIL00005 | Downtown Audibles 04th & E S29 / B18162 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Guillermo, Erick | Charter Only | Awarded | Removed |  | Added - Aug 1st |  |  |  |  | FY25 |  | Removed - Aug 1st |  | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2021-10-22 | FY00 | Q3 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 |  | 2025-03-13 | 2025-03-13 | 2025-03-13 | FY00 | Q3 | FY25 | Q3 | FY25 | Q3 | FY25 | Q3 |  | 485000 | 485000 | 485000 |  | 888500 |  | 888500 | 385100 | 783600 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18183 | AJA00001 | Accelerated Sewer Referral Group 847 | 2025-10-01 | Sewer Main Replacements / AJA00001 | Accelerated Sewer Referral Group 847 / B18183 | 1, 3, 7, 9, 2, 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-15 | 2025-08-28 | 2025-08-27 | 2025-08-27 | 2022-12-01 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-01-30 | 2025-01-30 |  | 2025-01-30 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 3687264 | 3687264 | 3687264 | 3687264 | 5855331 | 6855331.32 |  | 6855331.32 | 1242900 | 4827031.32 | 0 | 0 | 0.43 | 0.39 |  | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B19049 | AIG00001 | Camino Del Rio West & Moore St Median | 2025-10-01 | Median Installation / AIG00001 | Camino Del Rio West & Moore St Median / B19049 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Bourojerdi, Neda | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-02-11 | 2026-05-18 |  | 2026-05-18 | 2022-09-01 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-08-01 | 2025-11-04 |  | 2025-11-04 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 1872242 | 1872242 |  | 1872242 | 2615627 | 2615627 |  | 2615627 | 1189000 | 787427 | 0 | 0 | 0 | 0 |  | No | Yes | Yes | No | No | No | No | No | No | No | Yes
B19056 | AIE00002 | Torrey Pines Rd, Prospect-Coast Walk GR | 2025-10-01 | Guard Rails / AIE00002 | Torrey Pines Rd, Prospect-Coast Walk GR / B19056 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Mansury, Nazie | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-04-03 | 2026-05-15 |  | 2026-05-15 | 2025-11-03 | FY26 | Q4 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-09-26 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 1203535 | 1288535 |  | 1288535 | 2190189 | 2729982.9 |  | 2729982.9 | 692730 | 716089 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B19069 | AIL00005 | Traffic Signal Mods Grp 19-01 | 2025-10-01 | Traffic Signals - Modify & Modernize / AIL00005 | Traffic Signal Mods Grp 19-01 / B19069 | 7, 9, 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-06-24 |  | 2026-06-24 | 2022-08-04 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-12-11 |  | 2025-12-11 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2438000 |  | 2438000 |  | 3637100 |  | 3637100 | 320300 | 3081700 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B19142 | AKB00003 | Pacific Beach Improv 1 (W) | 2025-10-01 | Main Replacements / AKB00003 | Pacific Beach Improv 1 (W) / B19142 | 1 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-04-08 | 2026-06-08 |  | 2026-06-08 | 2024-12-02 | FY26 | Q4 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-10-02 | 2025-12-03 |  | 2025-12-03 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 6060100 | 6060100 |  | 6060100 | 8710558 | 8710558 |  | 8710558 | 5638300 | 529058 | 2.85 | 2.85 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B19163 | AGF00004 | Rose Marie Starns Parking Lot Imprvemts | 2025-10-01 | Mission Bay Improvements / AGF00004 | Rose Marie Starns Parking Lot Imprvemts / B19163 | 2 | Parks | Job Order Contract | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | Afagh, Negin | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | Added - Sept 1st |  |  |  | 2025-09-29 | 2025-09-30 |  | 2025-09-30 | 2024-01-02 | FY26 | Q1 | FY26 | Q1 |  |  | FY26 | Q1 | 2025-06-16 | 2025-07-07 |  | 2025-07-07 | FY25 | Q4 | FY26 | Q1 |  |  | FY26 | Q1 | 2981811 | 2000473.9 |  | 2000473.9 | 4044832 | 4044832 |  | 4044832 | 3804300 | -1900167.6 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | Yes | No | No | No | No | Yes
B19196 | AKB00003 | Mission Valley West Improv 1 (W) | 2025-10-01 | Main Replacements / AKB00003 | Mission Valley West Improv 1 (W) / B19196 | 3 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-02-09 | 2026-05-12 |  | 2026-05-12 | 2023-04-03 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-30 | 2025-10-29 |  | 2025-10-29 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 14632854 | 4730087.8 |  | 4730087.8 | 17666642 | 7853875.98 |  | 7853875.98 | 5249400 | 9961341.7 | 0.75 | 0.75 | 0 | 0 |  | No | No | Yes | No | No | No | No | No | No | No | Yes
B19206 | AJA00001 | Mission Valley West Improv 1 (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Mission Valley West Improv 1 (S) / B19206 | 3 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-02-09 | 2026-05-12 |  | 2026-05-12 | 2023-04-03 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-30 | 2025-10-29 |  | 2025-10-29 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 1463637 | 1463637.39 |  | 1463637.39 | 1814057 | 1814057.21 |  | 1814057.21 | 425400 | 1182357.21 | 0 | 0 | 0.18 | 0.18 |  | No | No | Yes | No | No | No | No | No | No | No | Yes
B20008 | AJA00001 | Colina Del Sol Improv 1 (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Colina Del Sol Improv 1 (S) / B20008 | 9 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Yelsits, Daniel | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-04-27 | 2026-06-10 |  | 2026-06-10 | 2025-07-31 | FY26 | Q4 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-10-14 | 2025-11-28 |  | 2025-11-28 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 10144735 | 10144735 |  | 10144735 | 15471795 | 15471795 |  | 15471795 | 8316033.3 | 2210499 | 0 | 0 | 1.74 | 1.74 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20010 | AKB00003 | Colina Del Sol Improv 1 (W) | 2025-10-01 | Main Replacements / AKB00003 | Colina Del Sol Improv 1 (W) / B20010 | 9 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Yelsits, Daniel | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-04-27 | 2026-06-10 |  | 2026-06-10 | 2025-07-31 | FY26 | Q4 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-10-14 | 2025-11-28 |  | 2025-11-28 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 7444700 | 7444700 |  | 7444700 | 11538138 | 11538138 |  | 11538138 | 6113289.6 | 1618725 | 1.28 | 1.28 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20023 | AKB00003 | La Jolla Improv 3 (W) | 2025-10-01 | Main Replacements / AKB00003 | La Jolla Improv 3 (W) / B20023 | 1 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-14 | 2026-04-20 |  | 2026-04-20 | 2024-01-02 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-08-26 | 2025-11-28 |  | 2025-11-28 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 5000000 | 5000000 |  | 5000000 | 7210067 | 7210067 |  | 7210067 | 2795400 | 2681467 | 0.74 | 0.74 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20038 | AJA00001 | Chollas Creek Improv 1 (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Chollas Creek Improv 1 (S) / B20038 | 9, 4 | Sewer | Job Order Contract | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Jaro, Janice | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-08-13 | 2025-12-16 |  | 2025-12-16 | 2025-03-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-04-23 | 2025-07-03 |  | 2025-07-03 | FY25 | Q4 | FY26 | Q1 |  |  | FY26 | Q1 | 3478000 | 3478000 |  | 3478000 | 5108360 | 5108359.72 |  | 5108359.72 | 2415900 | 1762259.72 | 0 | 0 | 1.12 | 1.12 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20039 | AKB00003 | Chollas Creek Improv 1 (W) | 2025-10-01 | Main Replacements / AKB00003 | Chollas Creek Improv 1 (W) / B20039 | 9, 4 | Water | Job Order Contract | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Jaro, Janice | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  |  | FY25 |  |  | 2025-08-13 | 2025-12-16 |  | 2025-12-16 | 2025-03-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-07-01 | 2025-07-03 |  | 2025-07-03 | FY26 | Q1 | FY26 | Q1 |  |  | FY26 | Q1 | 7297091 | 7297091 |  | 7297091 | 10350519 | 9818519 |  | 9818519 | 6174700 | 1266619 | 2.16 | 2.16 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20060 | AGF00007 | Chicano Park Improvements Phase III | 2025-10-01 | Park Improvements / AGF00007 | Chicano Park Improvements Phase III / B20060 | 8 | Parks | Job Order Contract | Parks & Recreation | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Le, Hong Khanh | Charter & Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-06-08 |  | 2026-06-08 | 2024-02-16 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2026-03-13 |  | 2026-03-13 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 1202064.94 |  | 1202064.94 |  | 2024320.94 |  | 2024320.94 | 1088771 | 199999.94 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
B20096 | AGF00007 | Willie Henderson Sports Complex Imp | 2025-10-01 | Park Improvements / AGF00007 | Willie Henderson Sports Complex Imp / B20096 | 4 | Buildings | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Kieser-Hua, Lin | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-04-13 |  | 2026-04-13 | 2023-10-02 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-12-30 |  | 2025-12-30 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 13393226 |  | 13393226 |  | 18775465 |  | 18775465 | 2290000 | 14233465 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20104 | AGE00001 | Ruffin Canyon Trail | 2025-10-01 | Resource Based Open Space Parks / AGE00001 | Ruffin Canyon Trail / B20104 | Not in Active P6 | Parks | Minor Contract | Parks & Recreation | Open Space | Not in Active P6 | Laura Ball | Not in Active P6 | Not in Active P6 | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-30 | Not in Active P6 | 2025-09-30 | 2025-09-30 | Not in Active P6 | FY26 | Q1 | #VALUE! | #VALUE! | FY26 | Q1 | FY26 | Q1 | 2025-06-30 | Not in Active P6 | 2025-06-30 | 2025-06-30 | FY25 | Q4 | #VALUE! | #VALUE! | FY25 | Q4 | FY25 | Q4 | 90000 | Not in Active P6 | 90000 | 90000 | 311981 | Not in Active P6 | 311981 | 311981 |  |  | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | No
B20122 | ABO00001 | SBWRP Reverse Osmosis System | 2025-10-01 | Metro Treatment Plants / ABO00001 | SBWRP Reverse Osmosis System / B20122 | 8 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Torres, Gabriel | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-03-25 | 2026-03-25 |  | 2026-03-25 | 2023-09-19 | FY26 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-11-17 | 2025-11-17 |  | 2025-11-17 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 19000000 | 19000000 |  | 19000000 | 28238384 | 28238384 |  | 28238384 | 8500000 | 17538384 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20140 | AIL00004 | Mississippi St @ El Cajon Blvd T/Signal | 2025-10-01 | Traffic Signals - Citywide / AIL00004 | Mississippi St @ El Cajon Blvd T/Signal / B20140 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-02-23 | 2026-05-26 |  | 2026-05-26 | 2023-07-13 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-08-29 | 2025-12-02 |  | 2025-12-02 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 1050000 | 1250000 |  | 1250000 | 2000000 | 2300000 |  | 2300000 | 353570 | 1293000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20148 | ABO00001 | NCWRP - Chiller Replacement | 2025-10-01 | Metro Treatment Plants / ABO00001 | NCWRP - Chiller Replacement / B20148 | 6 | Sewer | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Rivera, Jacob | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-06 | 2025-11-19 |  | 2025-11-19 | 2022-03-01 | FY26 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-07-01 | 2025-07-09 |  | 2025-07-09 | FY26 | Q1 | FY26 | Q1 |  |  | FY26 | Q1 | 2100000 | 1600000 |  | 1600000 | 3300000 | 3300000 |  | 3300000 | 1186900 | 1686400 | 0 | 0 | 0 | 0 |  | Yes | No | No | Yes | No | No | No | No | No | No | Yes
B21114 | AGF00007 | Mt View Sports Courts ADA Improvements | 2025-10-01 | Park Improvements / AGF00007 | Mt View Sports Courts ADA Improvements / B21114 | 4 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Kieser-Hua, Lin | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-02-17 | 2026-06-11 |  | 2026-06-11 | 2024-07-16 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-08-06 | 2025-12-01 |  | 2025-12-01 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 458026 | 458026 |  | 458026 | 1233329 | 1233329 |  | 1233329 | 196200 | 688329 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
B22002 | ABL00001 | SV Dam Low Level Outlet Improvements | 2025-10-01 | Standpipe & Reservoir Rehabilitations / ABL00001 | SV Dam Low Level Outlet Improvements / B22002 | Project outside of City limits | Water | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Rivera, Jacob | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-10-28 | 2026-03-06 |  | 2026-03-06 | 2024-01-11 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-07-01 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 3000000 | 2500000 |  | 2500000 | 5366555 | 5366554.94 |  | 5366554.94 | 1210400 | 3311254.94 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22008 | AJA00002 | Chollas View Improv 1 (S) | 2025-10-01 | Pipeline Rehabilitation / AJA00002 | Chollas View Improv 1 (S) / B22008 | 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Mills, Amy | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-02-11 | 2026-05-08 |  | 2026-05-08 | 2026-01-02 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-08-01 | 2025-10-27 |  | 2025-10-27 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 5501610 | 5501610 |  | 5501610 | 8724500 | 8724500 |  | 8724500 | 5501610 | 200800 | 0 | 0 | 4.24 | 4.24 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22012 | AGF00006 | Old Salt Pool Access Stairs | 2025-10-01 | Coastal Erosion and Access / AGF00006 | Old Salt Pool Access Stairs / B22012 | 2 | Parks | Job Order Contract | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | Afagh, Negin | Charter Only | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-03 | 2026-01-02 |  | 2026-01-02 | 2024-10-03 | FY26 | Q1 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-06-12 | 2025-06-16 |  | 2025-06-16 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 853808 | 853807.73 |  | 853807.73 | 1707194 | 1707193.77 |  | 1707193.77 | 449598 | 509193.77 | 0 | 0 | 0 | 0 |  | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B22015 | AKB00003 | Via De La Valle Pipeline | 2025-10-01 | Main Replacements / AKB00003 | Via De La Valle Pipeline / B22015 | 1 | Water | Design Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Rekani, Ronak | Charter Only | On Schedule | On Schedule | [5 empty] | Added - Aug 1st |  |  |  |  | 2026-03-02 |  | 2026-03-02 | 2024-03-06 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-10-13 |  | 2025-10-13 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 6788293 |  | 6788293 |  | 10023393 |  | 10023393 | 4298000 | 3346183 | 1.13 | 1.13 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22031 | AFA00001 | South Chollas Landfill Gas Collection System Improvements | 2025-10-01 | Minor Improvements to Landfills / AFA00001 | South Chollas Landfill Gas Collection System Improvements / B22031 | Not in Active P6 | Landfil | Design Bid Build | Environmental Services | Disposal & Environmental protection | Not in Active P6 | Luis Campos | Not in Active P6 | Not in Active P6 | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-03-30 | Not in Active P6 | 2026-03-30 | 2026-03-30 | Not in Active P6 | FY26 | Q3 | #VALUE! | #VALUE! | FY26 | Q3 | FY26 | Q3 | 2026-01-12 | Not in Active P6 | 2026-01-12 | 2026-01-12 | FY26 | Q3 | #VALUE! | #VALUE! | FY26 | Q3 | FY26 | Q3 | 2000000 | Not in Active P6 | 2000000 | 2000000 | 3000000 | Not in Active P6 | 3000000 | 3000000 |  |  | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | No
B22037 | ABI00001 | Otay WTP Raw Water PS Switchboard Replac | 2025-10-01 | Water Treatment Plants / ABI00001 | Otay WTP Raw Water PS Switchboard Replac / B22037 | 8 | Water | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Rivera, Jacob | Charter Only | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  |  | 2025-08-26 | 2025-11-28 |  | 2025-11-28 | 2024-04-29 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-07-02 | 2025-06-03 |  | 2025-06-03 | FY26 | Q1 | FY25 | Q4 |  |  | FY25 | Q4 | 1100000 | 1100000 |  | 1100000 | 1990000 | 2500000 |  | 2500000 | 729000 | 1208000 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
B22045 | AGF00007 | Hard Court Improvements | 2025-10-01 | Park Improvements / AGF00007 | Hard Court Improvements / B22045 | 8, 4 | Parks | Job Order Contract | Parks & Recreation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | On Schedule | Removed |  | Added - Aug 1st |  |  |  |  | FY25 |  |  |  | 2025-10-01 |  | 2025-10-01 | 2025-09-10 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-05-05 |  | 2025-05-05 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 810000 |  | 810000 |  | 1200000 |  | 1200000 | 810000 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22047 | AGF00007 | Dr. Bertha O. Pendleton Park Improvement | 2025-10-01 | Park Improvements / AGF00007 | Dr. Bertha O. Pendleton Park Improvement / B22047 | 9 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Marquez, Francis Albert | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-09-02 | 2025-02-11 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-03-27 | 2025-03-27 |  | 2025-03-27 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 5557553 | 5451882 | 5451882 | 5451882 | 7852573 | 7852573 |  | 7852573 | 1907190 | 4487473 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22062 | AID00005 | AC Water & Sewer Group 1029 (P) | 2025-10-01 | Resurfacing of City Streets / AID00005 | AC Water & Sewer Group 1029 (P) / B22062 | 4 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Katzenstein, Phuong | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY23 |  | Removed - Aug 1st | 2025-08-18 | 2026-02-02 |  | 2026-02-02 | 2023-02-15 | FY26 | Q1 | FY26 | Q3 |  |  | FY26 | Q3 | 2022-10-05 | 2022-10-05 |  | 2022-10-05 | FY23 | Q2 | FY23 | Q2 |  |  | FY23 | Q2 | 383314 | 540360 |  | 540360 | 407759 | 900600 |  | 900600 | 161240.73 | 246518.28 | 0 | 0 | 0 | 0 |  | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B22080 | ABT00001 | Police HQ Security Fencing | 2025-10-01 | City Facility Improvements / ABT00001 | Police HQ Security Fencing / B22080 | 3 | Buildings | Design Bid Build | General Services | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Lozano, Yazmin | Charter Only | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-11-28 | 2025-08-20 | 2025-08-20 | 2025-08-20 | 2023-11-16 | FY26 | Q2 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-05-20 | 2025-05-20 |  | 2025-05-20 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 1588000 | 1793081.75 | 1793081.75 | 1793081.75 | 2514350 | 3014350 |  | 3014350 | 433000 | 2038350 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
B22085 | ALA00001 | PW Genesee Avenue Median Improv | 2025-10-01 | Pure Water Program / ALA00001 | PW Genesee Avenue Median Improv / B22085 | 6 | Transportation | Design Bid Build | Public Utilities | Infrastructure Project Delivery | IPD_PW | Tadros, Sameh | Block, Colleen | No Project Charter or Amendment | On Schedule | Removed |  | Added - Aug 1st |  |  |  |  | FY25 |  |  |  | 2025-10-24 |  | 2025-10-24 | 2024-12-31 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-03-21 |  | 2025-03-21 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3604165.04 |  | 3604165.04 |  | 4425849.49 |  | 4425849.49 | 1100000 | 2501873.49 | 0 | 0 | 0 | 0 |  | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B22091 | AJA00001 | Golden Hill Improv 2 (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Golden Hill Improv 2 (S) / B22091 | 3, 8 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Stohr, John | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-06-16 |  | 2026-06-16 | 2026-06-11 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2026-02-09 |  | 2026-02-09 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2820220 |  | 2820220 |  | 4520020 |  | 4520020 | 2293200 | 627020 | 0 | 0 | 0.97 | 0.97 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22093 | AKB00003 | Golden Hill Improv 2 (W) | 2025-10-01 | Main Replacements / AKB00003 | Golden Hill Improv 2 (W) / B22093 | 3 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Stohr, John | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-06-16 |  | 2026-06-16 | 2026-06-11 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2026-02-09 |  | 2026-02-09 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 16842000 |  | 16842000 |  | 21332400 |  | 21332400 | 7356600 | 9485400 | 2.78 | 2.78 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22111 | AIL00004 | Center City Traffic Signals-15th Street | 2025-10-01 | Traffic Signals - Citywide / AIL00004 | Center City Traffic Signals-15th Street / B22111 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Guillermo, Erick | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-11-04 | 2025-08-25 | 2025-08-25 | 2025-08-25 | 2025-01-10 | FY26 | Q2 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-03-13 | 2025-03-13 | 2025-03-13 | 2025-03-13 | FY25 | Q3 | FY25 | Q3 | FY25 | Q3 | FY25 | Q3 | 1875000 | 1700000 | 1700000 | 1700000 | 2709981 | 2534981.36 |  | 2534981.36 | 1200000 | 874981.36 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22138 | AID00005 | Crespo Dr (Mecca-Soledad) Improv (P) | 2025-10-01 | Resurfacing of City Streets / AID00005 | Crespo Dr (Mecca-Soledad) Improv (P) / B22138 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-06-22 |  | 2026-06-22 | 2024-12-17 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-12-22 |  | 2025-12-22 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 458800 |  | 458800 |  | 688400 |  | 688400 | 412920 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22139 | ABT00001 | Scripps Miramar Ranch Library Roof Repl | 2025-10-01 | City Facility Improvements / ABT00001 | Scripps Miramar Ranch Library Roof Repl / B22139 | 5 | Buildings | Job Order Contract | General Services | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Hossan, Farhad | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-10-21 | 2025-10-21 |  | 2025-10-21 | 2025-05-02 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 2024-10-01 | 2024-10-01 |  | 2024-10-01 | FY25 | Q2 | FY25 | Q2 |  |  | FY25 | Q2 | 2292271 | 2292271 |  | 2292271 | 3267971 | 3267971 |  | 3267971 | 1700391.6 | 679971 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22149 | AIH00001 | Installation of City Owned SL 2201 (NSG) | 2025-10-01 | Installation of City Owned Street Lights / AIH00001 | Installation of City Owned SL 2201 (NSG) / B22149 | 8, 9, 4 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Xiao, Jie | Charter Only | On Schedule | Removed | [5 empty] | Added - Aug 1st | FY25 |  | Removed - Sept 1st |  | 2025-09-08 |  | 2025-09-08 | 2025-03-03 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-03-04 |  | 2025-03-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 800000 |  | 800000 |  | 1157000 |  | 1157000 | 393570 | 455200 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22157 | AAA00001 | Terminal Parking Lot East Rehabilitation | 2025-10-01 | Montgomery Field / AAA00001 | Terminal Parking Lot East Rehabilitation / B22157 | 7 | Airport | Job Order Contract | Economic Development | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Castaneyra, Jose | Charter Only | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-10-01 | 2025-12-02 |  | 2025-12-02 | 2023-10-17 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-03-28 | 2025-03-28 |  | 2025-03-28 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 885967 | 885967 |  | 885967 | 1558347 | 1558347 |  | 1558347 | 409500 | 936347 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23000 | AFA00001 | West Miramar Central Basin Expansion | 2025-10-01 | Minor Improvements to Landfills / AFA00001 | West Miramar Central Basin Expansion / B23000 | Not in Active P6 | Landfil | Design Bid Build | Environmental Services | Disposal & Environmental protection | Not in Active P6 | Luke Bromley | Not in Active P6 | Not in Active P6 | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-02-01 | Not in Active P6 | 2026-02-01 | 2026-02-01 | Not in Active P6 | FY26 | Q3 | #VALUE! | #VALUE! | FY26 | Q3 | FY26 | Q3 | 2025-11-01 | Not in Active P6 | 2025-11-01 | 2025-11-01 | FY26 | Q2 | #VALUE! | #VALUE! | FY26 | Q2 | FY26 | Q2 | 2900000 | Not in Active P6 | 2900000 | 2900000 | 3750000 | Not in Active P6 | 3750000 | 3750000 |  |  | 0 | 0 | 0 | 0 |  | No | Yes | No | No | No | No | No | No | No | No | No
B23011 | AGF00007 | Willie Henderson Lighting Upgrades | 2025-10-01 | Park Improvements / AGF00007 | Willie Henderson Lighting Upgrades / B23011 | 4 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Kieser-Hua, Lin | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-05 | 2025-07-16 | 2025-07-14 | 2025-07-14 | 2024-09-03 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-02-27 | 2025-02-27 |  | 2025-02-27 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 1301682 | 1301682 | 1300000 | 1300000 | 2132550 | 2132550 |  | 2132550 | 633000 | 999550 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
B23014 | ABI00001 | Miramar WTP Caustic Pumping System | 2025-10-01 | Water Treatment Plants / ABI00001 | Miramar WTP Caustic Pumping System / B23014 | 5 | Water | Design Bid Build | Public Utilities | Infrastructure Project Delivery | IPD_Facilities | Ammerlahn, Parita | Yoshioka, Ryo | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-08-01 | 2025-10-13 |  | 2025-10-13 | 2024-07-01 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-04-04 | 2025-04-04 |  | 2025-04-04 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 600000 | 1317300 |  | 1317300 | 1678250 | 2853250.41 |  | 2853250.41 | 1200000 | 419712.41 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
B23049 | ABI00001 | Miramar WTP Interim Solids Management | 2025-10-01 | Water Treatment Plants / ABI00001 | Miramar WTP Interim Solids Management / B23049 | 5 | Water | Design Bid Build | Public Utilities | Infrastructure Project Delivery | IPD_Facilities | Ammerlahn, Parita | Yoshioka, Ryo | No Project Charter or Amendment | On Schedule | Advertised | Yes | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2026-02-23 |  | 2026-02-23 | 2025-04-08 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-29 | 2025-08-29 | 2025-08-29 | FY00 | Q3 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 |  | 4409785 |  | 4409785 |  | 5612453 |  | 5612453 | 2000000 | 3015565 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
B23071 | AEA00002 | Balboa Park Golf Course Improvements | 2025-10-01 | Balboa Park Golf Course / AEA00002 | Balboa Park Golf Course Improvements / B23071 | 3 | Parks | Design Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Chan, Ling | Charter Only | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-12-16 | 2026-02-09 |  | 2026-02-09 | 2026-06-01 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-06-06 | 2025-06-06 |  | 2025-06-06 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 3300000 | 3300000 |  | 3300000 | 6400000 | 6400000 |  | 6400000 | 2923299 | 999901 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23075 | AKA00003 | Miramar Valve No2 Replacement | 2025-10-01 | Large Diameter Water Transmission PPL / AKA00003 | Miramar Valve No2 Replacement / B23075 | 5 | Water | Job Order Contract | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Adam, Julie | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-06 | 2026-05-06 |  | 2026-05-06 | 2025-01-02 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-09-02 | 2025-12-31 |  | 2025-12-31 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 1100000 | 1200000 |  | 1200000 | 1778105 | 2067521 |  | 2067521 | 500000 | 1181201 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23110 | ABL00001 | Black Mountain Reservoir Spillway Stairs | 2025-10-01 | Standpipe & Reservoir Rehabilitations / ABL00001 | Black Mountain Reservoir Spillway Stairs / B23110 | 5 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Pan, Junmin | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  | On Published List | FY25 |  | Removed - Sept 1st | 2025-10-27 | 2025-11-26 |  | 2025-11-26 | 2025-11-03 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-08-15 | 2025-06-05 |  | 2025-06-05 | FY26 | Q1 | FY25 | Q4 |  |  | FY25 | Q4 | 350000 | 639666.02 |  | 639666.02 | 850000 | 1200000 |  | 1200000 | 229000 | 698000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23117 | ACA00001 | CMP SD Lining IV | 2025-10-01 | Flood Resilience Infrastructure / ACA00001 | CMP SD Lining IV / B23117 | 1, 3, 6, 7, 5, 2 | Storm Water Drainage | Job Order Contract | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Talamayan, Jonard | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-06-26 |  | 2026-06-26 | 2025-11-10 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-12-15 |  | 2025-12-15 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 1453177 |  | 1453177 |  | 3190409 |  | 3190409 | 1620729 | 780122 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23145 | AIL00004 | 47th St & Hartley St HAWK | 2025-10-01 | Traffic Signals - Citywide / AIL00004 | 47th St & Hartley St HAWK / B23145 | 4 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Damnjanovic, Nenad | Charter Only | On Schedule | On Schedule |  | On Published List |  |  | Removed - Sept 1st | On Published List |  |  |  | 2026-05-21 | 2026-06-23 |  | 2026-06-23 | 2025-10-01 | FY26 | Q4 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-11-07 | 2025-12-10 |  | 2025-12-10 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 528480 | 528480 |  | 528480 | 992500 | 992500 |  | 992500 | 528480 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24015 | TBD | Northern Garage Dorm Repl | 2025-10-01 | TBD | Northern Garage Dorm Repl / B24015 | Not in Active P6 | Buildings | Minor Contract | General Services | Logistics | Not in Active P6 | Stephanie Bracci | Not in Active P6 | Not in Active P6 | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-01 | Not in Active P6 | 2025-09-01 | 2025-09-01 | Not in Active P6 | FY26 | Q1 | #VALUE! | #VALUE! | FY26 | Q1 | FY26 | Q1 | 2025-05-01 | Not in Active P6 | 2025-05-01 | 2025-05-01 | FY25 | Q4 | #VALUE! | #VALUE! | FY25 | Q4 | FY25 | Q4 | 50000 | Not in Active P6 | 50000 | 50000 | 362000 | Not in Active P6 | 362000 | 362000 |  |  | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | No
B24135 | TBD | Mission Blvd South Loring Overlay | 2025-10-01 | TBD | Mission Blvd South Loring Overlay / B24135 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2026-01-05 | 2026-01-15 |  | 2026-01-15 | 2025-07-11 | FY26 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-07-28 | 2025-08-07 | 2025-08-07 | 2025-08-07 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 654293 | 902293 |  | 902293 | 1145000 | 1393000 |  | 1393000 | 448825 | 371175 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24137 | TBD | Roswell Street Overlay | 2025-10-01 | TBD | Roswell Street Overlay / B24137 | 4 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Sherzai, Hossai | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | Added - Sept 1st |  |  |  | 2026-01-28 | 2026-01-02 |  | 2026-01-02 | 2025-05-01 | FY26 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-10-28 | 2025-09-26 |  | 2025-09-26 | FY26 | Q2 | FY26 | Q1 |  |  | FY26 | Q1 | 400000 | 400000 |  | 400000 | 710000 | 710000 |  | 710000 | 400000 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25007 | TBD | AC Overlay Group 2507 | 2025-10-01 | TBD | AC Overlay Group 2507 / B25007 | 3, 8 | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-10-03 | 2026-02-17 |  | 2026-02-17 | 2025-02-07 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-07-01 | 2025-09-05 | 2025-09-05 | 2025-09-05 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 6700000 | 6700000 |  | 6700000 | 8300000 | 8295000 |  | 8295000 | 0 | 8000000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25014 | TBD | AC Water & Sewer Group 1033 North (W) | 2025-10-01 | TBD | AC Water & Sewer Group 1033 North (W) / B25014 | 3, 2 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-03-10 | 2026-05-15 |  | 2026-05-15 | 2025-07-16 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-08-27 | 2025-11-03 |  | 2025-11-03 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 14572839 | 15202839 |  | 15202839 | 18302569 | 18302568.3 |  | 18302568.3 | 15500000 | -1382431.7 | 1.51 | 1.51 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25036 | TBD | Pump Station H ATS Emergency | 2025-10-01 | TBD | Pump Station H ATS Emergency / B25036 | 2 | Storm Water Drainage | Emergency (City Forces) | Stormwater | Storm Water | SWD | Phillips, Michael | Vila, Jacquelyn | No Project Charter or Amendment | On Schedule | Removed |  | Added - Sept 1st |  |  |  |  | FY00 |  |  |  | 2025-10-01 |  | 2025-10-01 | 2025-09-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 0 |  | 0 | FY00 | Q3 | FY00 | Q3 |  |  | FY00 | Q3 |  | 228187 |  | 228187 |  | 300000 |  | 300000 | 228187 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25049 | TBD | AC Overlay Group 2511 | 2025-10-01 | TBD | AC Overlay Group 2511 / B25049 | 5 | Transportation | Job Order Contract | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  |  | 2025-09-09 | 2025-09-10 |  | 2025-09-10 | 2025-09-02 | FY26 | Q1 | FY26 | Q1 |  |  | FY26 | Q1 | 2025-07-01 | 2025-05-22 |  | 2025-05-22 | FY26 | Q1 | FY25 | Q4 |  |  | FY25 | Q4 | 2500000 | 3344019.56 |  | 3344019.56 | 3226150 | 4070169.56 |  | 4070169.56 | 3914850 | -1414850 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25063 | TBD | Brown Field Terminal Roof Replacement | 2025-10-01 | TBD | Brown Field Terminal Roof Replacement / B25063 | 8, 2 | Airport | Design Bid Build | Economic Development | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Lewis, Yovanna | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-09 | 2026-04-14 |  | 2026-04-14 | 2025-08-27 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-07-01 | 2025-10-01 |  | 2025-10-01 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 700000 | 700000 |  | 700000 | 1000000 | 1000000 |  | 1000000 | 700000 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25067 | TBD | AC Overlay Group 2511A | 2025-10-01 | TBD | AC Overlay Group 2511A / B25067 | 5 | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-09 | 2025-09-25 | 2025-09-25 | 2025-09-25 | 2025-09-11 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-05-21 | 2025-05-21 |  | 2025-05-21 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 890000 | 632643 | 632643 | 632643 | 1240000 | 1000000 |  | 1000000 | 890000 | -340000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25068 | TBD | AC Overlay Group 2511B | 2025-10-01 | TBD | AC Overlay Group 2511B / B25068 | 5 | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-09 | 2025-10-17 |  | 2025-10-17 | 2025-09-11 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-05-20 | 2025-05-20 |  | 2025-05-20 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 700000 | 623000 |  | 623000 | 1050000 | 920000 |  | 920000 | 890000 | -420000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25069 | TBD | AC Overlay Group 2511C | 2025-10-01 | TBD | AC Overlay Group 2511C / B25069 | 5 | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-09 | 2025-10-17 |  | 2025-10-17 | 2025-09-11 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-05-21 | 2025-05-21 |  | 2025-05-21 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 700000 | 608000 |  | 608000 | 1050000 | 910000 |  | 910000 | 890000 | -430000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25083 | TBD | AC Overlay Group 2520 UUP | 2025-10-01 | TBD | AC Overlay Group 2520 UUP / B25083 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2026-01-05 | 2026-01-15 |  | 2026-01-15 | 2025-09-08 | FY26 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-07-28 | 2025-08-07 | 2025-08-07 | 2025-08-07 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 474929 | 523329 |  | 523329 | 474929 | 523329 |  | 523329 | 474929 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25096 | TBD | 4918/4980 Canterbury Dr SD Emergency | 2025-10-01 | TBD | 4918/4980 Canterbury Dr SD Emergency / B25096 | 9 | Storm Water Drainage | Emergency (As-needed) | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Delgado, Carolina | No Project Charter or Amendment | Awarded | Advertised |  | Added - Oct 1st |  |  |  | Added - Oct 1st |  |  |  |  | 2025-04-08 | 2025-09-17 | 2025-09-17 | 2025-04-08 | FY00 | Q3 | FY25 | Q4 | FY26 | Q1 | FY26 | Q1 |  | 2025-09-16 |  | 2025-09-16 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 4750000 | 4750000 | 4750000 |  | 6000000 |  | 6000000 | 4750000 | 750000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B26000 | TBD | Pump Station 64 Valve Replacement | 2025-10-01 | TBD | Pump Station 64 Valve Replacement / B26000 | Not in Active P6 | Sewer | Design Bid Build | Public Utilities | PUD Wastewater Collections | Not in Active P6 | Gastil, Charles | Not in Active P6 | Not in Active P6 | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-03-31 | Not in Active P6 | 2026-03-31 | 2026-03-31 | Not in Active P6 | FY26 | Q3 | #VALUE! | #VALUE! | FY26 | Q3 | FY26 | Q3 | 2025-12-31 | Not in Active P6 | 2025-12-31 | 2025-12-31 | FY26 | Q2 | #VALUE! | #VALUE! | FY26 | Q2 | FY26 | Q2 | 1400000 | Not in Active P6 | 1400000 | 1400000 | 2500000 | Not in Active P6 | 2500000 | 2500000 |  |  | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | No
B26003 | TBD | Sidewalk Replacement Group 2530 - U & MM | 2025-10-01 | TBD | Sidewalk Replacement Group 2530 - U & MM / B26003 | 6 | Transportation | Design Bid Build | Transportation | Transportation | TD | Hoenes, Craig | Medina, Steven M | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2026-06-26 | 2026-08-28 | 2026-06-26 | 2026-06-26 | 2026-08-17 | FY26 | Q4 | FY27 | Q1 | FY26 | Q4 | FY26 | Q4 | 2025-03-13 | 2026-05-14 | 2025-03-13 | 2025-03-13 | FY25 | Q3 | FY26 | Q4 | FY25 | Q3 | FY25 | Q3 | 1700000 | 1600000 | 1700000 | 1700000 | 3100000 | 3100000 | 3100000 | 3100000 |  |  | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B26015 | TBD | Jamacha Lomita Storm Drain (P) | 2025-10-01 | TBD | Jamacha Lomita Storm Drain (P) / B26015 | 4 | Storm Water Drainage | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Shamoun, Ikhlass | No Project Charter or Amendment | On Schedule | Removed |  | Added - Sept 1st |  |  |  |  | FY25 |  |  |  | 2025-08-13 |  | 2025-08-13 | 2019-04-02 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-21 |  | 2025-01-21 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 197881.1 |  | 197881.1 |  | 197881.1 |  | 197881.1 | 197881.1 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B26039 | TBD | Carmel Mountain TS Emergency | 2025-10-01 | TBD | Carmel Mountain TS Emergency / B26039 | 5 | Transportation | Sole Source Emergency | Transportation | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Pan, Junmin | No Project Charter or Amendment | Awarded | Advertised |  | Added - Sept 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2025-07-18 |  | 2025-07-18 | 2025-07-18 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-07-18 |  | 2025-07-18 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2200000 |  | 2200000 |  | 2500000 |  | 2500000 | 1700000 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
L17000.7 | L17000 | Office Trailers Replacement | 2025-10-01 | Miramar Landfill Facility Improvements / L17000 | Office Trailers Replacement / L17000.7 | Not in Active P6 | Landfill | Design Build | Environmental Services | Protection | Not in Active P6 | Luis Campos | Not in Active P6 | Not in Active P6 | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-07-30 | Not in Active P6 | 2025-07-30 | 2025-07-30 | Not in Active P6 | FY26 | Q1 | #VALUE! | #VALUE! | FY26 | Q1 | FY26 | Q1 | 2025-03-10 | Not in Active P6 | 2025-03-10 | 2025-03-10 | FY25 | Q3 | #VALUE! | #VALUE! | FY25 | Q3 | FY25 | Q3 | 4500000 | Not in Active P6 | 4500000 | 4500000 | 5000000 | Not in Active P6 | 5000000 | 5000000 |  |  | 0 | 0 | 0 | 0 |  | Yes | No | Yes | No | No | No | No | No | No | No | No
L20000.2 | L20000 | Rancho Bernardo CP Dog Park | 2025-10-01 | Rancho Bernardo CP Improvements / L20000 | Rancho Bernardo CP Dog Park / L20000.2 | 5 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Grotzinger, Juliana | Charter Only | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-11-26 | 2025-11-14 |  | 2025-11-14 | 2023-04-03 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-05-19 | 2025-05-19 |  | 2025-05-19 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 3165000 | 3428000 |  | 3428000 | 5710340 | 5700000 |  | 5700000 | 743000 | 4247000 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
S00869 | S00869 | Palm Avenue Interstate 805 Interchange | 2025-10-01 | Palm Avenue Interstate 805 Interchange / S00869 | Palm Avenue Interstate 805 Interchange / S00869 | 8 | Transportation | Agency/ Developer Managed Built - City Paid | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter Amendment Only | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2026-02-26 | 2026-02-05 |  | 2026-02-05 | 2023-11-17 | FY26 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-06-10 | 2025-06-10 |  | 2025-06-10 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 31500000 | 31500000 |  | 31500000 | 51730634 | 51730633.53 |  | 51730633.53 | 23356000 | 12798392.53 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
S00995 | S00995 | HIDDEN TRAILS NEIGHBORHOOD PARK | 2025-10-01 | Hidden Trails Neighborhood Park / S00995 | HIDDEN TRAILS NEIGHBORHOOD PARK / S00995 | 8 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Chan, Ling | Charter Only | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-10-03 | 2025-09-08 | 2025-09-08 | 2025-09-08 | 2020-12-01 | FY26 | Q2 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-04-21 | 2025-04-21 |  | 2025-04-21 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 8685000 | 8685000 | 8685000 | 8685000 | 12577230 | 12577229.6 |  | 12577229.6 | 3272000 | 7344229.6 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
S14006 | S14006 | El Cuervo Adobe Improvements | 2025-10-01 | El Cuervo Adobe Improvements / S14006 | El Cuervo Adobe Improvements / S14006 | 1 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Stoks, Shannon | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-02 | 2026-04-07 |  | 2026-04-07 | 2016-08-22 | FY26 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 | 2025-10-02 | 2026-01-06 |  | 2026-01-06 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 292315 | 292315 |  | 292315 | 956000 | 956000.4 |  | 956000.4 | 126000 | 706000.4 | 0 | 0 | 0 | 0 |  | Yes | No | No | Yes | Yes | No | Yes | Yes | Yes | No | Yes
S16032 | S16032 | Solana Highlands NP-Comfort Station | 2025-10-01 | Solana Highlands NP-Comfort Station Development / S16032 | Solana Highlands NP-Comfort Station / S16032 | 1 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Tobchi, Rawan | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-12-15 | 2025-12-15 |  | 2025-12-15 | 2021-09-15 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-12-01 | 2025-12-01 |  | 2025-12-01 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 4161200 | 4461200 |  | 4461200 | 5833600 | 6133600 |  | 6133600 | 967000 | 3942600 | 0 | 0 | 0 | 0 |  | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Yes
S20012 | S20012 | Chollas Creek Oak Park Trail | 2025-10-01 | Chollas Creek Oak Park Trail / S20012 | Chollas Creek Oak Park Trail / S20012 | 9, 4 | Parks | Design Build | Parks & Recreation | City Planning | PLANNING | Busby, Breanne | Busby, Breanne | No Project Charter or Amendment | On Schedule | Removed |  | Added - Aug 1st |  |  |  |  | FY00 |  |  |  | 2026-05-18 |  | 2026-05-18 | 2024-08-02 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 0 |  | 0 | FY00 | Q3 | FY00 | Q3 |  |  | FY00 | Q3 |  | 2380000 |  | 2380000 |  | 4111500 |  | 4111500 | 1992000 | 1143000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S20015 | S20015 | Ocean Beach Branch Library | 2025-10-01 | Ocean Beach Branch Library / S20015 | Ocean Beach Branch Library / S20015 | 2 | Buildings | Design Build | Library | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Getz, Shannon | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-01-02 | 2026-02-04 |  | 2026-02-04 | 2022-08-02 | FY26 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 | 2025-10-27 | 2025-12-24 |  | 2025-12-24 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 8195649 | 8195649 |  | 8195649 | 12751489 | 12751489 |  | 12751489 | 5075105 | 4251716 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S21004 | S21004 | Rancho Bernardo Industrial Pump Stn Repl | 2025-10-01 | Rancho Bernardo Industrial Pump Stn Replacement / S21004 | Rancho Bernardo Industrial Pump Stn Repl / S21004 | 5 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Safavi, Ramin | Charter & Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Sept 1st |  |  |  |  | 2026-05-18 |  | 2026-05-18 | 2025-09-15 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-11-04 |  | 2025-11-04 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 9308762 |  | 9308762 |  | 15511809 |  | 15511809 | 9308762 | -1 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
S23010 | S23010 | MTRP Trail System Management | 2025-10-01 | MTRP Trail System Management / S23010 | MTRP Trail System Management / S23010 | Not in Active P6 | Parks | Minor Contract | Parks & Recreation | Open Space | Not in Active P6 | Laura Ball | Not in Active P6 | Not in Active P6 | On Schedule | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-30 | Not in Active P6 | 2025-09-30 | 2025-09-30 | Not in Active P6 | FY26 | Q1 | #VALUE! | #VALUE! | FY26 | Q1 | FY26 | Q1 | 2025-06-30 | Not in Active P6 | 2025-06-30 | 2025-06-30 | FY25 | Q4 | #VALUE! | #VALUE! | FY25 | Q4 | FY25 | Q4 | 90000 | Not in Active P6 | 90000 | 90000 | 200000 | Not in Active P6 | 200000 | 200000 |  |  | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | No
S23013 | TBD | City Hts Library Performance Annex Imp | 2025-10-01 | TBD | City Hts Library Performance Annex Imp / S23013 | 9 | Buildings | Design Build | Library | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Huang, Tina | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY25 |  | Removed - Aug 1st | 2025-09-08 | 2025-08-28 | 2025-08-28 | 2025-08-28 | 2025-06-30 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 | 2025-03-25 | 2025-03-25 |  | 2025-03-25 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 5650000 | 5417724 | 5417724 | 5417724 | 6514956 | 6532680 |  | 6532680 | 4650000 | 916724 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S24013 | TBD | Paradise Hills Community Park Trail | 2025-10-01 | TBD | Paradise Hills Community Park Trail / S24013 | Not in Active P6 | Parks | Minor Contract | Parks & Recreation | Administration | Not in Active P6 | Shannon Scoggins | Not in Active P6 | Not in Active P6 | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2026-03-01 | Not in Active P6 | 2026-03-01 | 2026-03-01 | Not in Active P6 | FY26 | Q3 | #VALUE! | #VALUE! | FY26 | Q3 | FY26 | Q3 | 2025-12-01 | Not in Active P6 | 2025-12-01 | 2025-12-01 | FY26 | Q2 | #VALUE! | #VALUE! | FY26 | Q2 | FY26 | Q2 | 700000 | Not in Active P6 | 700000 | 700000 | 750000 | Not in Active P6 | 750000 | 750000 |  |  | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | No
S00800 | S00800 | SAN CARLOS BRANCH LIBRARY | 2025-10-01 | San Carlos Branch Library / S00800 | SAN CARLOS BRANCH LIBRARY / S00800 | 7 | Buildings | Design Build | Library | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Huang, Tina | No Project Charter or Amendment | Removed | Removed |  |  | FY27 |  |  | Added - Sept 1st | FY24 |  |  |  | 2026-08-03 |  | 2026-08-03 | 2011-07-27 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2024-03-01 |  | 2024-03-01 | FY00 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 |  | 32803563 |  | 32803563 |  | 47500000 |  | 47500000 | 13000000 | 32834926 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20116 | ABT00001 | Air & Space Museum Roof Replacement | 2025-10-01 | City Facility Improvements / ABT00001 | Air & Space Museum Roof Replacement / B20116 | 3 | Buildings | Design Bid Build | General Services | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Lozano, Yazmin | Charter Only | Removed | Removed |  | On Published List | FY27 |  | Removed - Sept 1st |  | FY25 |  | Removed - Aug 1st | 2025-12-31 | 2026-07-16 |  | 2026-07-16 | 2024-07-01 | FY26 | Q2 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-06-23 | 2025-06-23 |  | 2025-06-23 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 5349400 | 9075000 |  | 9075000 | 8100831 | 12198991 |  | 12198991 | 4174000 | 5408991 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
L22000.3 | L22000 | Alvarado Laboratory ImprovementsTrailers | 2025-10-01 | Alvarado Laboratory Improvements / L22000 | Alvarado Laboratory ImprovementsTrailers / L22000.3 | 7 | Water | Job Order Contract | Public Utilities | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Huang, Tina | No Project Charter or Amendment | Removed | Advertised | Yes | Added - Aug 1st | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-11 |  | 2026-09-11 | 2024-07-18 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2025-10-01 |  | 2025-10-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 4134049 |  | 4134049 |  | 6000000 |  | 6000000 | 1090800 | 4400000 | 0 | 0 | 0 | 0 |  | Yes | No | No | No | No | No | No | No | No | No | Yes
L22000.1 | L22000 | Alvarado Laboratory Improvements Phase 1 | 2025-10-01 | Alvarado Laboratory Improvements / L22000 | Alvarado Laboratory Improvements Phase 1 / L22000.1 | 7 | Buildings | Design Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Huang, Tina | Charter Only | Removed | Advertised | Yes | Added - Aug 1st | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-11 |  | 2026-09-11 | 2026-04-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2025-08-21 | 2025-08-22 | 2025-08-22 | FY00 | Q3 | FY26 | Q1 | FY26 | Q1 | FY26 | Q1 |  | 109303239 |  | 109303239 |  | 161245481.7 |  | 161245481.7 | 80030700 | 41022481.7 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23030 | AIL00005 | Linda Vista & Comstock Intersection Upg | 2025-10-01 | Traffic Signals - Modify & Modernize / AIL00005 | Linda Vista & Comstock Intersection Upg / B23030 | 7 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Chan, Chun Yu | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2026-04-24 | 2026-07-16 |  | 2026-07-16 | 2025-01-02 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-12-22 | 2026-03-16 |  | 2026-03-16 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 729720 | 955250 |  | 955250 | 1281200 | 1506730 |  | 1506730 | 729720 | 225530 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22020 | AKB00003 | Fairmount Park Improv 1 (W) | 2025-10-01 | Main Replacements / AKB00003 | Fairmount Park Improv 1 (W) / B22020 | 9 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2025-11-26 | 2026-08-24 |  | 2026-08-24 | 2025-04-01 | FY26 | Q2 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-07-23 | 2025-10-22 |  | 2025-10-22 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 5610479 | 5610479.44 |  | 5610479.44 | 8116429 | 8116429.44 |  | 8116429.44 | 3237120 | 2894129.44 | 0.63 | 0.63 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21075 | AJA00001 | Valencia Park Improv 3 (s) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Valencia Park Improv 3 (s) / B21075 | 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Zare Afifi, Mehrnaz | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2025-12-23 | 2026-08-31 |  | 2026-08-31 | 2024-05-14 | FY26 | Q2 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-08-06 | 2026-03-24 |  | 2026-03-24 | FY26 | Q1 | FY26 | Q3 |  |  | FY26 | Q3 | 3940000 | 3940000 |  | 3940000 | 5465708 | 5465707.89 |  | 5465707.89 | 3540000 | 1027707.89 | 0 | 0 | 0.6 | 0.6 |  | No | No | No | No | No | No | No | No | No | No | Yes
B19071 | AIL00005 | Traffic Signal Mods Grp 19-02 | 2025-10-01 | Traffic Signals - Modify & Modernize / AIL00005 | Traffic Signal Mods Grp 19-02 / B19071 | 2 | Transportation | Design Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Kim, Jinsil | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2026-01-09 | 2026-11-06 |  | 2026-11-06 | 2022-09-01 | FY26 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 | 2025-07-31 | 2026-04-30 |  | 2026-04-30 | FY26 | Q1 | FY26 | Q4 |  |  | FY26 | Q4 | 380350 | 380350 |  | 380350 | 850000 | 850000 |  | 850000 | 594500 | -64150 | 0 | 0 | 0 | 0 |  | No | No | Yes | No | No | No | No | No | No | No | Yes
B16158 | AKA00003 | Otay 2nd Pipeline Phase 3 | 2025-10-01 | Large Diameter Water Transmission PPL / AKA00003 | Otay 2nd Pipeline Phase 3 / B16158 | Project outside of City limits | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Salha, Rawsan | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2026-04-13 | 2026-07-14 |  | 2026-07-14 | 2020-10-01 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-09-30 | 2025-12-31 |  | 2025-12-31 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 28600000 | 28600000 |  | 28600000 | 42266000 | 42266000 |  | 42266000 | 10116000 | 29630000 | 0.64 | 0.64 | 0 | 0 |  | Yes | No | No | No | Yes | No | No | No | No | No | Yes
B19181 | AGF00004 | Dusty Rhodes Playground | 2025-10-01 | Mission Bay Improvements / AGF00004 | Dusty Rhodes Playground / B19181 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Nguyen, Kevin | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY27 |  |  | Added - Sept 1st |  |  |  |  | 2026-10-07 |  | 2026-10-07 | 2022-05-31 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-03-30 |  | 2026-03-30 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 4000000 |  | 4000000 |  | 5205715 |  | 5205715 | 1015640 | 3261715 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B19180 | AGF00004 | Dusty Rhodes Comfort Station Improvement | 2025-10-01 | Mission Bay Improvements / AGF00004 | Dusty Rhodes Comfort Station Improvement / B19180 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Nguyen, Kevin | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY27 |  |  | Added - Sept 1st |  |  |  |  | 2026-10-07 |  | 2026-10-07 | 2022-05-31 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-03-30 |  | 2026-03-30 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 1200000 |  | 1200000 |  | 2765334.15 |  | 2765334.15 | 1015640 | 821334.15 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B19158 | AGF00004 | Dusty Rhodes Parking Lot Improvements | 2025-10-01 | Mission Bay Improvements / AGF00004 | Dusty Rhodes Parking Lot Improvements / B19158 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Nguyen, Kevin | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY27 |  |  | Added - Sept 1st |  |  |  |  | 2026-10-07 |  | 2026-10-07 | 2022-05-31 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-03-30 |  | 2026-03-30 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 785629 |  | 785629 |  | 1785629 |  | 1785629 | 338720 | 1143629 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S23008 | S23008 | Beyer Park Development Phase II | 2025-10-01 | Beyer Park Development Phase II / S23008 | Beyer Park Development Phase II / S23008 | 8 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Rios, Richard | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-28 |  | 2026-10-28 | 2026-04-03 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-21 |  | 2026-04-21 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 12700000 |  | 12700000 |  | 17988000 |  | 17988000 | 11387000 | 2651000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S22004 | S22004 | John Baca Park | 2025-10-01 | John Baca Park / S22004 | John Baca Park / S22004 | 7 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Rios, Richard | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-08 |  | 2026-12-08 | 2026-06-11 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | ac |  | 2026-05-29 |  | 2026-05-29 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2906100 |  | 2906100 |  | 4996000 |  | 4996000 | 2906100 | 50000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S22002 | S22002 | Grove Neighborhood Park | 2025-10-01 | Southwest Neighborhood Park / S22002 | Grove Neighborhood Park / S22002 | 8 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Marshall, Lydia | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-08-24 |  | 2026-08-24 | 2024-05-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-01-28 |  | 2026-01-28 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 985500 |  | 985500 |  | 4000000 |  | 4000000 | 17822000 | -15558244 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S22001 | S22001 | North/South Metro Interceptors Rehab | 2025-10-01 | North/South Metro Interceptors Rehablitation / S22001 | North/South Metro Interceptors Rehab / S22001 | 3, 8, 7, 2 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Safavi, Ramin | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-14 |  | 2026-09-14 | 2026-02-20 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-03-05 |  | 2026-03-05 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 52477482 |  | 52477482 |  | 76690776 |  | 76690776 | 25350000 | 44730776 | 0 | 0 | 2.3 | 2.3 |  | No | No | No | No | No | No | No | No | No | No | Yes
S21003 | S21003 | EMTS Lab Remodel at NTC | 2025-10-01 | Enviro Monitoring Tech Svcs Div Lab Remodel at NTC / S21003 | EMTS Lab Remodel at NTC / S21003 | 2 | Buildings | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Hossan, Farhad | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-03 |  | 2026-11-03 | 2025-11-04 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-01 |  | 2026-05-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 38352047 |  | 38352047 |  | 54125501 |  | 54125501 | 21971700 | 21685501 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S15019 | S15019 | Alvarado Trunk Sewer Phase IV | 2025-10-01 | Alvarado Trunk Sewer Phase IV / S15019 | Alvarado Trunk Sewer Phase IV / S15019 | 7, 9 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | Charter & Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-23 |  | 2026-07-23 | 2020-04-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2025-10-01 |  | 2025-10-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 54300000 |  | 54300000 |  | 72349085 |  | 72349085 | 17279200 | 46642935 | 0 | 0 | 5.01 | 5.01 |  | No | No | No | No | Yes | Yes | No | No | No | No | Yes
S14017 | S14017 | Fire Station No. 51 Skyline Hills | 2025-10-01 | Fire Station No. 51 - Skyline Hills / S14017 | Fire Station No. 51 Skyline Hills / S14017 | 4 | Buildings | Design Bid Build | Fire-Rescue | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Castaneyra, Jose | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-08-10 |  | 2026-08-10 | 2017-05-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2025-11-17 |  | 2025-11-17 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 20000000 |  | 20000000 |  | 31255000 |  | 31255000 | 9982000 | 17943000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S13008 | S13008 | Mohnike Adobe and Barn Restoration | 2025-10-01 | Mohnike Adobe and Barn Restoration / S13008 | Mohnike Adobe and Barn Restoration / S13008 | 6 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Getz, Shannon | Charter & Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-03 |  | 2026-09-03 | 2022-11-29 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-25 |  | 2026-02-25 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 3451214 |  | 3451214 |  | 5086017.51 |  | 5086017.51 | 1950000 | 2389017.51 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S00951 | S00951 | Coastal Rail Trail | 2025-10-01 | Coastal Rail Trail / S00951 | Coastal Rail Trail / S00951 | 1, 6 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Rekani, Ronak | Charter Amendment Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2027-02-24 |  | 2027-02-24 | 2025-02-14 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 2026-06-15 |  | 2026-06-15 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 19837589 |  | 19837589 |  | 32034184.41 |  | 32034184.41 | 19157589 | 1876179.3 | 0 | 0 | 0 | 0 |  | No | No | No | No | Yes | No | No | No | No | No | Yes
S00856 | S00856 | El Camino Real to ViaDeLaValle (1/2mile) | 2025-10-01 | El Camino Real to ViaDeLaValle (1/2 mile) / S00856 | El Camino Real to ViaDeLaValle (1/2mile) / S00856 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Randles, Jacob | Charter Amendment Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-12 |  | 2026-10-12 | 2023-04-03 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-03 |  | 2026-04-03 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 56749356 |  | 56749356 |  | 91969949.5 |  | 91969949.5 | 19425981 | 54020556.5 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S00784 | S00784 | FIRE STATION #49 OTAY MESA | 2025-10-01 | Fire Station No. 49 - Otay Mesa / S00784 | FIRE STATION #49 OTAY MESA / S00784 | 8 | Buildings | Design Build | Fire-Rescue | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Arredondo, Monica | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2027-06-04 |  | 2027-06-04 | 2027-06-04 | FY00 | Q3 | FY27 | Q4 |  |  | FY27 | Q4 |  | 2026-06-08 |  | 2026-06-08 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 23317263 |  | 23317263 |  | 39165038 |  | 39165038 | 22125000 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
L24005.2 | TBD | Boston Avenue and South 30th Street | 2025-10-01 | TBD | Boston Avenue and South 30th Street / L24005.2 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Sherzai, Hossai | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-01 |  | 2026-12-01 | 2026-12-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-06-01 |  | 2026-06-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 637120 |  | 637120 |  | 1055300 |  | 1055300 | 663600 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
L24005.1 | TBD | Bardsley Street and Newton Avenue | 2025-10-01 | TBD | Bardsley Street and Newton Avenue / L24005.1 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Sherzai, Hossai | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-01 |  | 2026-12-01 | 2026-12-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-06-01 |  | 2026-06-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1120392 |  | 1120392 |  | 1832800 |  | 1832800 | 1152600 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
L24004.1 | TBD | Kearny Mesa Trunk Sewer Phase 1 | 2025-10-01 | TBD | Kearny Mesa Trunk Sewer Phase 1 / L24004.1 | 3, 6, 7 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Safavi, Ramin | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-06 |  | 2026-10-06 | 2026-03-20 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-03-27 |  | 2026-03-27 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 4876110 |  | 4876110 |  | 11317986 |  | 11317986 | 4876110 | 0 | 0 | 0 | 2.7 | 2.7 |  | No | No | No | No | No | No | No | No | No | No | Yes
L24003.1 | TBD | Howard Lane Park | 2025-10-01 | TBD | Howard Lane Park / L24003.1 | 8 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | Salguero, Bryan | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-08-03 |  | 2026-08-03 | 2026-12-24 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-02 |  | 2026-02-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 4000000 |  | 4000000 |  | 5000000 |  | 5000000 | 4000000 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
L23001.1 | L230011 | El Camino Real Pipeline North | 2025-10-01 | El Camino Real Pipeline North / L230011 | El Camino Real Pipeline North / L23001.1 | 1 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Randles, Jacob | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-08-12 |  | 2026-08-12 | 2024-07-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-02 |  | 2026-02-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2204805 |  | 2204805 |  | 3610098.5 |  | 3610098.5 | 1710000 | 985098.5 | 0.51 | 0.51 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
L20000.1 | L20000 | Rancho Bernardo CP Lighting Improvements | 2025-10-01 | Rancho Bernardo CP Improvements / L20000 | Rancho Bernardo CP Lighting Improvements / L20000.1 | 5 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Grotzinger, Juliana | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-09 |  | 2026-09-09 | 2026-04-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-03-02 |  | 2026-03-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2721518 |  | 2721518 |  | 4000000 |  | 4000000 | 0 | 3162300 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
L14005.1 | L14005 | Demolition of Loma Land Structures | 2025-10-01 | Sunset Cliffs Park Drainage Improvements / L14005 | Demolition of Loma Land Structures / L14005.1 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Kieser-Hua, Lin | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-27 |  | 2026-10-27 | 2018-02-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-20 |  | 2026-04-20 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1462500 |  | 1462500 |  | 3164990 |  | 3164990 | 320000 | 2329990 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | Yes | No | No | No | Yes
B25016 | TBD | AC Water & Sewer Group 1033 West (S) | 2025-10-01 | TBD | AC Water & Sewer Group 1033 West (S) / B25016 | 3 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | Charter Amendment Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-08-26 |  | 2026-08-26 | 2026-07-16 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-17 |  | 2026-02-17 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 6124568.81 |  | 6124568.81 |  | 7481801.53 |  | 7481801.53 | 6124568.81 | -296400.86 | 0 | 0 | 0.62 | 0.62 |  | No | No | No | No | No | No | No | No | No | No | Yes
B25015 | TBD | AC Water & Sewer Group 1033 West (W) | 2025-10-01 | TBD | AC Water & Sewer Group 1033 West (W) / B25015 | 3 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | Charter Amendment Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-08-26 |  | 2026-08-26 | 2026-07-16 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-17 |  | 2026-02-17 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 20469105 |  | 20469105 |  | 24984395.07 |  | 24984395.07 | 20375431 | -892402.35 | 2.07 | 2.07 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24117 | TBD | 34th & Adams HAWK | 2025-10-01 | TBD | 34th & Adams HAWK / B24117 | 9 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-02 |  | 2026-11-02 | 2026-06-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-24 |  | 2026-04-24 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 633600 |  | 633600 |  | 1218900 |  | 1218900 | 633600 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24113 | TBD | PLWTP Sludge Pump Replacement | 2025-10-01 | TBD | PLWTP Sludge Pump Replacement / B24113 | 2 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Oriqat, Bilal | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-25 |  | 2026-09-25 | 2026-09-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-03-18 |  | 2026-03-18 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 5188000 |  | 5188000 |  | 8300000 |  | 8300000 | 4000000 | 1900000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24107 | TBD | TS Upgrades - Camino Ruiz & TX Madison | 2025-10-01 | TBD | TS Upgrades - Camino Ruiz & TX Madison / B24107 | 3, 6 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Xiao, Jie | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-30 |  | 2026-11-30 | 2025-07-15 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-20 |  | 2026-05-20 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1200000 |  | 1200000 |  | 1805000 |  | 1805000 | 1200000 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24101 | TBD | Southcrest CP Lighting Improvements | 2025-10-01 | TBD | Southcrest CP Lighting Improvements / B24101 | 8 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Marshall, Lydia | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-15 |  | 2026-12-15 | 2026-10-28 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-06-05 |  | 2026-06-05 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1353000 |  | 1353000 |  | 2347000 |  | 2347000 | 756000 | 1363.31 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23146 | AIL00001 | Gompers Prep 47th St Safety Enhancements | 2025-10-01 | Traffic Calming / AIL00001 | Gompers Prep 47th St Safety Enhancements / B23146 | 4 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Xiao, Jie | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-13 |  | 2026-11-13 | 2025-10-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-06 |  | 2026-05-06 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2400000 |  | 2400000 |  | 3410570 |  | 3410570 | 1182330 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23086 | AIH00002 | Sunset Cliffs Devonshire Series Circuit | 2025-10-01 | Street Light Circuit Upgrades / AIH00002 | Sunset Cliffs Devonshire Series Circuit / B23086 | 2 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Kim, Jinsil | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-18 |  | 2026-11-18 | 2026-09-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-11 |  | 2026-05-11 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1517194 |  | 1517194 |  | 3406300 |  | 3406300 | 1973160 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23085 | ALA00001 | NCPWF/NCWRP Warehouse Storage | 2025-10-01 | Pure Water Program / ALA00001 | NCPWF/NCWRP Warehouse Storage / B23085 | 6 | Water | Design Build | Public Utilities | Infrastructure Project Delivery | IPD_PW | Lotfi, Elham | Meredith, William | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-08-28 |  | 2026-08-28 | 2026-06-05 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-01-21 |  | 2026-01-21 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 10100000 |  | 10100000 |  | 12188000 |  | 12188000 | 10100000 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23076 | AIL00005 | 32nd St & Market St Intersection Upgrade | 2025-10-01 | Traffic Signals - Modify & Modernize / AIL00005 | 32nd St & Market St Intersection Upgrade / B23076 | 9 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Xiao, Jie | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-09 |  | 2026-12-09 | 2024-12-31 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-06-01 |  | 2026-06-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1093040 |  | 1093040 |  | 1450000 |  | 1450000 | 381240 | 711800 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23038 | AKB00003 | Pacific Beach Improv 2 (W) | 2025-10-01 | Main Replacements / AKB00003 | Pacific Beach Improv 2 (W) / B23038 | 1 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-01 |  | 2026-09-01 | 2026-09-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-04-22 |  | 2026-04-22 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 7129170 |  | 7129170 |  | 11348860 |  | 11348860 | 10350810 | -4323740 | 3.12 | 3.12 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23037 | AJA00001 | Pacific Beach Improv 2 (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Pacific Beach Improv 2 (S) / B23037 | 1 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-01 |  | 2026-09-01 | 2026-09-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-04-22 |  | 2026-04-22 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 3774870 |  | 3774870 |  | 5963133 |  | 5963133 | 3774870 | 418533 | 0 | 0 | 2.47 | 2.47 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23031 | AFA00001 | Miramar Pl Fleet Main Facility Upgrade | 2025-10-01 | Minor Improvements to Landfills / AFA00001 | Miramar Pl Fleet Main Facility Upgrade / B23031 | 6 | Buildings | Job Order Contract | Environmental Services | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Getz, Shannon | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-07 |  | 2026-07-07 | 2024-05-17 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-04-01 |  | 2026-04-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1650000 |  | 1650000 |  | 2904500 |  | 2904500 | 553500 | 2174500 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22150 | AID00005 | Palm Ave I-5 to Georgia Street Repairs | 2025-10-01 | Resurfacing of City Streets / AID00005 | Palm Ave I-5 to Georgia Street Repairs / B22150 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-13 |  | 2026-10-13 | 2024-09-05 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-03-26 |  | 2026-03-26 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2680000 |  | 2680000 |  | 4000000 |  | 4000000 | 1393020 | 1786500 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22135 | AIL00001 | Milton St Burgener Blvd Curb Ext (NSG) | 2025-10-01 | Traffic Calming / AIL00001 | Milton St Burgener Blvd Curb Ext (NSG) / B22135 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Chan, Chun Yu | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-19 |  | 2026-10-19 | 2026-03-11 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-13 |  | 2026-04-13 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 723780 |  | 723780 |  | 1072200 |  | 1072200 | 723780 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22130 | ACA00001 | Famosa Slough Alley Slope Restoration | 2025-10-01 | Flood Resilience Infrastructure / ACA00001 | Famosa Slough Alley Slope Restoration / B22130 | 2 | Storm Water Drainage | Design Bid Build | Stormwater | Storm Water | SWD | Eckert, Kristopher | Salvani, Anthony | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-05 |  | 2026-11-05 | 2026-10-26 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-29 |  | 2026-04-29 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2104442 |  | 2104442 |  | 4366619 |  | 4366619 | 2104442 | 88944 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22033 | ACA00001 | Crespo Dr (Mecca-Soledad) Improv (SD) | 2025-10-01 | Flood Resilience Infrastructure / ACA00001 | Crespo Dr (Mecca-Soledad) Improv (SD) / B22033 | 1 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-05 |  | 2026-10-05 | 2024-05-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-09 |  | 2026-04-09 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 84300 |  | 84300 |  | 131277.31 |  | 131277.31 | 63180 | 6877.31 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21132 | AKB00003 | Crespo Dr (Mecca-Soledad) Improv (W) | 2025-10-01 | Main Replacements / AKB00003 | Crespo Dr (Mecca-Soledad) Improv (W) / B21132 | 1 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-05 |  | 2026-10-05 | 2024-05-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-09 |  | 2026-04-09 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 918600 |  | 918600 |  | 1474335.67 |  | 1474335.67 | 642240 | 241735.67 | 0.31 | 0.31 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21131 | AJA00001 | Crespo Dr (Mecca-Soledad) Improv (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Crespo Dr (Mecca-Soledad) Improv (S) / B21131 | 1 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-05 |  | 2026-10-05 | 2024-05-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-09 |  | 2026-04-09 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 575200 |  | 575200 |  | 930514.09 |  | 930514.09 | 431370 | 177914.09 | 0 | 0 | 0.13 | 0.13 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21130 | ABI00001 | Alvarado WTP Area 40 Sludge PS | 2025-10-01 | Water Treatment Plants / ABI00001 | Alvarado WTP Area 40 Sludge PS / B21130 | 7 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Vega, Melissa | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-24 |  | 2026-12-24 | 2026-03-23 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-06-16 |  | 2026-06-16 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1880100 |  | 1880100 |  | 3375000 |  | 3375000 | 1880100 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21125 | ABP00001 | Sewer Pump Station 11 Repair | 2025-10-01 | Pump Station Restorations / ABP00001 | Sewer Pump Station 11 Repair / B21125 | 2 | Sewer | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Rivera, Jacob | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-18 |  | 2026-09-18 | 2025-02-13 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-03-11 |  | 2026-03-11 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 1750000 |  | 1750000 |  | 3000000 |  | 3000000 | 1425600 | 545000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21120 | AIL00005 | Palm Ave Traffic Signal Modification(VZ) | 2025-10-01 | Traffic Signals - Modify & Modernize / AIL00005 | Palm Ave Traffic Signal Modification(VZ) / B21120 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-04 |  | 2026-11-04 | 2024-09-03 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-28 |  | 2026-04-28 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2608880 |  | 2608880 |  | 3511200 |  | 3511200 | 758880 | 2043700 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21118 | AIL00002 | Catalina Blvd TS Interconnect Upgrade | 2025-10-01 | Install T/S Interconnect Systems / AIL00002 | Catalina Blvd TS Interconnect Upgrade / B21118 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Guillermo, Erick | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-09 |  | 2026-11-09 | 2024-02-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-01 |  | 2026-05-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1248152.93 |  | 1248152.93 |  | 1950000 |  | 1950000 | 585000 | 979700 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21102 | AIG00001 | Carmel Mtn @ Carmel Country Roundabout | 2025-10-01 | Median Installation / AIG00001 | Carmel Mtn @ Carmel Country Roundabout / B21102 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Leon, Heidi | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-23 |  | 2026-11-23 | 2023-10-02 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-14 |  | 2026-05-14 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 3222000 |  | 3222000 |  | 4432100 |  | 4432100 | 2502600 | 719400 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21070 | ABT00003 | Solar Implementation @ EMTS Lab Bldg | 2025-10-01 | Citywide Energy Improvements / ABT00003 | Solar Implementation @ EMTS Lab Bldg / B21070 | 2 | Buildings | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Hossan, Farhad | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-03 |  | 2026-11-03 | 2025-11-04 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-01 |  | 2026-05-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2930204 |  | 2930204 |  | 4200585.39 |  | 4200585.39 | 2007900 | 1320585.39 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21053 | ABI00001 | Otay WTP Raw Water PS Slope Restoration | 2025-10-01 | Water Treatment Plants / ABI00001 | Otay WTP Raw Water PS Slope Restoration / B21053 | 8 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_Dams | Van Martin, Debbie | Hawk, Gavin | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-08 |  | 2026-12-08 | 2024-11-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-29 |  | 2026-05-29 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 5657750 |  | 5657750 |  | 10323033 |  | 10323033 | 5553200 | 2319833 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20142 | AIG00001 | 6th Ave @ Juniper St Roundabout | 2025-10-01 | Median Installation / AIG00001 | 6th Ave @ Juniper St Roundabout / B20142 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Leon, Heidi | Charter Routing | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2027-04-12 |  | 2027-04-12 | 2023-01-03 | FY00 | Q3 | FY27 | Q4 |  |  | FY27 | Q4 |  | 2026-05-22 |  | 2026-05-22 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 1606300 |  | 1606300 |  | 3105000 |  | 3105000 | 1119100 | 1285000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20135 | AKB00003 | Valencia Park Improv 2 (W) | 2025-10-01 | Main Replacements / AKB00003 | Valencia Park Improv 2 (W) / B20135 | 4 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-11-23 |  | 2026-11-23 | 2024-08-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-14 |  | 2026-05-14 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 6829287 |  | 6829287 |  | 10513589 |  | 10513589 | 3857130 | 4357989 | 2.03 | 2.03 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20132 | AJA00001 | Valencia Park Improv 2 (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Valencia Park Improv 2 (S) / B20132 | 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-06 |  | 2026-10-06 | 2024-08-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-03-27 |  | 2026-03-27 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 8399464 |  | 8399464 |  | 12948409 |  | 12948409 | 5732190 | 3760909 | 0 | 0 | 2.4 | 2.4 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20123 | ABJ00001 | Gatewood Hills Pump Station | 2025-10-01 | Water Pump Station Restoration / ABJ00001 | Gatewood Hills Pump Station / B20123 | 5 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Adam, Julie | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-03 |  | 2026-12-03 | 2023-09-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-26 |  | 2026-05-26 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 3440000 |  | 3440000 |  | 7027935.75 |  | 7027935.75 | 2713600 | 2848935.75 | 0.16 | 0.16 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20054 | AGE00001 | West Sycamore Staging Area | 2025-10-01 | Resource Based Open Space Parks / AGE00001 | West Sycamore Staging Area / B20054 | 6 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Calleran, Mark | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-09 |  | 2026-12-09 | 2023-02-06 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-06-01 |  | 2026-06-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2100000 |  | 2100000 |  | 3935188 |  | 3935188 | 1282600 | 2162188 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20001 | ABO00001 | STORM WATER DIVERSION AT THE PLWTP | 2025-10-01 | Metro Treatment Plants / ABO00001 | STORM WATER DIVERSION AT THE PLWTP / B20001 | 2 | Sewer | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | Marshall, Lydia | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-09-22 |  | 2026-09-22 | 2022-05-02 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-05-05 |  | 2026-05-05 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 8756775 |  | 8756775 |  | 12922725 |  | 12922725 | 3100300 | 7714125 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B19212 | AGF00004 | Robb Field Gateway Path | 2025-10-01 | Mission Bay Improvements / AGF00004 | Robb Field Gateway Path / B19212 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Grotzinger, Juliana | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-08 |  | 2026-07-08 | 2023-09-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2025-12-24 |  | 2025-12-24 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2242915 |  | 2242915 |  | 3233046 |  | 3233046 | 393000 | 2440046 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B19089 | ACA00001 | Crown Point SD Replacement | 2025-10-01 | Flood Resilience Infrastructure / ACA00001 | Crown Point SD Replacement / B19089 | 1 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Chan, Chun Yu | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-15 |  | 2026-07-15 | 2022-06-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-01-02 |  | 2026-01-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 890625.55 |  | 890625.55 |  | 1292059.88 |  | 1292059.88 | 145500 | 1041759.88 | 0 | 0 | 0 | 0 |  | No | No | No | Yes | No | No | No | No | No | No | Yes
B18108 | AJA00001 | AC Water and Sewer Group 1054 (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | AC Water and Sewer Group 1054 (S) / B18108 | 9, 4 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-14 |  | 2026-07-14 | 2023-04-03 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2025-12-31 |  | 2025-12-31 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 6334023 |  | 6334023 |  | 7957162 |  | 7957162 | 2480600 | 7757350 | 0 | 0 | 1.7 | 1.7 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18107 | AKB00003 | AC Water & Sewer Group 1054 (W) | 2025-10-01 | Main Replacements / AKB00003 | AC Water & Sewer Group 1054 (W) / B18107 | 9, 4 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-14 |  | 2026-07-14 | 2023-04-03 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2025-12-31 |  | 2025-12-31 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 4835414 |  | 4835414 |  | 6065913 |  | 6065913 | 1982600 | 6735941 | 2.83 | 2.83 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18022 | AJA00001 | AC Water & Sewer Group 1033 (S) | 2025-10-01 | Sewer Main Replacements / AJA00001 | AC Water & Sewer Group 1033 (S) / B18022 | 3 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | Charter & Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-08-20 |  | 2026-08-20 | 2026-01-23 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-10 |  | 2026-02-10 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 13055354 |  | 13055354 |  | 17089974.34 |  | 17089974.34 | 11610241.02 | 2344968.23 | 0 | 0 | 2.43 | 2.43 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18021 | AKB00003 | AC Water & Sewer Group 1033 (W) | 2025-10-01 | Main Replacements / AKB00003 | AC Water & Sewer Group 1033 (W) / B18021 | 3 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | Charter & Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-08-20 |  | 2026-08-20 | 2026-01-23 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-10 |  | 2026-02-10 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 10611349 |  | 10611349 |  | 15831251.17 |  | 15831251.17 | 8389758.98 | 5176257.28 | 4.03 | 4.03 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18017 | AIK00001 | 73rd St-El Cajon Bl to Saranac-Sidewalk | 2025-10-01 | New Walkways / AIK00001 | 73rd St-El Cajon Bl to Saranac-Sidewalk / B18017 | 9 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Mansury, Nazie | Charter & Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-15 |  | 2026-07-15 | 2022-12-08 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-01-02 |  | 2026-01-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 345000 |  | 345000 |  | 850798 |  | 850798 | 345000 | 49048 | 0 | 0 | 0 | 0 |  | No | No | No | Yes | No | No | No | No | No | No | Yes
B18009 | AIG00001 | Crown Point Drive Roundabouts | 2025-10-01 | Median Installation / AIG00001 | Crown Point Drive Roundabouts / B18009 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Chan, Chun Yu | Charter & Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-15 |  | 2026-07-15 | 2024-07-12 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-01-02 |  | 2026-01-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 3230000 |  | 3230000 |  | 5320366.95 |  | 5320366.95 | 2130000 | 1657066.95 | 0 | 0 | 0 | 0 |  | No | No | No | Yes | No | No | No | No | No | No | Yes
B16119 | AIH00002 | Pacific Beach 1 SL Series Circuit Conv | 2025-10-01 | Street Light Circuit Upgrades / AIH00002 | Pacific Beach 1 SL Series Circuit Conv / B16119 | 1 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-08 |  | 2026-10-08 | 2019-10-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-01 |  | 2026-04-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 5100000 |  | 5100000 |  | 6600000 |  | 6600000 | 4067300 | 439000 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | Yes | No | No | Yes
B16115 | ACA00001 | Oak Park (SD) | 2025-10-01 | Flood Resilience Infrastructure / ACA00001 | Oak Park (SD) / B16115 | 9, 4 | Storm Water Drainage | Design Bid Build | Stormwater | Storm Water | SWD | Dastgheibi, Sara | Garcia Guzman, Julio | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-18 |  | 2026-12-18 | 2026-08-14 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-06-10 |  | 2026-06-10 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 14413145 |  | 14413145 |  | 21309554 |  | 21309554 | 14413145 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B16114 | ACC00001 | Oak Park Storm Dr Repl & Green Infr (GI) | 2025-10-01 | Stormwater Green Infrastructure / ACC00001 | Oak Park Storm Dr Repl & Green Infr (GI) / B16114 | 9, 4 | Storm Water Drainage | Design Bid Build | Stormwater | Storm Water | SWD | Dastgheibi, Sara | Garcia Guzman, Julio | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-12-02 |  | 2026-12-02 | 2026-08-14 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-22 |  | 2026-05-22 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2543496 |  | 2543496 |  | 3779266 |  | 3779266 | 2543496 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B15102 | ACC00001 | Green Infrastructure Group 1024 | 2025-10-01 | Stormwater Green Infrastructure / ACC00001 | Green Infrastructure Group 1024 / B15102 | 4 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Talamayan, Jonard | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-02 |  | 2026-07-02 | 2018-06-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2025-12-19 |  | 2025-12-19 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 1653146 |  | 1653146 |  | 4043254 |  | 4043254 | 1474100 | 2043254 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B15047 | AIL00004 | Division St & Osborn St Traffic Signal | 2025-10-01 | Traffic Signals - Citywide / AIL00004 | Division St & Osborn St Traffic Signal / B15047 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-07-08 |  | 2026-07-08 | 2020-06-12 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-01-06 |  | 2026-01-06 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 1220000 |  | 1220000 |  | 2142278 |  | 2142278 | 212200 | 1867278 | 0 | 0 | 0 | 0 |  | No | No | No | Yes | Yes | No | No | No | Yes | Yes | Yes
B00429 | AJA00001 | Buchanan Canyon Sewer B (UP) | 2025-10-01 | Sewer Main Replacements / AJA00001 | Buchanan Canyon Sewer B (UP) / B00429 | 3 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | On Schedule |  |  | FY27 |  |  | Added - Aug 1st |  |  |  |  | 2026-10-08 |  | 2026-10-08 | 2010-03-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-01-06 |  | 2026-01-06 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 20930286 |  | 20930286 |  | 24252420 |  | 24252420 | 2487492 | 20606024.57 | 0 | 0 | 0.79 | 0.79 |  | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes
B22095 | ABT00001 | Rancho Penasquitos Library Rehab | 2025-10-01 | City Facility Improvements / ABT00001 | Rancho Penasquitos Library Rehab / B22095 | 5 | Buildings | Design Bid Build | General Services | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Lozano, Yazmin | Charter Only | Removed | On Schedule |  |  | FY27 |  | Removed - Sept 1st | Added - Sept 1st |  |  |  |  | 2027-01-08 |  | 2027-01-08 | 2027-04-14 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 2026-06-30 |  | 2026-06-30 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 3100000 |  | 3100000 |  | 4696000 |  | 4696000 | 0 | 4127940 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S18000 | S18000 | Streamview Drive Improvements Phase 2 | 2025-10-01 | Streamview Drive Improvements Phase 2 / S18000 | Streamview Drive Improvements Phase 2 / S18000 | 9 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2026-05-19 | 2026-08-14 |  | 2026-08-14 | 2023-04-03 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-11-05 | 2026-02-04 |  | 2026-02-04 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 17917057 | 22324315 |  | 22324315 | 28154804 | 28154803 |  | 28154803 | 9469400 | 13592803 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S10008 | S10008 | El Monte Pipeline No. 2 | 2025-10-01 | El Monte Pipeline No 2 / S10008 | El Monte Pipeline No. 2 / S10008 | 7 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Bustamante, Ramesis W | Charter & Amendment | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2026-06-16 | 2026-09-04 |  | 2026-09-04 | 2022-08-01 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-12-04 | 2026-02-26 |  | 2026-02-26 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 74000000 | 74000000 |  | 74000000 | 92099966 | 92099966 |  | 92099966 | 15867067 | 67100015 | 0.07 | 0.07 | 0 | 0 |  | No | No | Yes | No | No | No | No | No | No | No | Yes
L24000.2 | TBD | Pump Station 2 Improvement and Modernization | 2025-10-01 | TBD | Pump Station 2 Improvement and Modernization / L24000.2 | 2 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Nezha, Shaza | No Project Charter or Amendment | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2026-06-29 | 2026-07-15 |  | 2026-07-15 | 2025-04-24 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-12-31 | 2026-01-16 |  | 2026-01-16 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 42000000 | 42000000 | 5300000 | 5300000 | 53809881 | 53809880.63 |  | 53809880.63 | 8829900 | 40073880.63 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24118 | TBD | Washington & Albatross HAWK | 2025-10-01 | TBD | Washington & Albatross HAWK / B24118 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Kim, Jinsil | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Sept 1st | On Published List |  |  |  | 2026-06-17 | 2026-08-31 |  | 2026-08-31 | 2026-03-02 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-12-18 | 2026-02-20 |  | 2026-02-20 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 706320 | 706320 |  | 706320 | 1355300 | 1355300 |  | 1355300 | 706320 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24096 | TBD | Rosecrans St & Byron St Shel Isl Signal | 2025-10-01 | TBD | Rosecrans St & Byron St Shel Isl Signal / B24096 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Kim, Jinsil | No Project Charter or Amendment | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Sept 1st | On Published List |  |  |  | 2026-05-01 | 2026-08-04 |  | 2026-08-04 | 2026-04-01 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-10-31 | 2026-01-23 |  | 2026-01-23 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 931600 | 931600 |  | 931600 | 1546600 | 2336600 |  | 2336600 | 931600 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23148 | AIL00001 | Otay Mesa Rd Pedestrian Improvements | 2025-10-01 | Traffic Calming / AIL00001 | Otay Mesa Rd Pedestrian Improvements / B23148 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Damnjanovic, Nenad | No Project Charter or Amendment | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Sept 1st | On Published List |  |  |  | 2026-05-12 | 2026-08-21 |  | 2026-08-21 | 2026-01-02 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-11-06 | 2026-02-11 |  | 2026-02-11 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 353925 | 353925 |  | 353925 | 743775 | 1008775 |  | 1008775 | 321750 | 82175 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B22101 | AIL00005 | Front & Washington TS Modification | 2025-10-01 | Traffic Signals - Modify & Modernize / AIL00005 | Front & Washington TS Modification / B22101 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Guillermo, Erick | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Sept 1st | On Published List |  |  |  | 2026-06-15 | 2026-09-02 |  | 2026-09-02 | 2024-02-14 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-12-03 | 2026-02-24 |  | 2026-02-24 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 931889 | 931888.62 |  | 931888.62 | 1530689 | 1530688.62 |  | 1530688.62 | 576200 | 499888.62 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B19095 | ACC00001 | Streamview Drive Green Infrastructure | 2025-10-01 | Stormwater Green Infrastructure / ACC00001 | Streamview Drive Green Infrastructure / B19095 | 9, 4 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter & Amendment | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2026-05-19 | 2026-08-14 |  | 2026-08-14 | 2023-03-30 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-11-05 | 2026-02-04 |  | 2026-02-04 | FY26 | Q2 | FY26 | Q3 |  |  | FY26 | Q3 | 19416048 | 19416048 |  | 19416048 | 24222655 | 24222655 |  | 24222655 | 6852000 | 13512655 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B18104 | AKB00003 | Alvarado TS Water Main Relocations | 2025-10-01 | Main Replacements / AKB00003 | Alvarado TS Water Main Relocations / B18104 | 7 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2026-01-09 | 2026-07-23 |  | 2026-07-23 | 2020-04-01 | FY26 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-07-01 | 2025-10-01 |  | 2025-10-01 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 9403562 | 9403562 |  | 9403562 | 11476867 | 11447866.65 |  | 11447866.65 | 1225100 | 9784366.65 | 1.38 | 1.38 | 0 | 0 |  | No | No | No | No | Yes | Yes | No | No | No | No | Yes
B17019 | AIL00004 | 31st St @ National Ave Traffic Signal | 2025-10-01 | Traffic Signals - Citywide / AIL00004 | 31st St @ National Ave Traffic Signal / B17019 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Amendment Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Sept 1st | On Published List |  |  |  | 2026-05-27 | 2026-08-27 |  | 2026-08-27 | 2022-02-10 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-09-26 | 2025-12-30 |  | 2025-12-30 | FY26 | Q1 | FY26 | Q2 |  |  | FY26 | Q2 | 1100000 | 1100000 |  | 1100000 | 1858400 | 1858388.94 |  | 1858388.94 | 379050 | 1233600 | 0 | 0 | 0 | 0 |  | No | Yes | No | No | No | No | No | No | No | No | Yes
B15097 | AID00001 | Block 8R UUP - CIP | 2025-10-01 | Utilities Undergrounding Program / AID00001 | Block 8R UUP - CIP / B15097 | 8 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | Charter Only | Removed | On Schedule |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List |  |  |  | 2026-05-26 | 2026-07-06 |  | 2026-07-06 | 2019-06-03 | FY26 | Q4 | FY27 | Q1 |  |  | FY27 | Q1 | 2025-11-12 | 2025-12-22 |  | 2025-12-22 | FY26 | Q2 | FY26 | Q2 |  |  | FY26 | Q2 | 1114000 | 1114000 |  | 1114000 | 1964000 | 1964000 |  | 1964000 | 4280026 | -4206626 | 0 | 0 | 0 | 0 |  | No | No | No | Yes | Yes | Yes | Yes | No | No | No | Yes
B21108 | ABL00001 | San Carlos Reservoir Replacement | 2025-10-01 | Standpipe & Reservoir Rehabilitations / ABL00001 | San Carlos Reservoir Replacement / B21108 | 7 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Adam, Julie | Charter Only | Removed | On Schedule |  |  | FY27 |  | Removed - Sept 1st | Added - Sept 1st |  |  |  |  | 2026-08-19 |  | 2026-08-19 | 2025-02-03 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-03-26 |  | 2026-03-26 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 13663122.11 |  | 13663122.11 |  | 17800000 |  | 17800000 | 6013700 | 8550000 | 0.09 | 0.09 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B20058 | AGF00007 | Ward Canyon Phase III | 2025-10-01 | Park Improvements / AGF00007 | Ward Canyon Phase III / B20058 | 9 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Marshall, Lydia | Charter Only | Removed | On Schedule |  |  | FY27 |  |  | Added - Oct 1st |  |  |  |  | 2026-12-08 |  | 2026-12-08 | 2024-02-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-29 |  | 2026-05-29 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 9695983.49 |  | 9695983.49 |  | 14407072.49 |  | 14407072.49 | 4996000 | 3800072.49 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B23147 | AIL00001 | Osler Street Traffic Calming | 2025-10-01 | Traffic Calming / AIL00001 | Osler Street Traffic Calming / B23147 | 7 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Rekani, Ronak | Charter Only | Removed | Removed |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List | FY27 |  | Removed - Oct 1st | 2026-05-18 | 2027-05-11 |  | 2027-05-11 | 2025-12-01 | FY26 | Q4 | FY27 | Q4 |  |  | FY27 | Q4 | 2025-11-14 | 2026-10-28 |  | 2026-10-28 | FY26 | Q2 | FY27 | Q2 |  |  | FY27 | Q2 | 346600 | 346600 |  | 346600 | 780220 | 1053130 |  | 1053130 | 346600 | 146270 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S15034 | S15034 | Junipero Serra Museum ADA Improvements | 2025-10-01 | Junipero Serra Museum ADA Improvements / S15034 | Junipero Serra Museum ADA Improvements / S15034 | 2 | Buildings | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | Fortier, Nicole | Charter & Amendment | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  |  |  | 2027-01-15 |  | 2027-01-15 | 2020-05-01 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 2026-07-08 |  | 2026-07-08 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 3469439 |  | 3469439 |  | 7089937.69 |  | 7089937.69 | 1369104 | 4822170.69 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | Yes | No | No | No | Yes
B25062 | TBD | Streetlights in University City | 2025-10-01 | TBD | Streetlights in University City / B25062 | 6 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Guillermo, Erick | No Project Charter or Amendment | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  |  |  | 2027-01-27 |  | 2027-01-27 | 2026-11-20 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 2026-07-17 |  | 2026-07-17 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 180600 |  | 180600 |  | 339700 |  | 339700 | 180600 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24119 | TBD | TS Mod at First Ave & Market St | 2025-10-01 | TBD | TS Mod at First Ave & Market St / B24119 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Zhang, Dayue | No Project Charter or Amendment | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  |  |  | 2027-02-08 |  | 2027-02-08 | 2026-05-28 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 2026-07-29 |  | 2026-07-29 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 371600 |  | 371600 |  | 650500 |  | 650500 | 371600 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B17033 | ACC00001 | Los Pen Lagoon Restoration Ph 1 | 2025-10-01 | Stormwater Green Infrastructure / ACC00001 | Los Pen Lagoon Restoration Ph 1 / B17033 | 1 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Damnjanovic, Nenad | Charter & Amendment | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  |  |  | 2027-03-23 |  | 2027-03-23 | 2023-06-02 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 2026-09-10 |  | 2026-09-10 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 79678886 |  | 79678886 |  | 121397161 |  | 121397161 | 22061000 | 83530361 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
S23011 | S23011 | Cypress Dr Cultural Corridor | 2025-10-01 | Cypress Dr Cultural Corridor / S23011 | Cypress Dr Cultural Corridor / S23011 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Krause, Shawn | Charter Only | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  | Removed - Sept 1st |  | 2027-06-01 |  | 2027-06-01 | 2024-01-12 | FY00 | Q3 | FY27 | Q4 |  |  | FY27 | Q4 |  | 2026-11-18 |  | 2026-11-18 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 3500000 |  | 3500000 |  | 4282192.11 |  | 4282192.11 | 0 | 3767192.11 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B15104 | ACC00001 | Green Infrastructure Group 1014 | 2025-10-01 | Stormwater Green Infrastructure / ACC00001 | Green Infrastructure Group 1014 / B15104 | 9 | Storm Water Drainage | Design Bid Build | Stormwater | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Cochinwala, Sabeen | Charter & Amendment | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  |  |  | 2027-04-23 |  | 2027-04-23 | 2018-04-20 | FY00 | Q3 | FY27 | Q4 |  |  | FY27 | Q4 |  | 2026-10-12 |  | 2026-10-12 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 1367574 |  | 1367574 |  | 3146301.8 |  | 3146301.8 | 2293396 | 669301.8 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | Yes | Yes | No | Yes
B00131 | AKB00003 | Water Group 525E | 2025-10-01 | Main Replacements / AKB00003 | Water Group 525E / B00131 | 8 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Abdelmottaleb, Noha | No Project Charter or Amendment | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  |  |  | 2027-01-13 |  | 2027-01-13 | 2025-07-01 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 2026-07-16 |  | 2026-07-16 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 4244000 |  | 4244000 |  | 7757423.76 |  | 7757423.76 | 3819600 | 1599423.76 | 1.15 | 1.15 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B00032 | AKB00003 | Water Group 525C | 2025-10-01 | Main Replacements / AKB00003 | Water Group 525C / B00032 | 8 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Abdelmottaleb, Noha | Charter Only | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  |  |  | 2027-01-13 |  | 2027-01-13 | 2024-03-27 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 2026-07-16 |  | 2026-07-16 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 3632000 |  | 3632000 |  | 6609850.67 |  | 6609850.67 | 3268800 | 1135850.67 | 0.99 | 0.99 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B24109 | TBD | Saturn Blvd Sidewalk Installation | 2025-10-01 | TBD | Saturn Blvd Sidewalk Installation / B24109 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Damnjanovic, Nenad | Charter Only | Removed | Removed |  | On Published List | FY27 |  | Removed - Oct 1st | On Published List | FY27 |  | Removed - Oct 1st | 2026-05-14 | 2027-01-29 |  | 2027-01-29 | 2025-05-06 | FY26 | Q4 | FY27 | Q3 |  |  | FY27 | Q3 | 2026-02-04 | 2026-07-21 |  | 2026-07-21 | FY26 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 | 850000 | 850000 |  | 850000 | 1500000 | 1500000 |  | 1500000 | 1010700 | 0 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B17030 | ACA00001 | Bay Terraces & Skyline South SD Repl | 2025-10-01 | Flood Resilience Infrastructure / ACA00001 | Bay Terraces & Skyline South SD Repl / B17030 | 4 | Storm Water Drainage | Design Bid Build | Stormwater | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Huang, Tina | No Project Charter or Amendment | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  | Removed - Sept 1st |  | 2027-06-01 |  | 2027-06-01 | 2027-06-01 | FY00 | Q3 | FY27 | Q4 |  |  | FY27 | Q4 |  | 2026-12-01 |  | 2026-12-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 7732570 |  | 7732570 |  | 14000000 |  | 14000000 | 7351470 | 1991100 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B15103 | ACC00001 | Green Infrastructure Group 1027 | 2025-10-01 | Stormwater Green Infrastructure / ACC00001 | Green Infrastructure Group 1027 / B15103 | 3 | Storm Water Drainage | Design Bid Build | Stormwater | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | Removed |  | Added - Aug 1st | FY28 |  |  | Added - Sept 1st | FY27 |  |  |  | 2027-09-20 |  | 2027-09-20 | 2018-06-01 | FY00 | Q3 | FY28 | Q1 |  |  | FY28 | Q1 |  | 2027-04-01 |  | 2027-04-01 | FY00 | Q3 | FY27 | Q4 |  |  | FY27 | Q4 |  | 1600000 |  | 1600000 |  | 3120000 |  | 3120000 | 1491000 | 1120000 | 0 | 0 | 0 | 0 |  | No | No | No | Yes | No | Yes | Yes | No | No | No | Yes
B24005 | TBD | El Capitan Dam Spillway Slope Stability | 2025-10-01 | TBD | El Capitan Dam Spillway Slope Stability / B24005 | Project outside of City limits | Water | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | McMullen, Sara | No Project Charter or Amendment | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  |  |  | 2027-07-29 |  | 2027-07-29 | 2026-03-10 | FY00 | Q3 | FY28 | Q1 |  |  | FY28 | Q1 |  | 2027-01-19 |  | 2027-01-19 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 1740000 |  | 1740000 |  | 3704193 |  | 3704193 | 2034000 | 314193 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
B21067 | S22013 | Dams & Reservoirs Security Improvements | 2025-10-01 | Dams & Reservoirs Security Improvements / S22013 | Dams & Reservoirs Security Improvements / B21067 | 8, 7, 5 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Stohr, John | Charter Only | Removed | Removed |  |  | FY27 |  |  | Added - Aug 1st | FY27 |  | Removed - Sept 1st |  | 2027-07-19 |  | 2027-07-19 | 2023-05-01 | FY00 | Q3 | FY28 | Q1 |  |  | FY28 | Q1 |  | 2027-01-06 |  | 2027-01-06 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 15300000 |  | 15300000 |  | 27300000 |  | 27300000 | 8440400 | 15352500 | 0 | 0 | 0 | 0 |  | No | No | No | No | No | No | No | No | No | No | Yes
Note on P9: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Awarded in FY24
Note on A21: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm LNTP date. Advertise date is after LNTP per Planetbids and P6?
Note on P27: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Awarded in FY24
Note on A77: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm this project has not been LNTP'd previously. Mark as Awarded for now.
Note on P101: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No record of LNTP in FY24 as of today

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only