## Slide 1: Fiscal Year 2025 Annual Report & Annual Review of Infrastructure Financing Plan
Otay Mesa Enhanced Infrastructure Financing District
February 26, 2026
Public Financing Authority Board Meeting Item #4

## Slide 2: Otay Mesa - EIFD
AB 116 Amendment to EIFD Legislation
Fiscal Year Annual Report
    Adopt annual report on or before June 30th after holding a public hearing
    Draft report shall be made available to the public 30 days before hearing
    Written notice shall be mailed to every landowner and occupant in the District

## Slide 3: Otay Mesa - EIFD
Report Requirements
  Description of the projects undertaken in the fiscal year
  A chart comparing actual revenues and expenses
  Amount of tax increment revenues received
  Assessment of the status of the projects in the District
  Amount of revenues expended to assist private businesses
Fiscal Year 2025 Annual Report

## Slide 4: Otay Mesa - EIFD
Project | Budgeted EIFD Funds Disbursed to Date | Expended To Date
La Media Road Improvements (S-15018)1 | $9,304,139 | $6,144,395
Hidden Trails Neighborhood Park (S-00995) 1 | $2,000,000 | $0
Dennery Ranch Neighborhood Park (RD22001) 1 | $6,462,601 | $0
Fire Station #49 (S-00784) | $1,500,000 | $0
Siempre Viva Road Improvements (P-19006) | $550,000 | $52,073
Airway Road Improvements (P-19007) | $450,000 | $199,155
1. Description of Projects Undertaken in Fiscal Year 2025
1La Media Road Improvements, Hidden Trails Neighborhood Park, and Dennery Ranch Neighborhood Park received funding prior to Fiscal Year 2025.

## Slide 5: Otay Mesa - EIFD
Fiscal Year 2025 Budget Vs Actuals |  | 
Revenues | Budget | Actual
Property Tax Revenue (including In-lieu of VLF revenue) | $7,022,373 | $6,537,057
Expenditures |  | 
CIP | $7,718,165 | $251,228
Administrative Costs | $159,810 | $147,465
2. Comparison of Actual Revenues and Expenditures

## Slide 6: Otay Mesa - EIFD
$6,537,057 of TI revenues were received including Property Tax In-lieu of vehicle licensing fees
3. Amount of Tax Increment (TI) Revenues Received

## Slide 7: Otay Mesa - EIFD
La Media Road Improvements (S-15018)
  Scope: Upgrade La Media Road between SR-905 and Siempre Viva Road to a six-lane arterial and improve drainage at Airway Road
  Status: Property acquisition completed (FY 2022), construction completed (FY 2025), wetland and vernal pool monitoring ongoing for 5 years post-construction
  Next Steps: Continued environmental monitoring.
Hidden Trails Neighborhood Park: (S-00995)
Scope: Develop a 4-acre neighborhood park with turf, play areas, picnic spots, comfort station, and public art
Status: Land acquisition completed (FY 2012), design completed (FY 2025), construction began October 2025; site clearing and grading underway
  Next Steps: Continue construction activities including drainage and retaining walls
4. CIP Project Status

## Slide 8: Otay Mesa - EIFD
Dennery Ranch Neighborhood Park (RD 22001)
  Scope: Build a 9-acre park with sports fields, play areas, trails, and staging area in Otay Mesa
  Status: Design phase ongoing; stormwater redesign required and Substantial Conformance Review completed; updated cost and schedule pending
  Next Steps: Finalize design and programming; construction anticipated FY 2027, conveyance of completed park in FY 2028
Fire Station #49 (S-00784)
  Scope: Construct a 13,000 sq. ft. double house fire station with 3 apparatus bays and training facilities
  Status: Land acquisition completed (FY 2022), scoping and surveys completed (FY 2025), CEQA addendum in progress; clearance anticipated in FY 2026 which will facilitate Design-Build solicitation in FY 2027
  Next Steps: Design-Build solicitation anticipated for FY 2027 (may defer if additional CEQA steps required)
4. CIP Project Status

## Slide 9: Otay Mesa - EIFD
Siempre Viva Road Improvements (P-19006)
  Scope: Upgrade Siempre Viva Road to a six-lane arterial; including unpaved segment requiring environmental considerations
  Status: Feasibility study underway; completion is anticipated in June 2026
  Next Steps: Submit completed feasibility study to Transportation Department in FY 2027
Airway Road Improvements (P-19007)
  Scope: Upgrade Airway Road to a four-lane major corridor serving industrial truck traffic
  Status: Feasibility completed in December 2025; submitted to Transportation Department in early 2026
  Next Steps: Await departmental review for next planning phase
4. CIP Project Status

## Slide 10: Otay Mesa - EIFD
  In FY 2025, no revenues were expended to assist private businesses
5. Amount of Revenues Expended to Assist Private Businesses

## Slide 11: Otay Mesa - EIFD
  AB116 Requirements
    Pursuant to Government Code section 53398.66(j)(1), the Authority must review the District’s IFP, at least annually, and make any amendments that are necessary and appropriate
    Staff has no recommended amendments to the IFP for the Authority’s consideration
Annual Review of the District’s Infrastructure Financing Plan (IFP)

## Slide 12: Otay Mesa - EIFD
  Approve, via resolution, the District’s FY 2025 Annual Report and confirm the annual review of the Districts Infrastructure Financing Plan
Requested Action