## Forecast of Projects
Line Number | Project Name | Project Name (Text) | Project Number | Asset Managing Department | Contract Type | Estimated Total Contract Cost ($) | Estimated Total Project Cost ($) | Fiscal Year Advertising | Quarter Advertising | Fiscal Year Awarding | Quarter Awarding
1 | Palm Avenue Interstate 805 Interchange | Palm Avenue Interstate 805 Interchange | S00869 | Transportation | Agency/ Developer Managed Built - City Paid | 52430633.53 | 31500000 | FY25 | Q4 | FY26 | Q3
2 | Colina Del Sol Improv 1 (S) | Colina Del Sol Improv 1 (S) | B20008 | Public Utilities | Design Bid Build | 15617179 | 10462084 | FY26 | Q3 | FY26 | Q4
3 | Ocean Beach Branch Library | Ocean Beach Branch Library | S20015 | Library | Design Build | 12751489 | 8195649 | FY26 | Q3 | FY26 | Q4
4 | HIDDEN TRAILS NEIGHBORHOOD PARK | HIDDEN TRAILS NEIGHBORHOOD PARK | S00995 | Parks & Recreation | Design Bid Build | 12577229.6 | 8685000 | FY25 | Q4 | FY26 | Q1
5 | Pressure Reducing Stations Upgrades Phs1 | Pressure Reducing Stations Upgrades Phs1 | B16017 | Public Utilities | Design Bid Build | 12305000 | 8600000 | FY26 | Q3 | FY26 | Q4
6 | Air & Space Museum Roof Replacement | Air & Space Museum Roof Replacement | B20116 | General Services | Design Bid Build | 12198991 | 9075000 | FY25 | Q4 | FY26 | Q4
7 | Sewer & AC Water Group 1055 (S) | Sewer & AC Water Group 1055 (S) | B18112 | Public Utilities | Design Bid Build | 11881393.04 | 9000000 | FY26 | Q3 | FY26 | Q4
8 | Colina Del Sol Improv 1 (W) | Colina Del Sol Improv 1 (W) | B20010 | Public Utilities | Design Bid Build | 11583516 | 7652760 | FY26 | Q3 | FY26 | Q4
9 | Via De La Valle Pipeline | Via De La Valle Pipeline | B22015 | Public Utilities | Design Build | 10023393 | 6788293 | FY26 | Q2 | FY26 | Q3
10 | Chollas Creek Improv 1 (W) | Chollas Creek Improv 1 (W) | B20039 | Public Utilities | Job Order Contract | 9818519 | 7297091 | FY26 | Q2 | FY26 | Q3
11 | AC Overlay Group 2507 | AC Overlay Group 2507 | B25007 | Transportation | Design Bid Build | 9550000 | 7955000 | FY26 | Q1 | FY26 | Q3
12 | Sewer & AC Water Group 1055 (W) | Sewer & AC Water Group 1055 (W) | B18115 | Public Utilities | Design Bid Build | 8244046.26 | 5800000 | FY26 | Q3 | FY26 | Q4
13 | Dr. Bertha O. Pendleton Park Improvement | Dr. Bertha O. Pendleton Park Improvement | B22047 | Parks & Recreation | Design Bid Build | 7852573 | 5451882 | FY25 | Q3 | FY26 | Q1
14 | La Jolla Improv 3 (W) | La Jolla Improv 3 (W) | B20023 | Public Utilities | Design Bid Build | 7635820 | 5000000 | FY26 | Q3 | FY26 | Q4
15 | Accelerated Sewer Referral Group 847 | Accelerated Sewer Referral Group 847 | B18183 | Public Utilities | Design Bid Build | 6855331.32 | 3687264 | FY25 | Q3 | FY26 | Q1
16 | Jamacha Lomita Storm Drain | Jamacha Lomita Storm Drain | B16094 | Stormwater | Design Bid Build | 6839000 | 4227242.25 | FY25 | Q3 | FY26 | Q1
17 | AC Overlay Group 2514 | AC Overlay Group 2514 | B25052 | Transportation | Design Bid Build | 6802286.78 | 4799999 | FY26 | Q2 | FY26 | Q3
18 | City Hts Library Performance Annex Imp | City Hts Library Performance Annex Imp | S23013 | Library | Design Build | 6514956 | 5417724 | FY25 | Q3 | FY26 | Q1
19 | Balboa Park Golf Course Improvements | Balboa Park Golf Course Improvements | B23071 | Parks & Recreation | Design Build | 6400000 | 4284863 | FY25 | Q4 | FY26 | Q2
20 | Solana Highlands NP-Comfort Station | Solana Highlands NP-Comfort Station | S16032 | Parks & Recreation | Design Bid Build | 6133600 | 4461200 | FY26 | Q2 | FY26 | Q3
21 | 4918/4980 Canterbury Dr SD Emergency | 4918/4980 Canterbury Dr SD Emergency | B25096 | Stormwater | Emergency (As-needed) | 6000000 | 4750000 | FY26 | Q1 | FY26 | Q1
22 | Rancho Bernardo CP Dog Park | Rancho Bernardo CP Dog Park | L20000.2 | Parks & Recreation | Design Bid Build | 5700000 | 3411200 | FY25 | Q4 | FY26 | Q2
23 | SV Dam Low Level Outlet Improvements | SV Dam Low Level Outlet Improvements | B22002 | Public Utilities | Design Bid Build | 5366554.94 | 2500000 | FY26 | Q2 | FY26 | Q4
24 | PW Genesee Avenue Median Improv | PW Genesee Avenue Median Improv | B22085 | Public Utilities | Design Bid Build | 5245834.96 | 3800000 | FY25 | Q3 | FY26 | Q2
25 | Chollas Creek Improv 1 (S) | Chollas Creek Improv 1 (S) | B20038 | Public Utilities | Job Order Contract | 5108359.72 | 3478000 | FY26 | Q2 | FY26 | Q3
26 | Office Trailers Replacement | Office Trailers Replacement | L17000.7 | Environmental Services | Design Build | 5000000 | 4500000 | FY25 | Q3 | FY26 | Q1
27 | AC Overlay Group 2511 | AC Overlay Group 2511 | B25049 | Transportation | Job Order Contract | 4348150 | 3622000 | FY25 | Q4 | FY26 | Q1
28 | Ofc. Jeremy Henwood Park Play Area Repl | Ofc. Jeremy Henwood Park Play Area Repl | S25004 | Parks & Recreation | Design Build | 4250000 | 3069000 | FY26 | Q3 | FY26 | Q4
29 | Chollas Creek Oak Park Trail | Chollas Creek Oak Park Trail | S20012 | Parks & Recreation | Design Build | 4111500 | 2380000 | FY00 | Q3 | FY26 | Q4
30 | Rose Marie Starns Parking Lot Imprvemts | Rose Marie Starns Parking Lot Imprvemts | B19163 | Parks & Recreation | Job Order Contract | 4044832 | 2000473.9 | FY26 | Q1 | FY26 | Q1
31 | 1687 Torrance St SD Emergency | 1687 Torrance St SD Emergency | B26050 | Stormwater | Emergency (As-needed) | 4000000 | 3500000 | FY26 | Q2 | FY26 | Q2
32 | AC Overlay Group 2508 | AC Overlay Group 2508 | B25046 | Transportation | Job Order Contract | 3800000 | 3014915 | FY26 | Q2 | FY26 | Q3
33 | West Miramar Central Basin Expansion | West Miramar Central Basin Expansion | B23000 | Environmental Services | Design Bid Build | 3750000 | 2900000 | FY26 | Q2 | FY26 | Q3
34 | NCWRP - Chiller Replacement | NCWRP - Chiller Replacement | B20148 | Public Utilities | Design Bid Build | 3646276 | 2575000 | FY26 | Q1 | FY26 | Q3
35 | Scripps Miramar Ranch Library Roof Repl | Scripps Miramar Ranch Library Roof Repl | B22139 | General Services | Job Order Contract | 3267971 | 1925816.59 | FY25 | Q2 | FY26 | Q2
36 | Chicano Park Improvements Phase III | Chicano Park Improvements Phase III | B20060 | Parks & Recreation | Job Order Contract | 3224321 | 2402065 | FY26 | Q4 | FY26 | Q4
37 | AC Overlay Group 2509 | AC Overlay Group 2509 | B25047 | Transportation | Job Order Contract | 3211845.91 | 2411845.91 | FY26 | Q2 | FY26 | Q3
38 | Sidewalk Replacement Group 2530 - U & MM | Sidewalk Replacement Group 2530 - U & MM | B26003 | Transportation | Design Bid Build | 3100000 | 1700000 | FY25 | Q3 | FY26 | Q4
39 | Police HQ Security Fencing | Police HQ Security Fencing | B22080 | General Services | Design Bid Build | 3014349.76 | 1793081.75 | FY25 | Q4 | FY26 | Q1
40 | South Chollas Landfill Gas Collection System Improvements | South Chollas Landfill Gas Collection System Improvements | B22031 | Environmental Services | Design Bid Build | 3000000 | 2000000 | FY26 | Q3 | FY26 | Q3
41 | Miramar WTP Caustic Pumping System | Miramar WTP Caustic Pumping System | B23014 | Public Utilities | Design Bid Build | 2853250.41 | 1317300 | FY25 | Q4 | FY26 | Q2
42 | Center City Traffic Signals-15th Street | Center City Traffic Signals-15th Street | B22111 | Transportation | Design Bid Build | 2709981.36 | 1700000 | FY25 | Q3 | FY26 | Q1
43 | Storm Drain Group 763 | Storm Drain Group 763 | B17143 | Stormwater | Design Bid Build | 2679869 | 817305.25 | FY25 | Q3 | FY26 | Q1
44 | Carmel Mountain TS Emergency | Carmel Mountain TS Emergency | B26039 | Transportation | Sole Source Emergency | 2500000 | 2200000 | FY26 | Q1 | FY26 | Q1
45 | Pump Station 64 Valve Replacement | Pump Station 64 Valve Replacement | B26000 | Public Utilities | Design Bid Build | 2500000 | 1400000 | FY26 | Q2 | FY26 | Q3
46 | Narragansett Avenue Access | Narragansett Avenue Access | B18026 | Parks & Recreation | Job Order Contract | 2205771.98 | 598314 | FY25 | Q4 | FY26 | Q3
47 | Signal Mods in Barrio Logan | Signal Mods in Barrio Logan | B13010 | Transportation | Job Order Contract | 2151900.63 | 1287091.83 | FY25 | Q2 | FY26 | Q1
48 | Willie Henderson Lighting Upgrades | Willie Henderson Lighting Upgrades | B23011 | Parks & Recreation | Design Bid Build | 2132550 | 1300000 | FY25 | Q3 | FY26 | Q1
49 | Miramar Valve No2 Replacement | Miramar Valve No2 Replacement | B23075 | Public Utilities | Job Order Contract | 2067521 | 1200000 | FY26 | Q4 | FY26 | Q4
50 | 31st St @ National Ave Traffic Signal | 31st St @ National Ave Traffic Signal | B17019 | Transportation | Design Bid Build | 2000000 | 1100000 | FY26 | Q2 | FY26 | Q4
51 | Block 7T - Allied Gardens SL UU65 | Block 7T - Allied Gardens SL UU65 | B18129 | Transportation | Job Order Contract | 1759000 | 1235700 | FY26 | Q3 | FY26 | Q4
52 | Old Salt Pool Access Stairs | Old Salt Pool Access Stairs | B22012 | Parks & Recreation | Job Order Contract | 1707193.77 | 853807.73 | FY25 | Q4 | FY26 | Q3
53 | Terminal Parking Lot East Rehabilitation | Terminal Parking Lot East Rehabilitation | B22157 | Economic Development | Job Order Contract | 1536487 | 885967 | FY26 | Q2 | FY26 | Q3
54 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | B18140 | Transportation | Design Bid Build | 1510285.56 | 820733.56 | FY26 | Q1 | FY26 | Q2
55 | Mission Blvd South Loring Overlay | Mission Blvd South Loring Overlay | B24135 | Transportation | Design Bid Build | 1420779.5 | 930072.5 | FY26 | Q1 | FY26 | Q2
56 | Downtown Audibles 04th & E S29 | Downtown Audibles 04th & E S29 | B18162 | Transportation | Design Bid Build | 1250000 | 485000 | FY25 | Q3 | FY26 | Q1
57 | Black Mountain Reservoir Spillway Stairs | Black Mountain Reservoir Spillway Stairs | B23110 | Public Utilities | Design Bid Build | 1200000.36 | 639666.02 | FY25 | Q4 | FY26 | Q3
58 | Hard Court Improvements | Hard Court Improvements | B22045 | Parks & Recreation | Job Order Contract | 1200000 | 810000 | FY25 | Q4 | FY26 | Q1
59 | Installation of City Owned SL 2201 (NSG) | Installation of City Owned SL 2201 (NSG) | B22149 | Transportation | Job Order Contract | 1157000 | 800000 | FY25 | Q3 | FY26 | Q1
60 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 | B18148 | Transportation | Design Bid Build | 975303.1 | 458379 | FY26 | Q1 | FY26 | Q2
61 | AC Overlay Group 2511A | AC Overlay Group 2511A | B25067 | Transportation | Design Bid Build | 945000 | 632643 | FY25 | Q4 | FY26 | Q1
62 | AC Overlay Group 2511C | AC Overlay Group 2511C | B25069 | Transportation | Design Bid Build | 815000 | 608199.5 | FY25 | Q4 | FY26 | Q2
63 | Mt Hope Improvements 2 Federal Blvd SWR | Mt Hope Improvements 2 Federal Blvd SWR | B26031 | Public Utilities | Job Order Contract | 750000 | 595000 | FY26 | Q3 | FY26 | Q3
64 | Paradise Hills Community Park Trail | Paradise Hills Community Park Trail | S24013 | Parks & Recreation | Minor Contract | 750000 | 700000 | FY26 | Q2 | FY26 | Q3
65 | Roswell Street Overlay | Roswell Street Overlay | B24137 | Transportation | Job Order Contract | 710000 | 400000 | FY26 | Q1 | FY26 | Q3
66 | AC Overlay Group 2511B | AC Overlay Group 2511B | B25068 | Transportation | Design Bid Build | 622808.2 | 687808.2 | FY25 | Q4 | FY26 | Q2
67 | AC Overlay Group 2520 UUP | AC Overlay Group 2520 UUP | B25083 | Transportation | Design Bid Build | 523329 | 523329 | FY26 | Q1 | FY26 | Q2
68 | Northern Garage Dorm Repl | Northern Garage Dorm Repl | B24015 | General Services | Minor Contract | 362000 | 50000 | FY25 | Q4 | FY26 | Q1
69 | Ruffin Canyon Trail | Ruffin Canyon Trail | B20104 | Parks & Recreation | Minor Contract | 311981 | 90000 | FY25 | Q4 | FY26 | Q1
70 | MTRP Trail System Management | MTRP Trail System Management | S23010 | Parks & Recreation | Minor Contract | 200000 | 90000 | FY25 | Q4 | FY26 | Q1
71 | Jamacha Lomita Storm Drain (P) | Jamacha Lomita Storm Drain (P) | B26015 | Transportation | Design Bid Build | 197881.1 | 197881.1 | FY25 | Q3 | FY26 | Q1
|  |  | 71 CIP Projects |  |  | 360909844.79 | 241488647.09

## Summary Table
Summary by Asset - Managing Departments
Asset - Managing Department | Estimated Construction Contract Award | Estimated Total Project Cost
Library | 19266445 | 13613373
Parks & Recreation | 62801552.35 | 40587805.63
Public Utilities | 122701995.01 | 81792458.02
Environmental Services | 11750000 | 9400000
Stormwater | 19818869 | 13522734.5
Transportation | 104491184.67 | 69070597.6
General Services | 18843311.76 | 12843898.34
Economic Development | 1536487 | 885967
FY 2025 Total | 361209844.79 | 241716834.09

## Master-Jan 1st (hidden)
WBS | Parent | Project Name | Data Date | Annual Allocation Project | Annual Allocation Subproject | Council Districts | Asset Type Group (PC) | Construction Contract Type | Asset Managing Department | Responsible Division | Responsible Manager | Design Section Head | Project Manager | Charter and/or Charter Amendment | Status of Award | Status of Advertise | Advertising/Awarding | Added to Current FY Award List | Removed from Current FY Award List | Reason for Removal (Award) | Month Removed (Award) | Added to Current FY Advertise List | Removed from Current FY Advertise List | Reason for Removal (Advertise) | Month Removed (Advertise) | ECP LNTP (Published) | LNTP (6010) | ECP LNTP (Override) | LNTP | LNTP BL (BL 6010) | Fiscal Year Awarding (Published) | Quarter Awarding (Published) | Fiscal Year Awarding (Actual/ Projection) P6 | Quarter Awarding (Actual/ Projection) P6 | Fiscal Year Awarding (Actual/ Projection) Overide | Quarter Awarding (Actual/ Projection) Overide | Fiscal Year Awarding (Actual/ Projection) | Quarter Awarding (Actual/ Projection) | ECP Contract Bid (Published) | Contract Bid - Start (5010) | Contract Bid - Start (Override) | Contract Bid - Start | Fiscal Year Advertising (Published) | Quarter Advertising (Published) | Fiscal Year Advertising (Actual/Projection) P6 | Quarter Advertising (Actual/Projection) P6 | Fiscal Year Advertising (Actual/Projection) Overide | Quarter Advertising (Actual/Projection) Overide | Fiscal Year Advertising (Actual/Projection) | Quarter Advertising (Actual/Projection) | Total Construction Cost (Published) | Est Construction Cost (730) | Total Construction Cost (Override) | Total Construction Cost | Total Project Cost (Published) | Planned Total Cost | Total Project Cost (Override) | Total Project Cost | Est Construction Cost (730) (Goal) | Planned Total Cost (Goal) | Total Water Mileage (Published) | Total Water Mileage | Total Sewer Mileage (Published) | Total Sewer Mileage | Current FY Published List | FY24 Published List | FY23 Published List | FY22 Published List | FY21 Published List | FY20 Published List | FY19 Published List | FY18 Published List | FY17 Published List | FY16 Published List | P6 Exists | Comments
B24076 | TBD | AC Water & Sewer Group Job 1023B (P) | 2025-01-01 | TBD | AC Water & Sewer Group Job 1023B (P) / B24076 | 3 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Abdelmottaleb, Noha | No Project Charter or Amendment | Removed | Removed |  | Added - Aug 1st | FY23 |  |  |  | FY23 |  | Removed - Aug 1st |  | 2023-03-02 |  | 2023-03-02 | 2023-03-02 | FY00 | Q3 | FY23 | Q3 |  |  | FY23 | Q3 |  | 2022-10-27 |  | 2022-10-27 | FY00 | Q3 | FY23 | Q2 |  |  | FY23 | Q2 |  | 98323.06 |  | 98323.06 |  | 98323.06 |  | 98323.06 | 33323.06 | 65000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S15020 | S15020 | Tecolote Canyon Trunk Sewer Improvement | 2025-01-01 | Tecolote Canyon Trunk Sewer Improvement / S15020 | Tecolote Canyon Trunk Sewer Improvement / S15020 | 7, 2 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | Charter Only | Removed | Removed |  | On Published List | FY24 |  | Removed - Aug 1st |  | FY24 |  | Removed - Aug 1st | 2024-07-01 | 2024-06-27 |  | 2024-06-27 | 2018-08-01 | FY25 | Q1 | FY24 | Q4 |  |  | FY24 | Q4 | 2023-12-26 | 2023-12-26 |  | 2023-12-26 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 44495068.83 | 44757802.83 |  | 44757802.83 | 55137802.74 | 55400536.9 |  | 55400536.9 | 12847000 | 38007802.74 | 0 | 0 | 4.7 | 4.7 | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | Yes
B15203 | AKB00003 | Tecolote Cyn GC Water Conn | 2025-01-01 | Main Replacements / AKB00003 | Tecolote Cyn GC Water Conn / B15203 | 7, 2 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | Charter Only | Removed | Removed |  | On Published List | FY24 |  | Removed - Aug 1st |  | FY24 |  | Removed - Aug 1st | 2024-07-01 | 2024-06-27 |  | 2024-06-27 | 2018-08-01 | FY25 | Q1 | FY24 | Q4 |  |  | FY24 | Q4 | 2023-12-26 | 2023-12-26 |  | 2023-12-26 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 1440444.43 | 1440444.43 |  | 1440444.43 | 2047698.26 | 2047698.26 |  | 2047698.26 | 208000 | 1769698.26 | 0.13 | 0.13 | 0 | 0 | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | Yes
B22145 | AID00005 | Undergrounding Resurfacing (SS) | 2025-01-01 | Resurfacing of City Streets / AID00005 | Undergrounding Resurfacing (SS) / B22145 | Geo-Mapping is in progress | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | No Project Charter or Amendment | Removed | Removed |  | On Published List | FY24 |  | Removed - Aug 1st |  | FY24 |  | Removed - Aug 1st | 2024-07-23 | 2024-05-13 |  | 2024-05-13 | 2023-07-14 | FY25 | Q1 | FY24 | Q4 |  |  | FY24 | Q4 | 2024-07-01 | 2023-10-30 |  | 2023-10-30 | FY25 | Q1 | FY24 | Q2 |  |  | FY24 | Q2 | 2147201.17 | 2132010.08 |  | 2132010.08 | 2147201.17 | 2144916.65 |  | 2144916.65 | 1835367.67 | 309548.98 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B19188 | AGF00007 | Marcy Neighborhood Park Improvements | 2025-01-01 | Park Improvements / AGF00007 | Marcy Neighborhood Park Improvements / B19188 | 6 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Kieser-Hua, Lin | Charter Only | Removed | Removed |  | Added - Sep 1st | FY24 |  |  |  | FY24 |  | Removed - Sept 1st |  | 2024-06-12 |  | 2024-06-12 | 2023-08-01 | FY00 | Q3 | FY24 | Q4 |  |  | FY24 | Q4 |  | 2024-01-22 |  | 2024-01-22 | FY00 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 |  | 2913103.65 |  | 2913103.65 |  | 5120224.65 |  | 5120224.65 | 1417000 | 2368224.65 | 0 | 0 | 0 | 0 | No | Yes | No | No | No | No | No | No | No | No | Yes
B25012 | TBD | Bay Ho Improv 2 (P) | 2025-01-01 | TBD | Bay Ho Improv 2 (P) / B25012 | 2 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Valadez, Roberto | No Project Charter or Amendment | Removed | Removed |  | Added - Sep 1st | FY24 |  |  |  | FY24 |  | Removed - Sept 1st |  | 2024-05-31 |  | 2024-05-31 | 2024-05-31 | FY00 | Q3 | FY24 | Q4 |  |  | FY24 | Q4 |  | 2024-01-16 |  | 2024-01-16 | FY00 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 |  | 1099992 |  | 1099992 |  | 1099992 |  | 1099992 | 1099992 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B15014 | AIL00004 | 31st St & Market St School Traffic Sgnal | 2025-01-01 | Traffic Signals - Citywide / AIL00004 | 31st St & Market St School Traffic Sgnal / B15014 | 9 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Guillermo, Erick | Charter & Amendment | Removed | On Schedule |  |  | FY24 |  |  | Added - Jan 1st |  |  |  |  | 2024-06-05 |  | 2024-06-05 | 2022-02-10 | FY00 | Q3 | FY24 | Q4 |  |  | FY24 | Q4 |  | 2025-01-02 |  | 2025-01-02 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 819000 |  | 819000 |  | 1597100 |  | 1597100 | 294000 | 1220100 | 0 | 0 | 0 | 0 | No | Yes | Yes | No | No | No | No | Yes | Yes | Yes | Yes
B19144 | AIA00001 | Downtown Complete St Impl Phase 3A1 | 2025-01-01 | Minor Bike Facilities / AIA00001 | Downtown Complete St Impl Phase 3A1 / B19144 | 3 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Kim, Jinsil | No Project Charter or Amendment | Awarded | Removed | [5 empty] | Added - Aug 1st | FY23 |  | Removed - Jan 1st |  | 2022-10-24 | 2024-12-03 | 2024-12-03 | 2021-02-01 | FY00 | Q3 | FY23 | Q2 | FY25 | Q2 | FY25 | Q2 |  | 2022-06-21 |  | 2022-06-21 | FY00 | Q3 | FY22 | Q4 |  |  | FY22 | Q4 |  | 4405622.61 | 27773281.9 | 27773281.9 |  | 6630000 |  | 6630000 | 4200000 | -360000 | 0 | 0 | 0 | 0 | No | No | Yes | Yes | No | No | No | No | No | No | Yes
B21064 | AJA00001 | Morena Improv 3 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Morena Improv 3 (S) / B21064 | 7 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Yelsits, Daniel | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY23 |  | Removed - Aug 1st | 2025-02-05 | 2025-02-27 |  | 2025-02-27 | 2021-05-03 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2023-05-04 | 2023-05-04 |  | 2023-05-04 | FY23 | Q4 | FY23 | Q4 |  |  | FY23 | Q4 | 1061220 | 1119497 |  | 1119497 | 1421911 | 1631666 |  | 1631666 | 550000 | 563048 | 0 | 0 | 0.15 | 0.15 | Yes | Yes | Yes | No | No | No | No | No | No | No | Yes
B22062 | AID00005 | AC Water & Sewer Group 1029 (P) | 2025-01-01 | Resurfacing of City Streets / AID00005 | AC Water & Sewer Group 1029 (P) / B22062 | 4 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Crespo, Santiago | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY23 |  | Removed - Aug 1st | 2024-08-26 | 2025-03-21 |  | 2025-03-21 | 2023-02-15 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 2022-10-05 | 2022-10-05 |  | 2022-10-05 | FY23 | Q2 | FY23 | Q2 |  |  | FY23 | Q2 | 2100000 | 361240.73 |  | 361240.73 | 2100000 | 361240.73 |  | 361240.73 | 161240.73 | 2308759.27 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B22152 | AKB00003 | Morena Improv 3A (W) | 2025-01-01 | Main Replacements / AKB00003 | Morena Improv 3A (W) / B22152 | 7 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Yelsits, Daniel | No Project Charter or Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY23 |  | Removed - Aug 1st | 2025-02-05 | 2025-02-27 |  | 2025-02-27 | 2021-10-08 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2023-05-04 | 2023-05-04 |  | 2023-05-04 | FY23 | Q4 | FY23 | Q4 |  |  | FY23 | Q4 | 406875 | 476975 |  | 476975 | 596574 | 692790 |  | 692790 | 0 | 674885 | 0.07 | 0.07 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
L16002.1 | L160021 | Mira Mesa Pool & Skate Plaza Ph2 | 2025-01-01 | Mira Mesa - Pool & Skate Plaza Ph 2 / L160021 | Mira Mesa Pool & Skate Plaza Ph2 / L16002.1 | 6 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Grotzinger, Juliana | Charter Only | Awarded | Removed |  | Added - Aug 1st |  |  |  |  | FY23 |  | Removed - Aug 1st |  | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2021-01-04 | FY00 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 |  | 2023-06-28 |  | 2023-06-28 | FY00 | Q3 | FY23 | Q4 |  |  | FY23 | Q4 |  | 43308127 | 43308127 | 43308127 |  | 55524058 |  | 55524058 | 19025000 | 25841058 | 0 | 0 | 0 | 0 | No | Yes | No | Yes | No | No | No | No | No | No | Yes
B18141 | AID00001 | 32nd St PHII (Market-Imp.) Rd Imp UU17 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | 32nd St PHII (Market-Imp.) Rd Imp UU17 / B18141 | 9 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter & Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-07-23 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2020-12-01 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 910000 | 434665.19 |  | 434665.19 | 1190450 | 1123449.7 |  | 1123449.7 | 281099 | 773360.5 | 0 | 0 | 0 | 0 | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B24014 | TBD | AC Overlay 2202 Phase 2 (SS) | 2025-01-01 | TBD | AC Overlay 2202 Phase 2 (SS) / B24014 | 8, 7, 9, 2, 4 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Saleh, Aveen | Charter Amendment Only | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-08-02 | 2024-03-29 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 2024-03-12 | 2024-03-12 |  | 2024-03-12 | FY24 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 | 4458616.03 | 4458616.03 |  | 4458616.03 | 5548462.58 | 5548462.16 |  | 5548462.16 | 3000000 | 1438462.58 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18153 | AID00001 | Hilltop PH I(Boundary-Toyne)Rd Imp UU617 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Hilltop PH I(Boundary-Toyne)Rd Imp UU617 / B18153 | 9 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter & Amendment | Awarded | Removed |  | Added - Aug 1st |  |  |  |  | FY24 |  | Removed - Aug 1st |  | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2020-06-01 | FY00 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 |  | 2023-11-07 |  | 2023-11-07 | FY00 | Q3 | FY24 | Q2 |  |  | FY24 | Q2 |  | 491412.61 | 1161665.47 | 1161665.47 |  | 1264453 |  | 1264453 | 235392 | 946673.8 | 0 | 0 | 0 | 0 | No | No | Yes | Yes | Yes | Yes | No | No | No | No | Yes
S22011 | S22011 | Oak Park Library | 2025-01-01 | Oak Park Library / S22011 | Oak Park Library / S22011 | 4 | Parks | Design Build | Library | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Arredondo, Monica | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-12-16 | 2024-12-11 | 2024-12-11 | 2024-12-11 | 2024-06-03 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2023-12-13 | 2023-12-13 |  | 2023-12-13 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 29000000 | 33073904 | 34900000 | 34900000 | 37285000 | 37285000 |  | 37285000 | 22050000 | 5285000 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B21045 | AJA00002 | Torrey Pines Improv 1 (S) | 2025-01-01 | Pipeline Rehabilitation / AJA00002 | Torrey Pines Improv 1 (S) / B21045 | 1 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Owen, Regan | Charter Only | Awarded | Removed |  | Added - Aug 1st |  |  |  |  | FY24 |  | Removed - Aug 1st |  | 2024-10-03 |  | 2024-10-03 | 2023-07-13 | FY00 | Q3 | FY25 | Q2 |  |  | FY25 | Q2 |  | 2024-01-11 |  | 2024-01-11 | FY00 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 |  | 2131092.17 |  | 2131092.17 |  | 3102647.17 |  | 3102647.17 | 1625800 | 794047.17 | 0 | 0 | 1.85 | 1.85 | No | No | No | No | No | No | No | No | No | No | Yes
B19021 | AGF00004 | Crown Point Playground Improvements | 2025-01-01 | Mission Bay Improvements / AGF00004 | Crown Point Playground Improvements / B19021 | 1 | Parks | Job Order Contract | Parks & Recreation | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Hossan, Farhad | Charter Only | On Schedule | Removed | Yes | Added - Aug 1st |  |  |  |  | FY24 |  | Removed - Aug 1st |  | 2025-01-28 |  | 2025-01-28 | 2022-01-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 2024-01-25 |  | 2024-01-25 | FY00 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 |  | 1720200 |  | 1720200 |  | 3108500 |  | 3108500 | 990000 | 1148500 | 0 | 0 | 0 | 0 | No | Yes | No | Yes | Yes | No | No | No | No | No | Yes
B19022 | AGF00004 | Crown Point Parking Lot Improvements | 2025-01-01 | Mission Bay Improvements / AGF00004 | Crown Point Parking Lot Improvements / B19022 | 1 | Parks | Job Order Contract | Parks & Recreation | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Hossan, Farhad | Charter Only | On Schedule | Removed | Yes | Added - Aug 1st |  |  |  |  | FY24 |  | Removed - Aug 1st |  | 2025-01-28 |  | 2025-01-28 | 2022-01-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 2024-01-25 |  | 2024-01-25 | FY00 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 |  | 1389000 |  | 1389000 |  | 2372000 |  | 2372000 | 832000 | 815000 | 0 | 0 | 0 | 0 | No | Yes | No | Yes | Yes | No | No | No | No | No | Yes
B21117 | AIG00001 | Chatsworth Blvd RRFB & Ped Refuge Island | 2025-01-01 | Median Installation / AIG00001 | Chatsworth Blvd RRFB & Ped Refuge Island / B21117 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Randles, Jacob | Charter & Amendment | On Schedule | Removed | Yes | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-07-01 | 2024-10-09 |  | 2024-10-09 | 2025-02-21 | FY25 | Q1 | FY25 | Q2 |  |  | FY25 | Q2 | 2024-02-15 | 2024-02-15 |  | 2024-02-15 | FY24 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 | 514900 | 514228.77 |  | 514228.77 | 979035 | 1059701.53 |  | 1059701.53 | 514900 | 0 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B21033 | AKB00003 | Rolando Improv 2 (W) | 2025-01-01 | Main Replacements / AKB00003 | Rolando Improv 2 (W) / B21033 | 9 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Gallardo, Jericho | Charter Only | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-11-04 | 2024-11-14 | 2024-11-13 | 2024-11-13 | 2025-03-14 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2024-03-28 | 2024-03-28 |  | 2024-03-28 | FY24 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 | 11298328.32 | 7343620.8 |  | 7343620.8 | 14433349.12 | 12624402.47 |  | 12624402.47 | 1770400 | 9988102.47 | 1.32 | 1.32 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B21031 | AJA00001 | Rolando Improv 2 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Rolando Improv 2 (S) / B21031 | 9 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Gallardo, Jericho | Charter Only | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-11-04 | 2024-11-14 | 2024-11-13 | 2024-11-13 | 2025-03-14 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2024-03-28 | 2024-03-28 |  | 2024-03-28 | FY24 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 | 6354247.18 | 16570874.2 |  | 16570874.2 | 8458021.38 | 21671429.87 |  | 21671429.87 | 7786000 | 10608229.87 | 0 | 0 | 2.35 | 2.35 | Yes | No | No | No | No | No | No | No | No | No | Yes
B22023 | AKB00003 | Oak Park Improv 2 (W) | 2025-01-01 | Main Replacements / AKB00003 | Oak Park Improv 2 (W) / B22023 | 4 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Cochinwala, Sabeen | Charter Only | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-10-03 | 2024-10-18 | 2024-10-18 | 2024-10-18 | 2025-07-02 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2023-12-14 | 2023-12-14 |  | 2023-12-14 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 13000000 | 11356700 | 12511700 | 12511700 | 15408300 | 15903599.7 |  | 15903599.7 | 4088700 | 9406599.7 | 2.15 | 2.15 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B24013 | TBD | AC Overlay Group 2403 | 2025-01-01 | TBD | AC Overlay Group 2403 / B24013 | 5 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Chan, Chun Yu | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-08-30 | 2024-08-27 | 2024-08-27 | 2024-08-27 | 2024-07-31 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 2024-04-18 | 2024-04-18 |  | 2024-04-18 | FY24 | Q4 | FY24 | Q4 |  |  | FY24 | Q4 | 6262036.65 | 6262036.65 | 6262036.65 | 6262036.65 | 8250000 | 8250000 |  | 8250000 | 5000000 | 870000 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B17098 | AID00001 | San Vicente PH I-II Rd Imp UU505-UU506 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | San Vicente PH I-II Rd Imp UU505-UU506 / B17098 | 4 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter & Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-07-23 | 2024-08-21 | 2024-08-21 | 2024-08-21 | 2020-06-01 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 2023-11-07 | 2023-11-07 |  | 2023-11-07 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 2641452.66 | 729455.49 |  | 729455.49 | 3100000 | 1764200 |  | 1764200 | 359483 | 1278897.95 | 0 | 0 | 0 | 0 | Yes | No | Yes | Yes | Yes | Yes | Yes | No | No | No | Yes
B18117 | ACA00001 | South Mission Beach SD Replacement | 2025-01-01 | Flood Resilience Infrastructure / ACA00001 | South Mission Beach SD Replacement / B18117 | 2 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Talamayan, Jonard | Charter Amendment Only | On Schedule | Removed | Yes | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-02-07 | 2025-01-08 |  | 2025-01-08 | 2021-11-08 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2023-12-20 | 2023-12-20 |  | 2023-12-20 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 33081385 | 55863950 |  | 55863950 | 45576670.49 | 68877838.5 |  | 68877838.5 | 12803995 | 52052676.25 | 0 | 0 | 0 | 0 | Yes | Yes | No | Yes | No | Yes | No | No | No | No | Yes
B18118 | ACC00001 | South Mission Beach GI | 2025-01-01 | Stormwater Green Infrastructure / ACC00001 | South Mission Beach GI / B18118 | 2 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Talamayan, Jonard | Charter & Amendment | On Schedule | Removed | Yes | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-02-07 | 2025-01-08 |  | 2025-01-08 | 2021-11-08 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-07-01 | 2023-12-20 |  | 2023-12-20 | FY25 | Q1 | FY24 | Q2 |  |  | FY24 | Q2 | 8343678 | 7813062 |  | 7813062 | 12961722.05 | 10973869.48 |  | 10973869.48 | 5404030 | 3259442.48 | 0 | 0 | 0 | 0 | Yes | Yes | No | Yes | No | Yes | No | No | No | No | Yes
B23088 | AIA00001 | South Mission Beach SD Replacement (BL) | 2025-01-01 | Minor Bike Facilities / AIA00001 | South Mission Beach SD Replacement (BL) / B23088 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Talamayan, Jonard | No Project Charter or Amendment | On Schedule | Removed | Yes | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-02-07 | 2025-01-08 |  | 2025-01-08 | 2023-09-13 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2023-12-20 | 2023-12-20 |  | 2023-12-20 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 63834 | 70820 |  | 70820 | 66440 | 93426 |  | 93426 | 52603.11 | 40822.89 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B23092 | AIK00003 | Sidewalk Replacement Group 2331 - CMR, R | 2025-01-01 | Sidewalk Repair & Replacement / AIK00003 | Sidewalk Replacement Group 2331 - CMR, R / B23092 | 5 | Transportation | Design Bid Build | Transportation | Transportation | TD | Hoenes, Craig | Medina, Steven M | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-08-16 | 2024-09-27 | 2024-09-27 | 2024-09-27 | 2024-05-15 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 2024-08-16 | 2024-05-28 |  | 2024-05-28 | FY25 | Q1 | FY24 | Q4 |  |  | FY24 | Q4 | 2000000 | 1599996 | 1599996 | 1599996 | 3268906 | 2895575.84 |  | 2895575.84 | 2000000 | -400004 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
S15015 | S15015 | Fire Station 48 | 2025-01-01 | Fire Station No. 48 - Black Mountain Ranch / S15015 | Fire Station 48 / S15015 | 5 | Buildings | Design Build | Fire-Rescue | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Arredondo, Monica | Charter Only | On Schedule | Removed | Yes | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-02-10 | 2025-03-12 |  | 2025-03-12 | 2021-04-01 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-05-06 | 2024-05-06 |  | 2024-05-06 | FY24 | Q4 | FY24 | Q4 |  |  | FY24 | Q4 | 25850000 | 26350000 |  | 26350000 | 32000000 | 33000000 |  | 33000000 | 10339000 | 16909000 | 0 | 0 | 0 | 0 | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Yes
B24011 | TBD | AC Overlay Group 2401 | 2025-01-01 | TBD | AC Overlay Group 2401 / B24011 | 6, 8, 2, 4 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Jaro, Janice | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-12-13 | 2024-10-18 | 2024-10-17 | 2024-10-17 | 2024-09-10 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2024-06-05 | 2024-06-05 |  | 2024-06-05 | FY24 | Q4 | FY24 | Q4 |  |  | FY24 | Q4 | 8000000 | 8763095.4 |  | 8763095.4 | 10875000 | 11396506 |  | 11396506 | 9950670 | -3820394 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B15015 | AIG00001 | Morena Bl & W. Bernardo Medians | 2025-01-01 | Median Installation / AIG00001 | Morena Bl & W. Bernardo Medians / B15015 | 5, 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Randles, Jacob | Charter & Amendment | On Schedule | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-02-05 | 2025-01-27 |  | 2025-01-27 | 2024-06-05 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2023-10-05 | 2023-10-05 |  | 2023-10-05 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 245000 | 271535 |  | 271535 | 506561 | 579550 |  | 579550 | 245000 | 100155 | 0 | 0 | 0 | 0 | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Yes
B21028 | AJA00001 | College East Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | College East Improv 1 (S) / B21028 | 9 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | No Project Charter or Amendment | On Schedule | Removed | Yes | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-02-04 | 2025-02-21 |  | 2025-02-21 | 2025-02-03 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-01-24 | 2024-01-24 |  | 2024-01-24 | FY24 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 | 6260580 | 14260580 |  | 14260580 | 10251000 | 18251000 |  | 18251000 | 6260580 | 8000000 | 0 | 0 | 3.94 | 3.94 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B21029 | AKB00003 | College East Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | College East Improv 1 (W) / B21029 | 9 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | No Project Charter or Amendment | On Schedule | Removed | Yes | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-02-04 | 2025-03-10 |  | 2025-03-10 | 2025-03-20 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-06-17 | 2024-06-17 |  | 2024-06-17 | FY24 | Q4 | FY24 | Q4 |  |  | FY24 | Q4 | 2817990 | 6895500 |  | 6895500 | 4662100 | 8739610 |  | 8739610 | 2817990 | 4077510 | 1.52 | 1.52 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B23157 | AID00005 | AC Overlay Group 2304 | 2025-01-01 | Resurfacing of City Streets / AID00005 | AC Overlay Group 2304 / B23157 | 3, 7, 9, 2 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-01-07 | 2024-10-11 | 2024-10-10 | 2024-10-10 | 2024-10-09 | FY25 | Q3 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2024-06-27 | 2024-06-27 |  | 2024-06-27 | FY24 | Q4 | FY24 | Q4 |  |  | FY24 | Q4 | 7000000 | 6023038.01 |  | 6023038.01 | 9520000 | 8533322.66 |  | 8533322.66 | 7000000 | -986677.34 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B23156 | AID00005 | AC Overlay Group 2303 | 2025-01-01 | Resurfacing of City Streets / AID00005 | AC Overlay Group 2303 / B23156 | 1, 8, 9, 2 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-01-08 | 2024-10-11 | 2024-10-10 | 2024-10-10 | 2024-10-09 | FY25 | Q3 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2024-06-27 | 2024-06-27 |  | 2024-06-27 | FY24 | Q4 | FY24 | Q4 |  |  | FY24 | Q4 | 4400000 | 3273924.56 |  | 3273924.56 | 5984000 | 4828599.85 |  | 4828599.85 | 4400000 | -1155400.15 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B20097 | AGF00007 | San Ysidro Act Cntr Prking Lot & ADA Imp | 2025-01-01 | Park Improvements / AGF00007 | San Ysidro Act Cntr Prking Lot & ADA Imp / B20097 | 8 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Marquez, Francis Albert | Charter Only | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-08-29 | 2024-07-29 | 2024-07-29 | 2024-07-29 | 2022-12-01 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 2023-12-08 | 2023-12-08 |  | 2023-12-08 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 3850666 | 3850666 | 3850666 | 3850666 | 5800000 | 5800000 |  | 5800000 | 1778900 | 3414700 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B23160 | ABT00001 | Scripps Miramar Ranch Lib Fire Sys Repl | 2025-01-01 | City Facility Improvements / ABT00001 | Scripps Miramar Ranch Lib Fire Sys Repl / B23160 | 5 | Buildings | Job Order Contract | General Services | Facility & Parks Project Delivery | FPPD_Pk3 | Shackelford, Kris | Lewis, Yovanna | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2024-07-05 | 2024-07-01 | 2024-07-01 | 2024-07-01 | 2024-01-25 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 2023-11-22 | 2023-11-22 |  | 2023-11-22 | FY24 | Q2 | FY24 | Q2 |  |  | FY24 | Q2 | 300000 | 301411.99 | 301412 | 301412 | 400000 | 401411.99 |  | 401411.99 | 300000 | 1411.99 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B16112 | ACC00001 | Southcrest Green Infrastructure (GI) | 2025-01-01 | Stormwater Green Infrastructure / ACC00001 | Southcrest Green Infrastructure (GI) / B16112 | 8, 4 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Talamayan, Jonard | Charter & Amendment | Awarded | Removed |  | On Published List |  |  |  |  | FY24 |  | Removed - Aug 1st | 2025-01-31 | 2024-08-26 | 2024-08-26 | 2024-08-26 | 2021-03-04 | FY25 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 2024-04-04 | 2024-04-04 |  | 2024-04-04 | FY24 | Q4 | FY24 | Q4 |  |  | FY24 | Q4 | 4089416.77 | 4089416.77 | 4089416.77 | 4089416.77 | 5698404.77 | 6673276.77 |  | 6673276.77 | 3050400 | 1098404.77 | 0 | 0 | 0 | 0 | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Yes
B24131 | TBD | 8097 Hemingway Ave SD Emergency | 2025-01-01 | TBD | 8097 Hemingway Ave SD Emergency / B24131 | 7 | Storm Water Drainage | Emergency (As-needed) | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Gonzalez, Manuel | No Project Charter or Amendment | Awarded | Removed |  | Added - Sep 1st |  |  |  |  | FY24 |  | Removed - Sept 1st |  | 2024-02-09 | 2024-08-20 | 2024-08-20 | 2024-02-09 | FY00 | Q3 | FY24 | Q3 | FY25 | Q1 | FY25 | Q1 |  | 2024-02-13 |  | 2024-02-13 | FY00 | Q3 | FY24 | Q3 |  |  | FY24 | Q3 |  | 4600000 | 4600000 | 4600000 |  | 5002000 |  | 5002000 | 4600000 | 152000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24150 | TBD | Pump Station 2 Emergency Repair | 2025-01-01 | TBD | Pump Station 2 Emergency Repair / B24150 | 2 | Sewer | Emergency (As-needed) | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Gonzalez, Manuel | No Project Charter or Amendment | Awarded | Removed | [6 empty] | FY24 |  | Removed - Jan 1st |  | 2024-05-01 | 2024-09-09 | 2024-09-09 | 2024-05-01 | FY00 | Q3 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 |  | 2024-05-03 |  | 2024-05-03 | FY00 | Q3 | FY24 | Q4 |  |  | FY24 | Q4 |  | 4500000 | 4200000 | 4200000 |  | 4800000 |  | 4800000 | 4500000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24142 | TBD | 6137 Tarragona Drive SD Emergency | 2025-01-01 | TBD | 6137 Tarragona Drive SD Emergency / B24142 | 9 | Storm Water Drainage | Emergency (As-needed) | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Delgado, Carolina | No Project Charter or Amendment | Awarded | Removed | [6 empty] | FY24 |  | Removed - Jan 1st |  | 2024-04-18 | 2024-09-17 | 2024-09-17 | 2024-04-18 | FY00 | Q3 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 |  | 2024-04-30 |  | 2024-04-30 | FY00 | Q3 | FY24 | Q4 |  |  | FY24 | Q4 |  | 2000000 | 2000000 | 2000000 |  | 3000000 |  | 3000000 | 1500000 | 1000000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24146 | TBD | 11131 Negley Avenue SD Emergency | 2025-01-01 | TBD | 11131 Negley Avenue SD Emergency / B24146 | 5 | Storm Water Drainage | Sole Source Emergency | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Pan, Junmin | No Project Charter or Amendment | Awarded | Removed | [6 empty] | FY24 |  | Removed - Jan 1st |  | 2024-04-15 | 2024-09-20 | 2024-09-20 | 2024-04-15 | FY00 | Q3 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 |  | 2024-04-17 |  | 2024-04-17 | FY00 | Q3 | FY24 | Q4 |  |  | FY24 | Q4 |  | 1700000 | 1500000 | 1500000 |  | 2000000 |  | 2000000 | 1700000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24145 | TBD | 7403 Rowena Street SD Emergency | 2025-01-01 | TBD | 7403 Rowena Street SD Emergency / B24145 | 7 | Storm Water Drainage | Sole Source Emergency | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Cramoline, Jeff | No Project Charter or Amendment | Awarded | Removed |  | Added - Oct 1st |  |  |  |  | FY24 |  | Removed - Jan 1st |  | 2024-03-29 | 2024-10-03 | 2024-10-03 | 2024-03-29 | FY00 | Q3 | FY24 | Q3 | FY25 | Q2 | FY25 | Q2 |  | 2024-04-03 |  | 2024-04-03 | FY00 | Q3 | FY24 | Q4 |  |  | FY24 | Q4 |  | 1500000 | 1500000 | 1500000 |  | 2000000 |  | 2000000 | 2000000 | -250000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
L24000.1 | TBD | Pump Station 1 Improvements and Modernization | 2025-01-01 | TBD | Pump Station 1 Improvements and Modernization / L24000.1 | 8 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Nezha, Shaza | No Project Charter or Amendment | Awarded | Removed |  | On Published List |  |  |  | On Published List | FY24 |  | Removed - Nov 1st | 2024-12-09 | 2024-10-28 | 2024-10-28 | 2024-10-28 | 2025-02-13 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2024-08-02 | 2024-04-17 |  | 2024-04-17 | FY25 | Q1 | FY24 | Q4 |  |  | FY24 | Q4 | 57000000 | 93282580 | 93282580 | 93282580 | 70086963.86 | 111369543 |  | 111369543 | 9969200 | 95046543 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18046 | AIL00001 | Kettner & Palm Pedestrian Hybrid Beacon | 2025-01-01 | Traffic Calming / AIL00001 | Kettner & Palm Pedestrian Hybrid Beacon / B18046 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | On Schedule | Removed |  | On Published List |  |  |  | On Published List | FY24 |  | Removed - Dec 1st | 2025-01-09 | 2024-11-05 |  | 2024-11-05 | 2021-01-04 | FY25 | Q3 | FY25 | Q2 |  |  | FY25 | Q2 | 2024-07-01 | 2024-02-29 |  | 2024-02-29 | FY25 | Q1 | FY24 | Q3 |  |  | FY24 | Q3 | 890000 | 680566.35 |  | 680566.35 | 1580810 | 1371376.35 |  | 1371376.35 | 275100 | 1099410 | 0 | 0 | 0 | 0 | Yes | Yes | No | Yes | No | No | No | No | No | No | Yes
L24002.2 | TBD | Sports Arena C-HRS Occupancy Upgrades | 2025-01-01 | TBD | Sports Arena C-HRS Occupancy Upgrades / L24002.2 | 2 | Buildings | Job Order Contract | Homelessness Strategies and Solutions | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Castaneyra, Jose | No Project Charter or Amendment | On Schedule | Removed |  | Added - Dec 1st |  |  |  |  | FY24 |  | Removed - Dec 1st |  | 2025-01-02 |  | 2025-01-02 | 2025-01-15 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 2023-08-02 |  | 2023-08-02 | FY00 | Q3 | FY24 | Q1 |  |  | FY24 | Q1 |  | 300000 |  | 300000 |  | 560000 |  | 560000 |  |  | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22107 | AIA00001 | Morena Pipeline (BL) | 2025-01-01 | Minor Bike Facilities / AIA00001 | Morena Pipeline (BL) / B22107 | 7, 2 | Transportation | Design Bid Build | Transportation | PUD Pure Water | PUD_PW | Tadros, Sameh | Aivati, Doran | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List | [7 empty] | 2025-02-05 | 2025-01-27 |  | 2025-01-27 | 2019-05-01 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2025-02-05 | 2024-07-25 |  | 2024-07-25 | FY25 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 | 373688 | 373688 |  | 373688 | 373688 | 373688 |  | 373688 | 373688 | 0 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B24106 | TBD | Villa La Jolla Drainage System Emergency | 2025-01-01 | TBD | Villa La Jolla Drainage System Emergency / B24106 | 1 | Storm Water Drainage | Sole Source Emergency | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Cramoline, Jeff | No Project Charter or Amendment | Awarded | Advertised |  | Added - Nov 1st |  |  |  | Added - Sep 1st |  |  |  |  | 2024-05-15 | 2024-11-07 | 2024-11-07 | 2024-05-15 | FY00 | Q3 | FY24 | Q4 | FY25 | Q2 | FY25 | Q2 |  | 2025-01-02 | 2024-11-07 | 2024-11-07 | FY00 | Q3 | FY25 | Q3 | FY25 | Q2 | FY25 | Q2 |  | 18000000 | 13000000 | 13000000 |  | 21890000 |  | 21890000 | 13000000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24144 | TBD | 6760 High Country Court SD Emergency | 2025-01-01 | TBD | 6760 High Country Court SD Emergency / B24144 | 7 | Storm Water Drainage | Sole Source Emergency | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Cramoline, Jeff | No Project Charter or Amendment | Awarded | Advertised | [5 empty] | Added - Sep 1st |  |  |  |  | 2024-04-03 | 2024-10-07 | 2024-10-07 | 2024-04-03 | FY00 | Q3 | FY24 | Q4 | FY25 | Q2 | FY25 | Q2 |  | 2024-08-02 |  | 2024-08-02 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 2750000 | 3000000 | 3000000 |  | 4000000 |  | 4000000 | 2750000 | 1000000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20149 | AJA00001 | Mountain View Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Mountain View Improv 1 (S) / B20149 | 9 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List | [7 empty] | 2024-08-28 | 2025-03-14 |  | 2025-03-14 | 2022-03-01 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-02-08 | 2024-09-20 | 2024-09-20 | 2024-09-20 | FY24 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 453800 | 2453800 |  | 2453800 | 715799 | 2915799 |  | 2915799 | 453800 | 1999 | 0 | 0 | 0.18 | 0.18 | Yes | Yes | Yes | Yes | No | No | No | No | No | No | Yes
B22092 | AKB00003 | Roseville/Fleet Ridge Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Roseville/Fleet Ridge Improv 1 (W) / B22092 | 2 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Zare Afifi, Mehrnaz | Charter Only | On Schedule | Advertised | Yes | On Published List | [7 empty] | 2024-12-30 | 2025-02-19 |  | 2025-02-19 | 2024-11-08 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-06-20 | 2024-06-20 | 2024-08-29 | 2024-08-29 | FY24 | Q4 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 | 2976000 | 10987496.79 |  | 10987496.79 | 4347000 | 13958497.48 |  | 13958497.48 | 2976000 | 7093940 | 1.13 | 1.13 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B22097 | AJA00002 | Roseville/Fleet Ridge Improv 1 (S) | 2025-01-01 | Pipeline Rehabilitation / AJA00002 | Roseville/Fleet Ridge Improv 1 (S) / B22097 | 2 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Zare Afifi, Mehrnaz | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List | [7 empty] | 2024-12-30 | 2025-02-19 |  | 2025-02-19 | 2024-11-08 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-06-20 | 2024-06-20 | 2024-08-29 | 2024-08-29 | FY24 | Q4 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 | 2954000 | 4583008.44 |  | 4583008.44 | 4315000 | 5613507.08 |  | 5613507.08 | 2954000 | 1160750 | 0 | 0 | 2.02 | 2.02 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18111 | AJA00001 | Sewer & AC Water Group 1037 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Sewer & AC Water Group 1037 (S) / B18111 | 3 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Famorcan, Ronald | Charter Only | On Schedule | Advertised | Yes | On Published List | [7 empty] | 2025-03-10 | 2025-05-09 |  | 2025-05-09 | 2023-07-28 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-06-25 | 2024-08-19 | 2024-08-19 | 2024-08-19 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 5009300 | 11895000 |  | 11895000 | 7163400 | 15606000 |  | 15606000 | 5009300 | 0 | 0 | 0 | 1.88 | 1.88 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18114 | AKB00003 | Sewer & AC Water Group 1037 (W) | 2025-01-01 | Main Replacements / AKB00003 | Sewer & AC Water Group 1037 (W) / B18114 | 3 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Famorcan, Ronald | Charter Only | On Schedule | Advertised | Yes | On Published List | [7 empty] | 2025-03-10 | 2025-05-09 |  | 2025-05-09 | 2023-07-28 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-06-25 | 2024-08-19 | 2024-08-19 | 2024-08-19 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 1493800 | 4526000 |  | 4526000 | 2136200 | 6098400 |  | 6098400 | 1493800 | 231622 | 0.71 | 0.71 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
S16027 | S16027 | Morena Pipeline | 2025-01-01 | Morena Pipeline / S16027 | Morena Pipeline / S16027 | 3, 7, 2 | Water | Design Bid Build | Public Utilities | PUD Pure Water | PUD_PW | Tadros, Sameh | Aivati, Doran | Charter Only | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-02-03 | 2025-02-04 |  | 2025-02-04 | 2019-05-01 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2023-05-04 | 2024-07-25 | 2024-08-07 | 2024-08-07 | FY23 | Q4 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 72462403.12 | 70456758 |  | 70456758 | 94010263 | 106384548 |  | 106384548 | 26078762 | 87266969.33 | 6.45 | 6.45 | 0 | 0 | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Yes
B23112 | AJA00002 | Serra Mesa Improv 1 Rehab (S) | 2025-01-01 | Pipeline Rehabilitation / AJA00002 | Serra Mesa Improv 1 Rehab (S) / B23112 | 7 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Katzenstein, Phuong | Charter Only | Awarded | Advertised |  | On Published List |  |  |  | On Published List |  |  |  | 2025-01-09 | 2025-02-07 | 2024-12-17 | 2024-12-17 | 2025-01-09 | FY25 | Q3 | FY25 | Q3 | FY25 | Q2 | FY25 | Q2 | 2024-07-01 | 2024-08-26 | 2024-08-26 | 2024-08-26 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 1429200 | 1254622.5 |  | 1254622.5 | 2203000 | 3022565.63 |  | 3022565.63 | 1429200 | 819565.63 | 0 | 0 | 1.1 | 1.1 | Yes | No | No | No | No | No | No | No | No | No | Yes
B22032 | ABP00002 | PQPS VFD Replacement Project | 2025-01-01 | Metropolitan System Pump Stations / ABP00002 | PQPS VFD Replacement Project / B22032 | 5 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Vega, Melissa | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-02-11 | 2025-04-04 |  | 2025-04-04 | 2023-07-11 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-01 | 2024-09-09 | 2024-09-09 | 2024-09-09 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 900000 | 1412200 |  | 1412200 | 1352743.52 | 2012848.18 |  | 2012848.18 | 497000 | 1195176.23 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B22035 | ABP00002 | PQPS Gas Sensor Replacement | 2025-01-01 | Metropolitan System Pump Stations / ABP00002 | PQPS Gas Sensor Replacement / B22035 | 5 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Kargar, Maryam | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-02-11 | 2025-04-04 |  | 2025-04-04 | 2023-07-11 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-01 | 2024-09-09 | 2024-09-09 | 2024-09-09 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 109518.89 | 155600 |  | 155600 | 594679.06 | 785600.17 |  | 785600.17 | 150000 | 354679.06 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B18183 | AJA00001 | Accelerated Sewer Referral Group 847 | 2025-01-01 | Sewer Main Replacements / AJA00001 | Accelerated Sewer Referral Group 847 / B18183 | 1, 3, 7, 9, 2, 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-11-26 | 2025-02-21 |  | 2025-02-21 | 2022-12-01 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-08-01 | 2025-01-14 |  | 2025-01-14 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 1242900 | 1867000 |  | 1867000 | 2028300 | 4035067.32 |  | 4035067.32 | 1242900 | 2006767.32 | 0 | 0 | 0.43 | 0.43 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B20134 | AJA00001 | East Village Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | East Village Improv 1 (S) / B20134 | 3 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-03-03 | 2025-05-01 |  | 2025-05-01 | 2025-03-03 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-03 | 2024-10-18 | 2024-10-18 | 2024-10-18 | FY25 | Q1 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 4099100 | 4099100 |  | 4099100 | 5636300 | 5836300 |  | 5836300 | 4099100 | 200000 | 0 | 0 | 1.43 | 1.43 | Yes | No | No | No | No | No | No | No | No | No | Yes
B22004 | AJA00001 | Ocean Beach Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Ocean Beach Improv 1 (S) / B22004 | 2 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | Charter Only | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-01-30 | 2025-06-05 |  | 2025-06-05 | 2025-07-01 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-01 | 2024-11-25 | 2024-11-20 | 2024-11-20 | FY25 | Q1 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 1567612.07 | 1655675.5 |  | 1655675.5 | 2141532.07 | 2846895.5 |  | 2846895.5 | 922680 | 1350295.5 | 0 | 0 | 0.3 | 0.3 | Yes | No | No | No | No | No | No | No | No | No | Yes
B21096 | AJA00001 | Valencia Park Improv 4 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Valencia Park Improv 4 (S) / B21096 | 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Crespo, Santiago | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-03-13 | 2025-05-09 |  | 2025-05-09 | 2023-10-09 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-30 | 2024-09-20 | 2024-09-20 | 2024-09-20 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 470300 | 470300 |  | 470300 | 736800 | 736800 |  | 736800 | 427770 | 0 | 0 | 0 | 0.18 | 0.18 | Yes | No | No | No | No | No | No | No | No | No | Yes
B24044 | TBD | Paradise Hills Improv 2 (W) | 2025-01-01 | TBD | Paradise Hills Improv 2 (W) / B24044 | 4 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Valadez, Roberto | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-04-17 | 2025-04-10 |  | 2025-04-10 | 2025-04-17 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-10-07 | 2024-09-12 | 2024-09-12 | 2024-09-12 | FY25 | Q2 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 13513770 | 13513770 |  | 13513770 | 19559000 | 19519771 |  | 19519771 | 13513770 | 0 | 2.49 | 2.49 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B22037 | ABI00001 | Otay WTP Raw Water PS Switchboard Replac | 2025-01-01 | Water Treatment Plants / ABI00001 | Otay WTP Raw Water PS Switchboard Replac / B22037 | 8 | Water | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Rivera, Jacob | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-03-05 | 2025-06-10 |  | 2025-06-10 | 2024-04-29 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-22 | 2025-02-03 |  | 2025-02-03 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 1100000 | 1100000 |  | 1100000 | 1990000 | 1990000 |  | 1990000 | 729000 | 698000 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B16017 | AKA00002 | Pressure Reducing Stations Upgrades Phs1 | 2025-01-01 | Pressure Reduction Upgrade / AKA00002 | Pressure Reducing Stations Upgrades Phs1 / B16017 | 1, 3, 6, 7, 9 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Torres, Gabriel | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-03-13 | 2025-06-23 |  | 2025-06-23 | 2022-05-02 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-30 | 2025-01-22 |  | 2025-01-22 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 8600000 | 8600000 |  | 8600000 | 11470575.05 | 12305000 |  | 12305000 | 3740000 | 5180575.05 | 0 | 0 | 0 | 0 | Yes | No | No | Yes | Yes | Yes | No | No | No | No | Yes
B19073 | ACA00001 | 5th and Brookes SD Upgrade | 2025-01-01 | Flood Resilience Infrastructure / ACA00001 | 5th and Brookes SD Upgrade / B19073 | 3 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Meredith, William | Charter Only | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-02-11 | 2025-03-18 |  | 2025-03-18 | 2022-03-01 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-08-01 | 2024-09-06 | 2024-09-06 | 2024-09-06 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 3219464 | 4730082 |  | 4730082 | 5173856 | 7068284 |  | 7068284 | 1559400 | 4728924 | 0 | 0 | 0 | 0 | Yes | No | No | Yes | No | No | No | No | No | No | Yes
B20125 | AKB00003 | East Village Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | East Village Improv 1 (W) / B20125 | 3 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-03-03 | 2025-05-01 |  | 2025-05-01 | 2025-03-03 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-03 | 2024-10-18 | 2024-10-18 | 2024-10-18 | FY25 | Q1 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 1004500 | 3500000 |  | 3500000 | 1381200 | 4200000 |  | 4200000 | 1004500 | 323329 | 0.51 | 0.51 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B19060 | AIL00004 | El Cajon & Kansas - Traffic Signal | 2025-01-01 | Traffic Signals - Citywide / AIL00004 | El Cajon & Kansas - Traffic Signal / B19060 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Kim, Jinsil | Charter Only | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2024-12-18 | 2025-06-18 |  | 2025-06-18 | 2021-01-04 | FY25 | Q2 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-07-05 | 2024-09-20 | 2024-09-20 | 2024-09-20 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 608200 | 997000 |  | 997000 | 1100000 | 1863000 |  | 1863000 | 413200 | 1065700 | 0 | 0 | 0 | 0 | Yes | No | No | Yes | No | No | No | No | No | No | Yes
B19064 | AJA00001 | Accelerated Sewer Referral Group 852 | 2025-01-01 | Sewer Main Replacements / AJA00001 | Accelerated Sewer Referral Group 852 / B19064 | 3, 6, 8, 7, 5, 2, 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-22 | 2025-04-22 |  | 2025-04-22 | 2023-07-03 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-11-12 | 2025-02-20 |  | 2025-02-20 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 1573000 | 1573000 |  | 1573000 | 2609600 | 3797835.61 |  | 3797835.61 | 1573000 | 1375235.61 | 0 | 0 | 0.7 | 0.7 | Yes | No | No | No | No | No | No | No | No | No | Yes
B22019 | AKB00003 | Azalea Park Improv 2 (W) | 2025-01-01 | Main Replacements / AKB00003 | Azalea Park Improv 2 (W) / B22019 | 9 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-29 | 2025-04-29 |  | 2025-04-29 | 2025-03-21 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-11-14 | 2025-01-14 |  | 2025-01-14 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 4284900 | 4284900 |  | 4284900 | 6940000 | 6940000 |  | 6940000 | 4284900 | 0 | 1.77 | 1.77 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B15168 | AIK00001 | Genesee Ave-Chateau to Sauk Sidewalk | 2025-01-01 | New Walkways / AIK00001 | Genesee Ave-Chateau to Sauk Sidewalk / B15168 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter & Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-01-24 | 2025-02-07 |  | 2025-02-07 | 2024-10-02 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-07-16 | 2024-10-01 | 2024-09-16 | 2024-09-16 | FY25 | Q1 | FY25 | Q2 | FY25 | Q1 | FY25 | Q1 | 2730910 | 3490587.35 |  | 3490587.35 | 4899015 | 5785692.35 |  | 5785692.35 | 2257632 | 1476835 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18155 | AID00001 | Block 1M (La Jolla 4) Rd Imp UU659_RP | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Block 1M (La Jolla 4) Rd Imp UU659_RP / B18155 | 1 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Saleh, Aveen | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-09-16 | 2025-01-16 |  | 2025-01-16 | 2021-06-01 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-07-15 | 2024-09-05 |  | 2024-09-05 | FY25 | Q1 | FY25 | Q1 |  |  | FY25 | Q1 | 2267379.53 | 1255645.53 |  | 1255645.53 | 2762182.16 | 2052456.64 |  | 2052456.64 | 268212.8 | 1520775 | 0 | 0 | 0 | 0 | Yes | No | Yes | Yes | Yes | No | No | No | No | No | Yes
B25003 | TBD | Asphalt Overlay Group 2503 | 2025-01-01 | TBD | Asphalt Overlay Group 2503 / B25003 | 4 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Damnjanovic, Nenad | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-11-05 | 2024-11-25 |  | 2024-11-25 | 2024-11-05 | FY25 | Q2 | FY25 | Q2 |  |  | FY25 | Q2 | 2024-09-04 | 2024-08-22 |  | 2024-08-22 | FY25 | Q1 | FY25 | Q1 |  |  | FY25 | Q1 | 4500000 | 2403719.71 |  | 2403719.71 | 6001000 | 4114719.71 |  | 4114719.71 | 4500000 | -1885000 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18136 | AID00001 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 / B18136 | 3 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-07 | 2025-06-30 |  | 2025-06-30 | 2019-12-02 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-24 | 2025-01-02 |  | 2025-01-02 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 701052.15 | 437500 |  | 437500 | 1086105.42 | 971000.66 |  | 971000.66 | 190910 | 713271.62 | 0 | 0 | 0 | 0 | Yes | No | Yes | Yes | Yes | Yes | No | No | No | No | Yes
S22010 | S22010 | Old Logan Heights Library Renovation | 2025-01-01 | Old Logan Heights Library Renovation / S22010 | Old Logan Heights Library Renovation / S22010 | 8 | Buildings | Design Bid Build | Library | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Arredondo, Monica | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-02-24 | 2025-03-03 |  | 2025-03-03 | 2025-02-03 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-08-16 | 2024-08-01 |  | 2024-08-01 | FY25 | Q1 | FY25 | Q1 |  |  | FY25 | Q1 | 2687000 | 3205751 |  | 3205751 | 6341521 | 6341521 |  | 6341521 | 0 | 5196237.11 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B23142 | AKB00003 | Talmadge Improv 2 (W) | 2025-01-01 | Main Replacements / AKB00003 | Talmadge Improv 2 (W) / B23142 | 9 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Cochinwala, Sabeen | No Project Charter or Amendment | On Schedule | Advertised | Yes | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2025-04-21 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2024-09-27 | 2024-09-27 | 2024-09-27 | FY00 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 |  | 7692300 |  | 7692300 |  | 12000000 |  | 12000000 | 7692300 | 0 | 2.15 | 2.15 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B21109 | AKA00003 | San Carlos Interconnect Trans Pipeline | 2025-01-01 | Large Diameter Water Transmission PPL / AKA00003 | San Carlos Interconnect Trans Pipeline / B21109 | 7 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Bustamante, Ramesis W | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-25 | 2025-06-25 |  | 2025-06-25 | 2025-02-11 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-10-24 | 2025-02-13 |  | 2025-02-13 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 7500000 | 7500000 |  | 7500000 | 9120900 | 10974100.16 |  | 10974100.16 | 4288050 | 2735500 | 1.38 | 1.38 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B13010 | AIL00005 | Signal Mods in Barrio Logan | 2025-01-01 | Traffic Signals - Modify & Modernize / AIL00005 | Signal Mods in Barrio Logan / B13010 | 8 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-07-01 | 2025-04-01 |  | 2025-04-01 | 2021-01-15 | FY25 | Q1 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-07-01 | 2024-10-04 |  | 2024-10-04 | FY25 | Q1 | FY25 | Q2 |  |  | FY25 | Q2 | 1430000 | 1287091.83 |  | 1287091.83 | 2151900 | 2008991.83 |  | 2008991.83 | 282800 | 1775300 | 0 | 0 | 0 | 0 | Yes | Yes | Yes | Yes | Yes | No | No | No | No | No | Yes
B24086 | TBD | Block 7G2 Rd Imp (CS) UU209 | 2025-01-01 | TBD | Block 7G2 Rd Imp (CS) UU209 / B24086 | 9 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-09-11 | 2025-01-13 |  | 2025-01-13 | 2024-07-12 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-07-10 | 2024-10-01 |  | 2024-10-01 | FY25 | Q1 | FY25 | Q2 |  |  | FY25 | Q2 | 2350000 | 2325712.51 |  | 2325712.51 | 3348000 | 3323712.51 |  | 3323712.51 | 2350000 | 0 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B24087 | TBD | Block 7G2 Rd Improv UU209 UU629 (P) | 2025-01-01 | TBD | Block 7G2 Rd Improv UU209 UU629 (P) / B24087 | 9 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-09-11 | 2025-01-13 |  | 2025-01-13 | 2024-07-12 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-07-10 | 2024-10-01 |  | 2024-10-01 | FY25 | Q1 | FY25 | Q2 |  |  | FY25 | Q2 | 1880000 | 1860804.33 |  | 1860804.33 | 1880000 | 1860804.33 |  | 1860804.33 | 850000 | 1030000 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18151 | AID00001 | Hughes St (58th St-Jodi St) Rd Imp UU101 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Hughes St (58th St-Jodi St) Rd Imp UU101 / B18151 | 9 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Saleh, Aveen | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-09-16 | 2025-01-16 |  | 2025-01-16 | 2020-12-01 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-07-15 | 2024-09-05 |  | 2024-09-05 | FY25 | Q1 | FY25 | Q1 |  |  | FY25 | Q1 | 509250 | 479810.81 |  | 479810.81 | 738463 | 988496.93 |  | 988496.93 | 208247 | 702691.87 | 0 | 0 | 0 | 0 | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B25001 | TBD | AC Overlay Group 2501 | 2025-01-01 | TBD | AC Overlay Group 2501 / B25001 | 3 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-10-07 | 2025-01-09 |  | 2025-01-09 | 2024-09-23 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-08-05 | 2024-10-02 |  | 2024-10-02 | FY25 | Q1 | FY25 | Q2 |  |  | FY25 | Q2 | 4500000 | 1961656.84 |  | 1961656.84 | 5168000 | 2629656.84 |  | 2629656.84 | 4500000 | -2538343.16 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B24148 | TBD | AC Overlay Group 2404 | 2025-01-01 | TBD | AC Overlay Group 2404 / B24148 | 8, 4 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Mansour, Amanda | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-12-03 | 2025-01-02 |  | 2025-01-02 | 2024-12-03 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-10-01 | 2024-08-07 |  | 2024-08-07 | FY25 | Q2 | FY25 | Q1 |  |  | FY25 | Q1 | 4500000 | 2758760.58 |  | 2758760.58 | 6358000 | 4431704.75 |  | 4431704.75 | 4500000 | -1850558.34 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B25004 | TBD | Asphalt Overlay Group 2504 | 2025-01-01 | TBD | Asphalt Overlay Group 2504 / B25004 | 9 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | CamachoDiaz, Jason | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-12-03 | 2024-12-03 |  | 2024-12-03 | 2024-12-03 | FY25 | Q2 | FY25 | Q2 |  |  | FY25 | Q2 | 2024-10-01 | 2024-09-03 |  | 2024-09-03 | FY25 | Q2 | FY25 | Q1 |  |  | FY25 | Q1 | 4500000 | 3048589.39 |  | 3048589.39 | 5730000 | 4263166.21 |  | 4263166.21 | 4500000 | -1157115.91 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B20075 | AIL00005 | Traffic Signal Mods Grp 20-01 | 2025-01-01 | Traffic Signals - Modify & Modernize / AIL00005 | Traffic Signal Mods Grp 20-01 / B20075 | 3, 6, 4 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Kim, Jinsil | Charter Only | On Schedule | Advertised | Yes | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-25 |  | 2025-06-25 | 2021-12-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2024-12-12 | 2024-12-12 | 2024-12-12 | FY00 | Q3 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 |  | 1035000 |  | 1035000 |  | 1849820 |  | 1849820 | 303400 | 1312100 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B18023 | AID00001 | Block 2BB (Pacific Beach) SL UU854 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Block 2BB (Pacific Beach) SL UU854 / B18023 | 1 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Kim, Jinsil | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-01-13 | 2024-11-20 |  | 2024-11-20 | 2020-12-01 | FY25 | Q3 | FY25 | Q2 |  |  | FY25 | Q2 | 2024-07-03 | 2024-07-03 |  | 2024-07-03 | FY25 | Q1 | FY25 | Q1 |  |  | FY25 | Q1 | 1348000 | 1078000 |  | 1078000 | 1943756.98 | 1673756.98 |  | 1673756.98 | 395400 | 998756.98 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B22007 | AJA00002 | Encanto Improv 3 (S) | 2025-01-01 | Pipeline Rehabilitation / AJA00002 | Encanto Improv 3 (S) / B22007 | 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Zare Afifi, Mehrnaz | Charter Only | On Schedule | Advertised | Yes | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-04-30 |  | 2025-04-30 | 2025-04-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2024-10-10 | 2024-10-10 | 2024-10-10 | FY00 | Q3 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 |  | 2792000 |  | 2792000 |  | 5262900 |  | 5262900 | 5568000 | 0 | 0 | 0 | 2.67 | 2.67 | No | No | No | No | No | No | No | No | No | No | Yes
B17071 | AID00001 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 / B17071 | 1 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-07 | 2025-06-30 |  | 2025-06-30 | 2020-06-01 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-24 | 2024-12-10 |  | 2024-12-10 | FY25 | Q1 | FY25 | Q2 |  |  | FY25 | Q2 | 454277.19 | 177000 |  | 177000 | 835166.74 | 628134.29 |  | 628134.29 | 106912 | 462305.29 | 0 | 0 | 0 | 0 | Yes | No | Yes | Yes | Yes | Yes | No | No | No | No | Yes
B18138 | AID00001 | Wightman (Chamoune -Euclid) Rd Imp UU388 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Wightman (Chamoune -Euclid) Rd Imp UU388 / B18138 | 9 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-07 | 2025-06-30 |  | 2025-06-30 | 2020-06-01 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-24 | 2025-01-02 |  | 2025-01-02 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 656451.79 | 420000 |  | 420000 | 900000 | 900000 |  | 900000 | 123367.07 | 733454.46 | 0 | 0 | 0 | 0 | Yes | No | Yes | Yes | Yes | Yes | No | No | No | No | Yes
B18142 | AID00001 | Block 6DD1 (Clairemont Mesa)Rd Imp UU410 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Block 6DD1 (Clairemont Mesa)Rd Imp UU410 / B18142 | 2 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-07 | 2025-06-30 |  | 2025-06-30 | 2020-12-01 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-24 | 2025-01-02 |  | 2025-01-02 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 2450215 | 677250 |  | 677250 | 2984764 | 1500811 |  | 1500811 | 1473215 | -383205 | 0 | 0 | 0 | 0 | Yes | No | Yes | Yes | Yes | No | No | No | No | No | Yes
B00836 | AID00001 | District 1 Block 1-J UUD | 2025-01-01 | Utilities Undergrounding Program / AID00001 | District 1 Block 1-J UUD / B00836 | 1 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Xiao, Jie | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-09 | 2024-11-21 |  | 2024-11-21 | 2020-06-01 | FY25 | Q4 | FY25 | Q2 |  |  | FY25 | Q2 | 2024-07-16 | 2024-07-05 |  | 2024-07-05 | FY25 | Q1 | FY25 | Q1 |  |  | FY25 | Q1 | 2075809.17 | 1415917.73 |  | 1415917.73 | 2571809.17 | 2028735.12 |  | 2028735.12 | 137536 | 2526818.56 | 0 | 0 | 0 | 0 | Yes | No | No | No | Yes | Yes | Yes | No | Yes | No | Yes
L17000.7 | L17000 | Miramar Landfill Office Trailer Replacement | 2025-01-01 | Miramar Landfill Facility Improvements / L17000 | Miramar Landfill Office Trailer Replacement / L17000.7 | Not in Active P6 | Landfill | Design Build | Environmental Services | Disposal & Environmental Protection | Not in Active P6 | Luis Campos | Not in Active P6 | Not in Active P6 | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-12-08 | Not in Active P6 | 2025-06-16 | 2025-06-16 | Not in Active P6 | FY25 | Q2 | #VALUE! | #VALUE! | FY25 | Q4 | FY25 | Q4 | 2024-12-08 | Not in Active P6 | 2025-02-10 | 2025-02-10 | FY25 | Q2 | #VALUE! | #VALUE! | FY25 | Q3 | FY25 | Q3 | 2000000 | Not in Active P6 | 2000000 | 2000000 | 2500000 | Not in Active P6 | 2500000 | 2500000 |  |  | 0 | 0 | 0 | 0 | Yes | No | Yes | No | No | No | No | No | No | No | No
B24147 | TBD | AC Overlay Group 2406 | 2025-01-01 | TBD | AC Overlay Group 2406 / B24147 | 7 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Chan, Chun Yu | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2024-11-15 |  | 2024-11-15 | 2024-12-03 | FY00 | Q3 | FY25 | Q2 |  |  | FY25 | Q2 |  | 2024-08-01 |  | 2024-08-01 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 2286800.2 |  | 2286800.2 |  | 2686800.2 |  | 2686800.2 | 2700000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25002 | TBD | AC Overlay Group 2502 | 2025-01-01 | TBD | AC Overlay Group 2502 / B25002 | 6, 7, 9 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Melo Rodriguez, Pedro | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-01-03 |  | 2025-01-03 | 2024-10-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 2024-08-16 |  | 2024-08-16 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 4813275.75 |  | 4813275.75 |  | 6092027.54 |  | 6092027.54 | 3600000 | 1291940 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B21148 | ABO00001 | MBC Gallery Pipeline Replacement | 2025-01-01 | Metro Treatment Plants / ABO00001 | MBC Gallery Pipeline Replacement / B21148 | 6 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Torres, Gabriel | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-30 |  | 2025-06-30 | 2023-12-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-02-20 |  | 2025-02-20 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 1827540 |  | 1827540 |  | 3479540 |  | 3479540 | 1323000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24053 | TBD | Linda Vista Improv 1 (S) | 2025-01-01 | TBD | Linda Vista Improv 1 (S) / B24053 | 7 | Sewer | Job Order Contract | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-04-07 |  | 2025-04-07 | 2025-04-25 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-01-31 |  | 2025-01-31 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3266000 |  | 3266000 |  | 4527000 |  | 4527000 | 3266000 | 0 | 0 | 0 | 1.78 | 1.78 | No | No | No | No | No | No | No | No | No | No | Yes
B20036 | AJA00001 | Corridor Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Corridor Improv 1 (S) / B20036 | 9 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | Charter Only | On Schedule | Advertised | Yes |  |  |  |  | Added - Aug 1st |  |  |  |  | 2025-04-04 |  | 2025-04-04 | 2024-10-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2024-08-27 | 2024-08-27 | 2024-08-27 | FY00 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 |  | 3699500 |  | 3699500 |  | 4892800 |  | 4892800 | 3699500 | 161000 | 0 | 0 | 1.83 | 1.83 | No | No | No | No | No | No | No | No | No | No | Yes
B19162 | AGF00004 | S. De Anza Parking Lot | 2025-01-01 | Mission Bay Improvements / AGF00004 | S. De Anza Parking Lot / B19162 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Marquez, Francis Albert | Charter & Amendment | On Schedule | Advertised | Yes | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2023-12-08 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2024-11-25 | 2024-11-22 | 2024-11-22 | FY00 | Q3 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 |  | 3200000 |  | 3200000 |  | 4572000 |  | 4572000 | 4837000 | -1797000 | 0 | 0 | 0 | 0 | No | No | No | No | No | Yes | No | No | No | No | Yes
B19172 | AGF00004 | S. De Anza Comfort Station | 2025-01-01 | Mission Bay Improvements / AGF00004 | S. De Anza Comfort Station / B19172 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Marquez, Francis Albert | Charter Only | On Schedule | Advertised | Yes | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2022-11-30 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2024-11-25 | 2024-11-22 | 2024-11-22 | FY00 | Q3 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 |  | 1300000 |  | 1300000 |  | 2657000 |  | 2657000 | 1011000 | 465750 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19173 | AGF00004 | S. De Anza Basketball Courts and Play Ar | 2025-01-01 | Mission Bay Improvements / AGF00004 | S. De Anza Basketball Courts and Play Ar / B19173 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Marquez, Francis Albert | Charter Only | On Schedule | Advertised | Yes | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-06 |  | 2025-06-06 | 2022-11-30 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2024-11-25 | 2024-11-22 | 2024-11-22 | FY00 | Q3 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 |  | 5416000 |  | 5416000 |  | 7546000 |  | 7546000 | 1153000 | 5097250 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24048 | TBD | Point Loma Heights Improv 3 (W) | 2025-01-01 | TBD | Point Loma Heights Improv 3 (W) / B24048 | 2 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Famorcan, Ronald | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-11 |  | 2025-06-11 | 2025-05-27 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-01-02 |  | 2025-01-02 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 12780000 |  | 12780000 |  | 16535906 |  | 16535906 | 8487000 | 0 | 2.13 | 2.13 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B17143 | ACA00001 | Storm Drain Group 763 | 2025-01-01 | Flood Resilience Infrastructure / ACA00001 | Storm Drain Group 763 / B17143 | 7 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Meredith, William | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-30 |  | 2025-06-30 | 2020-12-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-01-21 |  | 2025-01-21 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 1056000 |  | 1056000 |  | 2011966 |  | 2011966 | 5000 | 1600166 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20047 | AKB00003 | Stockton Improv 2 (W) | 2025-01-01 | Main Replacements / AKB00003 | Stockton Improv 2 (W) / B20047 | 9 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-03-28 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-03-18 |  | 2025-03-18 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 10440000 |  | 10440000 |  | 12813300 |  | 12813300 | 4893300 | 0 | 1.92 | 1.92 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20048 | AJA00001 | Stockton Improv 2 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Stockton Improv 2 (S) / B20048 | 8, 9 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-13 |  | 2025-06-13 | 2025-03-28 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-03-18 |  | 2025-03-18 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 7980000 |  | 7980000 |  | 10289900 |  | 10289900 | 4762500 | 0 | 0 | 0 | 1.37 | 1.37 | No | No | No | No | No | No | No | No | No | No | Yes
B20037 | AKB00003 | Corridor Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Corridor Improv 1 (W) / B20037 | 9 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | Charter Only | On Schedule | Advertised | Yes |  |  |  |  | Added - Aug 1st |  |  |  |  | 2025-04-04 |  | 2025-04-04 | 2024-10-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2024-08-27 | 2024-08-27 | 2024-08-27 | FY00 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 |  | 14160600 |  | 14160600 |  | 17259200 |  | 17259200 | 14160600 | 0 | 3.26 | 3.26 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22146 | AAA00001 | 8690 Aero Drive Roof Replacement | 2025-01-01 | Montgomery Field / AAA00001 | 8690 Aero Drive Roof Replacement / B22146 | 7 | Airport | Quick Build | Airports | Facility & Parks Project Delivery | FPPD_Pk3 | Shackelford, Kris | Lewis, Yovanna | No Project Charter or Amendment | On Schedule | Advertised | Yes | Added - Sep 1st | [8 empty] | 2025-01-02 | 2025-01-02 | 2025-01-02 | 2024-12-19 | FY00 | Q3 | FY25 | Q3 | FY25 | Q3 | FY25 | Q3 |  | 2024-08-13 | 2024-08-13 | 2024-08-13 | FY00 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 |  | 662000 |  | 662000 |  | 805000 |  | 805000 | 450000 | 162000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20023 | AKB00003 | La Jolla Improv 3 (W) | 2025-01-01 | Main Replacements / AKB00003 | La Jolla Improv 3 (W) / B20023 | 1 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-23 |  | 2025-06-23 | 2024-01-02 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-02-03 |  | 2025-02-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 5000000 |  | 5000000 |  | 7210067 |  | 7210067 | 2795400 | 1681467 | 0.74 | 0.74 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B21097 | AKB00003 | Valencia Park Improv 4 (W) | 2025-01-01 | Main Replacements / AKB00003 | Valencia Park Improv 4 (W) / B21097 | 4 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Crespo, Santiago | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-04-11 | 2025-05-09 |  | 2025-05-09 | 2023-10-09 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-30 | 2024-09-20 | 2024-09-20 | 2024-09-20 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 387639.39 | 1329401 |  | 1329401 | 514800.39 | 1456562 |  | 1456562 | 231210 | 116500 | 0.12 | 0.12 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B22047 | AGF00007 | Clay Neighborhood Park Improvements | 2025-01-01 | Park Improvements / AGF00007 | Clay Neighborhood Park Improvements / B22047 | 9 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Marquez, Francis Albert | No Project Charter or Amendment | On Schedule | On Schedule | [5 empty] | Added - Aug 1st |  |  |  |  | 2025-06-16 |  | 2025-06-16 | 2025-02-11 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-03-03 |  | 2025-03-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 5657553 |  | 5657553 |  | 8301200 |  | 8301200 | 1907190 | 4485453 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22157 | AAA00001 | Terminal Parking Lot East Rehabilitation | 2025-01-01 | Montgomery Field / AAA00001 | Terminal Parking Lot East Rehabilitation / B22157 | 7 | Airport | Job Order Contract | Airports | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Castaneyra, Jose | Charter Only | On Schedule | On Schedule | [5 empty] | Added - Aug 1st |  |  |  |  | 2025-06-20 |  | 2025-06-20 | 2023-10-17 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-01-28 |  | 2025-01-28 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 885967 |  | 885967 |  | 1558347 |  | 1558347 | 409500 | 936347 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24149 | TBD | AC Overlay Group 2405 | 2025-01-01 | TBD | AC Overlay Group 2405 / B24149 | 6, 5 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | No Project Charter or Amendment | Awarded | Advertised |  | On Published List |  |  |  | On Published List |  |  |  | 2024-12-03 | 2024-08-13 | 2024-08-13 | 2024-08-13 | 2024-12-03 | FY25 | Q2 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 2024-10-01 | 2024-07-12 |  | 2024-07-12 | FY25 | Q2 | FY25 | Q1 |  |  | FY25 | Q1 | 4500000 | 4704021.73 |  | 4704021.73 | 6167000 | 6371021.73 |  | 6371021.73 | 4500000 | 204021.73 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
L24002.1 | TBD | NTC H-Barracks Shelter Project | 2025-01-01 | TBD | NTC H-Barracks Shelter Project / L24002.1 | 2 | Parks | Job Order Contract | Economic Development | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Le, Hong Khanh | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Sep 1st | [8 empty] | 2025-01-02 |  | 2025-01-02 | 2024-11-06 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 2024-10-01 |  | 2024-10-01 | FY00 | Q3 | FY25 | Q2 |  |  | FY25 | Q2 |  | 2681352 |  | 2681352 |  | 3478648 |  | 3478648 | 1800000 | 890000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25005 | TBD | AC Overlay Group 2505 | 2025-01-01 | TBD | AC Overlay Group 2505 / B25005 | 8 | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Oct 1st | [8 empty] | 2025-06-06 |  | 2025-06-06 | 2025-02-07 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-03-04 |  | 2025-03-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 8200000 |  | 8200000 |  | 8500000 |  | 8500000 | 0 | 8200000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25006 | TBD | AC Overlay Group 2506 | 2025-01-01 | TBD | AC Overlay Group 2506 / B25006 | 3 | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Oct 1st | [8 empty] | 2025-06-06 |  | 2025-06-06 | 2024-12-06 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-03-04 |  | 2025-03-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 6200000 |  | 6200000 |  | 6500000 |  | 6500000 | 0 | 6200000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25007 | TBD | AC Overlay Group 2507 | 2025-01-01 | TBD | AC Overlay Group 2507 / B25007 | 3, 8 | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Oct 1st | [8 empty] | 2025-06-06 |  | 2025-06-06 | 2025-02-07 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-03-04 |  | 2025-03-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 9000000 |  | 9000000 |  | 9300000 |  | 9300000 | 0 | 9000000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25019 | TBD | AC Overlay Group 2519 UUP | 2025-01-01 | TBD | AC Overlay Group 2519 UUP / B25019 | 1, 9 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Saleh, Aveen | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Oct 1st | [8 empty] | 2025-01-16 |  | 2025-01-16 | 2024-11-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 2024-09-04 |  | 2024-09-04 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 744131.56 |  | 744131.56 |  | 813746.37 |  | 813746.37 | 813746.37 | 162875.62 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25024 | TBD | Pump Station B SD Rehab Emergency | 2025-01-01 | TBD | Pump Station B SD Rehab Emergency / B25024 | 2 | Storm Water Drainage | Sole Source Emergency | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Pan, Junmin | No Project Charter or Amendment | Awarded | Advertised |  | Added - Sep 1st | [8 empty] | 2024-07-22 | 2024-07-22 | 2024-07-22 | 2024-07-22 | FY00 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 |  | 2024-07-22 |  | 2024-07-22 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 1500000 |  | 1500000 |  | 2000000 |  | 2000000 | 1500000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22012 | AGF00006 | Old Salt Pool Access Stairs | 2025-01-01 | Coastal Erosion and Access / AGF00006 | Old Salt Pool Access Stairs / B22012 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | Afagh, Negin | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-01-07 | 2025-02-18 |  | 2025-02-18 | 2024-10-03 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-08-30 | 2025-02-03 |  | 2025-02-03 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 449598 | 853807.73 |  | 853807.73 | 1198000 | 1623018.77 |  | 1623018.77 | 449598 | 425018.77 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B24012 | TBD | AC Overlay Group 2402 | 2025-01-01 | TBD | AC Overlay Group 2402 / B24012 | 1, 6, 5, 2 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Chan, Chun Yu | No Project Charter or Amendment | Awarded | Advertised |  | On Published List | [7 empty] | 2025-01-03 | 2024-10-11 | 2024-10-11 | 2024-10-11 | 2024-08-23 | FY25 | Q3 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2024-06-25 | 2024-06-25 | 2024-09-12 | 2024-09-12 | FY24 | Q4 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 | 16000000 | 16488929.85 | 13748929.85 | 13748929.85 | 21420000 | 23000000 |  | 23000000 | 11413500 | 6695000 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B25048 | TBD | AC Overlay Group 2510 | 2025-01-01 | TBD | AC Overlay Group 2510 / B25048 | 7 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Mills, Amy | No Project Charter or Amendment | On Schedule | On Schedule | [5 empty] | Added - Oct 1st |  |  |  |  | 2025-06-02 |  | 2025-06-02 | 2025-09-02 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-03-28 |  | 2025-03-28 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 4377250 |  | 4377250 |  | 5185000 |  | 5185000 | 4377250 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25028 | TBD | 5989 San Dimas Ave USD SD Emergency | 2025-01-01 | TBD | 5989 San Dimas Ave USD SD Emergency / B25028 | 7 | Storm Water Drainage | Sole Source Emergency | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Cramoline, Jeff | No Project Charter or Amendment | Awarded | Advertised |  | Added - Nov 1st | [8 empty] | 2024-07-25 |  | 2024-07-25 | 2024-07-25 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 2024-07-25 |  | 2024-07-25 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 2700000 |  | 2700000 |  | 4000000 |  | 4000000 | 2700000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25060 | TBD | Block 1M Nautilus St (BL) | 2025-01-01 | TBD | Block 1M Nautilus St (BL) / B25060 | 1 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Saleh, Aveen | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Nov 1st | [8 empty] | 2025-01-16 |  | 2025-01-16 | 2024-11-21 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 2024-09-05 |  | 2024-09-05 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 223001.89 |  | 223001.89 |  | 223001.89 |  | 223001.89 | 118000 | 105001.89 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24043 | TBD | Citywide Referral Rehab 1 (S) | 2025-01-01 | TBD | Citywide Referral Rehab 1 (S) / B24043 | 1, 6, 8, 5, 2 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Valadez, Roberto | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-04-16 | 2025-06-02 |  | 2025-06-02 | 2025-04-01 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-10-17 | 2024-11-19 | 2024-11-14 | 2024-11-14 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 2205000 | 2452136 |  | 2452136 | 3394000 | 3789971.7425 |  | 3789971.7425 | 2205000 | 0 | 0 | 0 | 1.01 | 1.01 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18140 | AID00001 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Mission Bl(Loring-Turquoise) Rd Imp UU30 / B18140 | 1 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-11-06 | 2025-06-25 |  | 2025-06-25 | 2020-06-01 | FY25 | Q2 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-05 | 2025-01-15 |  | 2025-01-15 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 1550000 | 809552 |  | 809552 | 2258546 | 1149552 |  | 1149552 | 170777 | 919003.05 | 0 | 0 | 0 | 0 | Yes | No | Yes | Yes | Yes | Yes | No | No | No | No | Yes
B18148 | AID00001 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 / B18148 | 1 | Utility Undergrounding | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2024-11-06 | 2025-06-25 |  | 2025-06-25 | 2020-12-01 | FY25 | Q2 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-05 | 2025-01-15 |  | 2025-01-15 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 703750 | 912066.57 |  | 912066.57 | 915674.1 | 1528990.67 |  | 1528990.67 | 109924 | 1388415.67 | 0 | 0 | 0 | 0 | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B18137 | AID00001 | Coronado SB (27th SB-Madden)Rd Imp UU193 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Coronado SB (27th SB-Madden)Rd Imp UU193 / B18137 | 8 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-07 | 2025-06-10 |  | 2025-06-10 | 2020-12-01 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-24 | 2025-01-02 |  | 2025-01-02 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 895391.93 | 339000 |  | 339000 | 1136146 | 716754.07 |  | 716754.07 | 268212.8 | 355551.07 | 0 | 0 | 0 | 0 | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B18144 | AID00001 | 32nd St PH I (Market-F St) Rd Imp UU386 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | 32nd St PH I (Market-F St) Rd Imp UU386 / B18144 | 9 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter & Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-07 | 2025-06-30 |  | 2025-06-30 | 2020-12-01 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-24 | 2025-01-03 |  | 2025-01-03 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 502852.45 | 168500 |  | 168500 | 649448.45 | 683096 |  | 683096 | 124122.35 | 496407 | 0 | 0 | 0 | 0 | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B18147 | AID00001 | 31st Street (Market-L St) Rd Imp UU11 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | 31st Street (Market-L St) Rd Imp UU11 / B18147 | 9 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-07 | 2025-06-30 |  | 2025-06-30 | 2020-12-01 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-24 | 2025-01-02 |  | 2025-01-02 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 614250 | 459000 |  | 459000 | 890845.78 | 954595.78 |  | 954595.78 | 286745 | 533893.78 | 0 | 0 | 0 | 0 | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B18150 | AID00001 | 25th (SB) (Coronado-Grove) Rd Imp UU995 | 2025-01-01 | Utilities Undergrounding Program / AID00001 | 25th (SB) (Coronado-Grove) Rd Imp UU995 / B18150 | 8 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Valenzuela, Farlito | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-07 | 2025-06-30 |  | 2025-06-30 | 2020-12-01 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-09-24 | 2025-01-03 |  | 2025-01-03 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 177537 | 68000 |  | 68000 | 300000 | 510213 |  | 510213 | 88173 | 387452 | 0 | 0 | 0 | 0 | Yes | No | Yes | No | Yes | No | No | No | No | No | Yes
B24135 | TBD | Mission Blvd South Loring Overlay | 2025-01-01 | TBD | Mission Blvd South Loring Overlay / B24135 | 1 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Aug 1st |  |  |  | Added - Aug 1st |  |  |  |  | 2025-06-25 |  | 2025-06-25 | 2025-07-11 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-01-15 |  | 2025-01-15 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 654293 |  | 654293 |  | 1145000 |  | 1145000 | 448825 | 371175 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22003 | AKB00003 | Ocean Beach Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Ocean Beach Improv 1 (W) / B22003 | 2 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | Charter Only | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-03-10 | 2025-06-05 |  | 2025-06-05 | 2025-07-01 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-01 | 2024-11-26 | 2024-11-20 | 2024-11-20 | FY25 | Q1 | FY25 | Q2 | FY25 | Q2 | FY25 | Q2 | 1698246.41 | 2227783 |  | 2227783 | 2342646.41 | 3744783 |  | 3744783 | 844200 | 2348183 | 0.35 | 0.35 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18112 | AJA00001 | Sewer & AC Water Group 1055 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Sewer & AC Water Group 1055 (S) / B18112 | 3 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-04-14 | 2025-06-04 |  | 2025-06-04 | 2023-07-03 | FY25 | Q4 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-10-04 | 2025-03-13 |  | 2025-03-13 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 4475700 | 4475700 |  | 4475700 | 6646500 | 6646500 |  | 6646500 | 4475700 | 0 | 0 | 0 | 1.98 | 1.98 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B25026 | TBD | Pacific Highway 8-in Swr Repl Emergency | 2025-01-01 | TBD | Pacific Highway 8-in Swr Repl Emergency / B25026 | 2 | Sewer | Sole Source Emergency | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Gonzalez, Manuel | No Project Charter or Amendment | Awarded | Advertised |  | Added - Oct 1st | [8 empty] | 2024-07-11 | 2024-07-11 | 2024-07-11 | 2024-07-11 | FY00 | Q3 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 |  | 2024-07-11 |  | 2024-07-11 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 1500000 |  | 1500000 |  | 1800000 |  | 1800000 | 1500000 | 0 | 0 | 0 | 0.06 | 0.06 | No | No | No | No | No | No | No | No | No | No | Yes
B24137 | TBD | Roswell Street Overlay | 2025-01-01 | TBD | Roswell Street Overlay / B24137 | Geo-Mapping is in progress | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Sherzai, Hossai | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Dec 1st | [8 empty] | 2025-05-29 |  | 2025-05-29 | 2025-05-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-03-03 |  | 2025-03-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 400000 |  | 400000 |  | 710000 |  | 710000 |  |  | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25045 | TBD | 6790 Friars Rd SD Emergency | 2025-01-01 | TBD | 6790 Friars Rd SD Emergency / B25045 | 7 | Storm Water Drainage | Emergency (As-needed) | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Delgado, Carolina | No Project Charter or Amendment | Awarded | Advertised |  | Added - Dec 1st | [8 empty] | 2024-07-30 |  | 2024-07-30 | 2024-07-30 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 2025-01-02 |  | 2025-01-02 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 2500000 |  | 2500000 |  | 3000000 |  | 3000000 |  |  | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23049 | ABI00001 | Miramar WTP Interim Solids Management | 2025-01-01 | Water Treatment Plants / ABI00001 | Miramar WTP Interim Solids Management / B23049 | 5 | Water | Design Bid Build | Public Utilities | Strategic Capital Projects | SCP | Ammerlahn, Parita | Yoshioka, Ryo | No Project Charter or Amendment | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-01-03 | 2025-03-19 |  | 2025-03-19 | 2025-04-08 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-08-01 | 2024-08-01 |  | 2024-08-01 | FY25 | Q1 | FY25 | Q1 |  |  | FY25 | Q1 | 4409785 | 4409785 |  | 4409785 | 5612453 | 5612453 |  | 5612453 | 2000000 | 3015565 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B23014 | ABI00001 | Miramar WTP Caustic Pumping System | 2025-01-01 | Water Treatment Plants / ABI00001 | Miramar WTP Caustic Pumping System / B23014 | 5 | Water | Design Bid Build | Public Utilities | Strategic Capital Projects | SCP | Ammerlahn, Parita | Yoshioka, Ryo | No Project Charter or Amendment | On Schedule | Advertised | Yes | On Published List |  |  |  | On Published List |  |  |  | 2025-03-20 | 2025-03-19 |  | 2025-03-19 | 2024-09-30 | FY25 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 | 2024-09-19 | 2024-09-23 | 2024-09-23 | 2024-09-23 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | FY25 | Q1 | 600000 | 600000 |  | 600000 | 1678250 | 1678250 |  | 1678250 | 1200000 | -755288 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B20148 | ABO00001 | NCWRP - Chiller Replacement | 2025-01-01 | Metro Treatment Plants / ABO00001 | NCWRP - Chiller Replacement / B20148 | 6 | Sewer | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Rivera, Jacob | Charter Only | On Schedule | On Schedule |  | On Published List |  |  |  | On Published List |  |  |  | 2025-03-12 | 2025-05-08 |  | 2025-05-08 | 2022-03-01 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2024-08-29 | 2025-02-03 |  | 2025-02-03 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 3065384.86 | 2100000 |  | 2100000 | 3705120.86 | 3300000 |  | 3300000 | 1186900 | 2091520.86 | 0 | 0 | 0 | 0 | Yes | No | No | Yes | No | No | No | No | No | No | Yes
B22020 | AKB00003 | Fairmount Park Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Fairmount Park Improv 1 (W) / B22020 | 9 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | Charter Only | On Schedule | On Schedule | [5 empty] | Added - Aug 1st |  |  |  |  | 2025-06-27 |  | 2025-06-27 | 2025-04-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-02-20 |  | 2025-02-20 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3237120 |  | 3237120 |  | 5414070 |  | 5414070 | 3237120 | 191770 | 1.08 | 1.08 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25044 | TBD | 1655 S 32nd St SD Emergency | 2025-01-01 | TBD | 1655 S 32nd St SD Emergency / B25044 | Geo-Mapping is in progress | Storm Water Drainage | Emergency (As-needed) | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Delgado, Carolina | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Jan 1st | [8 empty] | 2024-09-19 |  | 2024-09-19 | 2024-09-19 | FY00 | Q3 | FY25 | Q1 |  |  | FY25 | Q1 |  | 2024-12-31 |  | 2024-12-31 | FY00 | Q3 | FY25 | Q2 |  |  | FY25 | Q2 |  | 3000000 |  | 3000000 |  | 3500000 |  | 3500000 |  |  | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25074 | TBD | Madrone Ave Pipe Replacement | 2025-01-01 | TBD | Madrone Ave Pipe Replacement / B25074 | Geo-Mapping is in progress | Water | Job Order Contract | Public Utilities | Project Management Office | PMO_ACP | Veverka, Matthew | Tadros, Gehan | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Jan 1st | [8 empty] | 2025-04-24 |  | 2025-04-24 | 2025-04-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2025-03-26 |  | 2025-03-26 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 270000 |  | 270000 |  | 450000 |  | 450000 |  |  | 0 | 0.17 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25078 | TBD | 2650 Broadway St Emergency Replacement | 2025-01-01 | TBD | 2650 Broadway St Emergency Replacement / B25078 | Geo-Mapping is in progress | Storm Water Drainage | Sole Source Emergency | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Leon, Heidi | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Jan 1st | [8 empty] | 2024-10-22 |  | 2024-10-22 | 2024-10-22 | FY00 | Q3 | FY25 | Q2 |  |  | FY25 | Q2 |  | 2024-10-24 |  | 2024-10-24 | FY00 | Q3 | FY25 | Q2 |  |  | FY25 | Q2 |  | 1900000 |  | 1900000 |  | 2000000 |  | 2000000 |  |  | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S24012 | TBD | 14th Street Greenway Block #2 | 2025-01-01 | TBD | 14th Street Greenway Block #2 / S24012 | Geo-Mapping is in progress | Transportation | Design Bid Build | Transportation | Development Services Department | DSD | Schoenfisch, Brian | Schoenfisch, Brian | No Project Charter or Amendment | On Schedule | On Schedule |  | Added - Jan 1st | [8 empty] | 2025-04-01 |  | 2025-04-01 | 2025-04-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2024-10-01 |  | 2024-10-01 | FY00 | Q3 | FY25 | Q2 |  |  | FY25 | Q2 |  | 2566733.75 |  | 2566733.75 |  | 3101825 |  | 3101825 |  |  | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S20012 | S20012 | Chollas Creek Oak Park Trail | 2025-01-01 | Chollas Creek Oak Park Trail / S20012 | Chollas Creek Oak Park Trail / S20012 | 9, 4 | Parks | Design Build | Parks & Recreation | City Planning | PLANNING | Busby, Breanne | Busby, Breanne | No Project Charter or Amendment | Removed | Removed |  | Added - Aug 1st | FY26 |  |  |  | FY00 |  | Removed - Aug 1st |  | 2025-12-04 |  | 2025-12-04 | 2024-08-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 0 |  | 0 | FY00 | Q3 | FY00 | Q3 |  |  | FY00 | Q3 |  | 2380000 |  | 2380000 |  | 4111500 |  | 4111500 | 1992000 | 1143000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B18089 | AKB00003 | AC Water & Sewer Group 1049 (W) | 2025-01-01 | Main Replacements / AKB00003 | AC Water & Sewer Group 1049 (W) / B18089 | 6, 7, 2 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Gallardo, Jericho | Charter Only | Removed | Removed | Yes | On Published List | FY26 |  |  |  | FY24 |  | Removed - Aug 1st | 2024-12-19 | 2026-05-18 |  | 2026-05-18 | 2021-11-08 | FY25 | Q2 | FY26 | Q4 |  |  | FY26 | Q4 | 2024-06-28 | 2025-01-02 | 2024-06-28 | 2024-06-28 | FY24 | Q4 | FY25 | Q3 | FY24 | Q4 | FY24 | Q4 | 6018669.13 | 27473695.5 |  | 27473695.5 | 9605802.59 | 32161275.5 |  | 32161275.5 | 8503100 | 19527075.5 | 4.65 | 4.65 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18097 | AJA00001 | AC Water & Sewer Group 1049 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | AC Water & Sewer Group 1049 (S) / B18097 | 6, 7 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Gallardo, Jericho | Charter Only | Removed | Removed | Yes | On Published List | FY26 |  |  |  | FY24 |  | Removed - Aug 1st | 2024-12-19 | 2026-05-18 |  | 2026-05-18 | 2021-11-08 | FY25 | Q2 | FY26 | Q4 |  |  | FY26 | Q4 | 2024-07-01 | 2025-01-02 | 2024-06-28 | 2024-06-28 | FY25 | Q1 | FY25 | Q3 | FY24 | Q4 | FY24 | Q4 | 27204758.42 | 4278660.5 |  | 4278660.5 | 29393096.34 | 6018031.72 |  | 6018031.72 | 2394400 | 2551031.72 | 0 | 0 | 1.08 | 1.08 | Yes | No | No | No | No | No | No | No | No | No | Yes
B21049 | AKB00003 | Normal Heights Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Normal Heights Improv 1 (W) / B21049 | 9 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Zare Afifi, Mehrnaz | Charter Only | Removed | Advertised | Yes | On Published List | FY26 | [6 empty] | 2025-01-07 | 2025-08-29 |  | 2025-08-29 | 2024-08-12 | FY25 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-06-27 | 2024-06-27 | 2024-09-24 | 2024-09-24 | FY24 | Q4 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 | 23670211 | 37260018 |  | 37260018 | 27689811 | 41279618 |  | 41279618 | 8926700 | 28400618 | 3.71 | 3.71 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B21048 | AJA00001 | Normal Heights Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Normal Heights Improv 1 (S) / B21048 | 9 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Zare Afifi, Mehrnaz | Charter Only | Removed | Advertised | Yes | On Published List | FY26 | [6 empty] | 2025-01-07 | 2025-08-29 |  | 2025-08-29 | 2024-08-19 | FY25 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-06-27 | 2024-06-27 | 2024-09-24 | 2024-09-24 | FY24 | Q4 | FY24 | Q4 | FY25 | Q1 | FY25 | Q1 | 3300799 | 3832455 |  | 3832455 | 4149799 | 4681455 |  | 4681455 | 1685700 | 2110155 | 0 | 0 | 0.63 | 0.63 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B20128 | AKB00003 | Morena Improv 2 (w) | 2025-01-01 | Main Replacements / AKB00003 | Morena Improv 2 (w) / B20128 | 3, 7 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Famorcan, Ronald | Charter Only | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-03-27 | 2025-07-07 |  | 2025-07-07 | 2023-10-02 | FY25 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-09-24 | 2025-01-02 |  | 2025-01-02 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 5672400 | 7281345 |  | 7281345 | 8445800 | 10142045 |  | 10142045 | 5672400 | 87300 | 2.79 | 2.79 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
S14006 | S14006 | El Cuervo Adobe Improvements | 2025-01-01 | El Cuervo Adobe Improvements / S14006 | El Cuervo Adobe Improvements / S14006 | 1 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Stoks, Shannon | Charter Only | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-01-02 | 2025-07-08 |  | 2025-07-08 | 2016-08-22 | FY25 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-10-02 | 2025-04-08 |  | 2025-04-08 | FY25 | Q2 | FY25 | Q4 |  |  | FY25 | Q4 | 353480 | 292315 |  | 292315 | 606000 | 926155 |  | 926155 | 126000 | 258782.6 | 0 | 0 | 0 | 0 | Yes | No | No | Yes | Yes | No | Yes | Yes | Yes | No | Yes
S16032 | S16032 | Solana Highlands NP-Comfort Station | 2025-01-01 | Solana Highlands NP-Comfort Station Development / S16032 | Solana Highlands NP-Comfort Station / S16032 | 1 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Tobchi, Rawan | Charter & Amendment | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-01-31 | 2025-07-24 |  | 2025-07-24 | 2021-09-15 | FY25 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-08-13 | 2025-02-04 |  | 2025-02-04 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 2554900 | 4161200 |  | 4161200 | 4031000 | 5833600 |  | 5833600 | 967000 | 2140000 | 0 | 0 | 0 | 0 | Yes | Yes | Yes | Yes | No | Yes | No | No | No | No | Yes
B20133 | AJA00001 | Morena Improv 2 (s) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Morena Improv 2 (s) / B20133 | 7, 2 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Famorcan, Ronald | Charter Only | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-03-27 | 2025-07-07 |  | 2025-07-07 | 2023-10-02 | FY25 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-09-24 | 2025-01-02 |  | 2025-01-02 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 1893100 | 1986007 |  | 1986007 | 2865600 | 3077007 |  | 3077007 | 1893100 | 221500 | 0 | 0 | 0.51 | 0.51 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18104 | AKB00003 | Alvarado TS Water Main Relocations | 2025-01-01 | Main Replacements / AKB00003 | Alvarado TS Water Main Relocations / B18104 | 7 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  |  | Added - Aug 1st |  |  |  |  | 2025-07-15 |  | 2025-07-15 | 2020-04-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-02 |  | 2025-01-02 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 9403562 |  | 9403562 |  | 10903273 |  | 10903273 | 1225100 | 9239773 | 1.38 | 1.38 | 0 | 0 | No | No | No | No | Yes | Yes | No | No | No | No | Yes
B22002 | ABL00001 | SV Dam Low Level Outlet Improvements | 2025-01-01 | Standpipe & Reservoir Rehabilitations / ABL00001 | SV Dam Low Level Outlet Improvements / B22002 | Project outside of City limits | Water | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Rivera, Jacob | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  |  | Added - Aug 1st |  |  |  |  | 2025-08-12 |  | 2025-08-12 | 2024-01-11 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-03 |  | 2025-02-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3000000 |  | 3000000 |  | 5366554.94 |  | 5366554.94 | 1210400 | 3311254.94 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S15019 | S15019 | Alvarado Trunk Sewer Phase IV | 2025-01-01 | Alvarado Trunk Sewer Phase IV / S15019 | Alvarado Trunk Sewer Phase IV / S15019 | 7, 9 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | Charter & Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-07-15 |  | 2025-07-15 | 2020-04-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-02 |  | 2025-01-02 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 54300000 |  | 54300000 |  | 72349085 |  | 72349085 | 17279200 | 46642935 | 0 | 0 | 5.01 | 5.01 | No | No | No | No | Yes | Yes | No | No | No | No | Yes
B22017 | ABL00001 | San Vicente Drainage Improvements | 2025-01-01 | Standpipe & Reservoir Rehabilitations / ABL00001 | San Vicente Drainage Improvements / B22017 | Project outside of City limits | Water | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Rivera, Jacob | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st |  |  |  |  | 2025-08-11 |  | 2025-08-11 | 2024-12-10 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-13 |  | 2025-02-13 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 1919270 |  | 1919270 |  | 3191710 |  | 3191710 | 480600 | 2358710 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B18012 | AIH00001 | Citywide Street Lights Group 1801 | 2025-01-01 | Installation of City Owned Street Lights / AIH00001 | Citywide Street Lights Group 1801 / B18012 | 7 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-07-16 |  | 2025-07-16 | 2019-03-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-03 |  | 2025-01-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 162762 |  | 162762 |  | 400000 |  | 400000 | 99463 | 200000 | 0 | 0 | 0 | 0 | No | Yes | Yes | No | No | No | No | No | No | No | Yes
B24033 | TBD | North Park Improv 4 (S) | 2025-01-01 | TBD | North Park Improv 4 (S) / B24033 | 3 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Melo Rodriguez, Pedro | No Project Charter or Amendment | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-02-25 | 2025-08-28 |  | 2025-08-28 | 2025-04-01 | FY25 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-08-14 | 2025-02-19 |  | 2025-02-19 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 2698000 | 3300000 |  | 3300000 | 4110000 | 5021931 |  | 5021931 | 2698000 | 0 | 0 | 0 | 1.46 | 1.46 | Yes | No | No | No | No | No | No | No | No | No | Yes
B22080 | ABT00001 | Police HQ Security Fencing | 2025-01-01 | City Facility Improvements / ABT00001 | Police HQ Security Fencing / B22080 | 3 | Buildings | Design Bid Build | General Services | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Castaneyra, Jose | Charter Only | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-04-03 | 2025-07-29 |  | 2025-07-29 | 2023-11-16 | FY25 | Q4 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-11-01 | 2025-04-08 |  | 2025-04-08 | FY25 | Q2 | FY25 | Q4 |  |  | FY25 | Q4 | 1588000 | 1588000 |  | 1588000 | 2514350 | 2514350 |  | 2514350 | 433000 | 1538350 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B18115 | AKB00003 | Sewer & AC Water Group 1055 (W) | 2025-01-01 | Main Replacements / AKB00003 | Sewer & AC Water Group 1055 (W) / B18115 | 3 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | Charter Only | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-04-14 | 2025-07-08 |  | 2025-07-08 | 2023-07-03 | FY25 | Q4 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-10-04 | 2025-03-14 |  | 2025-03-14 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 2509000 | 2509000 |  | 2509000 | 3725900 | 3924495 |  | 3924495 | 2509000 | 198595 | 1.19 | 1.19 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B23012 | AAA00001 | West Ramp Spider Hanger Rehabilitation | 2025-01-01 | Montgomery Field / AAA00001 | West Ramp Spider Hanger Rehabilitation / B23012 | 7 | Airport | Job Order Contract | Airports | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Castaneyra, Jose | No Project Charter or Amendment | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st |  |  |  |  | 2025-07-17 |  | 2025-07-17 | 2023-10-17 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-06 |  | 2025-01-06 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 1143339 |  | 1143339 |  | 2073342 |  | 2073342 | 402300 | 1466342 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S00869 | S00869 | Palm Avenue Interstate 805 Interchange | 2025-01-01 | Palm Avenue Interstate 805 Interchange / S00869 | Palm Avenue Interstate 805 Interchange / S00869 | 8 | Transportation | Agency/ Developer Managed Built - City Paid | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter Amendment Only | Removed | On Schedule |  | On Published List | FY26 |  | Removed - Dec 1st | On Published List |  |  |  | 2024-12-09 | 2025-09-17 |  | 2025-09-17 | 2023-11-17 | FY25 | Q2 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-07-30 | 2025-01-21 |  | 2025-01-21 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 31308867 | 31500000 |  | 31500000 | 49320372.53 | 51730633.53 |  | 51730633.53 | 23356000 | 11698392.53 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
S00995 | S00995 | HIDDEN TRAILS NEIGHBORHOOD PARK | 2025-01-01 | Hidden Trails Neighborhood Park / S00995 | HIDDEN TRAILS NEIGHBORHOOD PARK / S00995 | 8 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Chan, Ling | Charter Only | Removed | On Schedule |  | On Published List | FY26 |  | Removed - Dec 1st | On Published List |  |  |  | 2025-04-09 | 2025-08-26 |  | 2025-08-26 | 2020-12-01 | FY25 | Q4 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-10-28 | 2025-01-23 |  | 2025-01-23 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 7638107.4 | 8260632 |  | 8260632 | 11313196 | 12577229.6 |  | 12577229.6 | 3272000 | 6080703 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B19049 | AIG00001 | Camino Del Rio West & Moore St Median | 2025-01-01 | Median Installation / AIG00001 | Camino Del Rio West & Moore St Median / B19049 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Meredith, William | No Project Charter or Amendment | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Dec 1st | Added - Aug 1st |  |  |  |  | 2025-07-14 |  | 2025-07-14 | 2022-09-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-03 |  | 2025-02-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 1872242 |  | 1872242 |  | 2615627 |  | 2615627 | 1189000 | 104185 | 0 | 0 | 0 | 0 | No | Yes | Yes | No | No | No | No | No | No | No | Yes
B23110 | ABL00001 | Black Mountain Reservoir Spillway Stairs | 2025-01-01 | Standpipe & Reservoir Rehabilitations / ABL00001 | Black Mountain Reservoir Spillway Stairs / B23110 | 5 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_EDP | Choi, Jong | Pan, Junmin | No Project Charter or Amendment | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Dec 1st | Added - Aug 1st |  |  |  |  | 2025-08-20 |  | 2025-08-20 | 2025-11-03 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-19 |  | 2025-02-19 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 350000 |  | 350000 |  | 700000 |  | 700000 | 229000 | 198000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20001 | ABO00001 | STORM WATER DIVERSION AT THE PLWTP | 2025-01-01 | Metro Treatment Plants / ABO00001 | STORM WATER DIVERSION AT THE PLWTP / B20001 | 2 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_Dams | Van Martin, Debbie | McMullen, Sara | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Dec 1st | Added - Aug 1st |  |  |  |  | 2025-07-31 |  | 2025-07-31 | 2022-05-02 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-04-01 |  | 2025-04-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 8756775 |  | 8756775 |  | 12922725 |  | 12922725 | 3100300 | 7714125 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B16094 | ACA00001 | Jamacha Lomita Storm Drain | 2025-01-01 | Flood Resilience Infrastructure / ACA00001 | Jamacha Lomita Storm Drain / B16094 | 4 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Shamoun, Ikhlass | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Dec 1st | Added - Aug 1st |  |  |  |  | 2025-08-14 |  | 2025-08-14 | 2019-07-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-04 |  | 2025-02-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3462881.5 |  | 3462881.5 |  | 6023703.4 |  | 6023703.4 | 0 | 4619302.8 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19119 | AKB00003 | AC Water & Sewer Group 1054A (W) | 2025-01-01 | Main Replacements / AKB00003 | AC Water & Sewer Group 1054A (W) / B19119 | 9, 4 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Dec 1st | Added - Aug 1st |  |  |  |  | 2025-07-30 |  | 2025-07-30 | 2023-04-03 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-13 |  | 2025-02-13 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 1979800 |  | 1979800 |  | 3095205.69 |  | 3095205.69 | 1979800 | 0 | 1.37 | 1.37 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19121 | AJA00001 | AC Water & Sewer Group 1054A (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | AC Water & Sewer Group 1054A (S) / B19121 | 9, 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Dec 1st | Added - Aug 1st |  |  |  |  | 2025-08-25 |  | 2025-08-25 | 2023-04-03 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-13 |  | 2025-02-13 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 1075000 |  | 1075000 |  | 1576600 |  | 1576600 | 1075000 | 0 | 0 | 0 | 0.06 | 0.06 | No | No | No | No | No | No | No | No | No | No | Yes
B21075 | AJA00001 | Valencia Park Improv 3 (s) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Valencia Park Improv 3 (s) / B21075 | 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Zare Afifi, Mehrnaz | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Dec 1st | Added - Aug 1st |  |  |  |  | 2025-07-30 |  | 2025-07-30 | 2024-05-14 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-03-19 |  | 2025-03-19 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3540000 |  | 3540000 |  | 4606700 |  | 4606700 | 3540000 | 0 | 0 | 0 | 0.6 | 0.6 | No | No | No | No | No | No | No | No | No | No | Yes
B20085 | AJA00001 | College West Improv 3 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | College West Improv 3 (S) / B20085 | 9 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Dec 1st | Added - Aug 1st |  |  |  |  | 2025-08-15 |  | 2025-08-15 | 2024-01-05 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-10 |  | 2025-02-10 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 8048000 |  | 8048000 |  | 11509000 |  | 11509000 | 8048000 | 0 | 0 | 0 | 1.6 | 1.6 | No | No | No | No | No | No | No | No | No | No | Yes
B20132 | AJA00001 | Valencia Park Improv 2 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Valencia Park Improv 2 (S) / B20132 | 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Dec 1st | Added - Aug 1st |  |  |  |  | 2025-08-26 |  | 2025-08-26 | 2024-08-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-14 |  | 2025-02-14 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 5732190 |  | 5732190 |  | 9187500 |  | 9187500 | 5732190 | 0 | 0 | 0 | 2.4 | 2.4 | No | No | No | No | No | No | No | No | No | No | Yes
B18191 | AJA00001 | Sewer & AC Water Group 1058 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Sewer & AC Water Group 1058 (S) / B18191 | 1, 2 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | Charter Only | Removed | On Schedule |  | Added - Oct 1st | FY26 |  | Removed - Dec 1st | [5 empty] | 2025-08-15 |  | 2025-08-15 | 2024-05-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-03-10 |  | 2025-03-10 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3839400 |  | 3839400 |  | 5887767 |  | 5887767 | 3839400 | 256567 | 0 | 0 | 1.22 | 1.22 | No | No | No | No | No | No | No | No | No | No | Yes
B18193 | AKB00003 | Sewer & AC Water Group 1058 (W) | 2025-01-01 | Main Replacements / AKB00003 | Sewer & AC Water Group 1058 (W) / B18193 | 1 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | Charter Only | Removed | On Schedule |  | Added - Oct 1st | FY26 |  | Removed - Dec 1st | [5 empty] | 2025-08-14 |  | 2025-08-14 | 2024-05-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-03-07 |  | 2025-03-07 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3107700 |  | 3107700 |  | 4200000 |  | 4200000 | 1079100 | 588698 | 0.49 | 0.49 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20084 | AKB00003 | College West Improv 3 (W) | 2025-01-01 | Main Replacements / AKB00003 | College West Improv 3 (W) / B20084 | 9 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st |  |  |  |  | 2025-08-15 |  | 2025-08-15 | 2024-01-05 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-07 |  | 2025-02-07 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 1774000 |  | 1774000 |  | 2536000 |  | 2536000 | 1774000 | 0 | 0.68 | 0.68 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20135 | AKB00003 | Valencia Park Improv 2 (W) | 2025-01-01 | Main Replacements / AKB00003 | Valencia Park Improv 2 (W) / B20135 | 4 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st |  |  |  |  | 2025-08-26 |  | 2025-08-26 | 2024-08-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-14 |  | 2025-02-14 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3857130 |  | 3857130 |  | 6155600 |  | 6155600 | 3857130 | 0 | 2.03 | 2.03 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20122 | ABO00001 | SBWRP Reverse Osmosis System | 2025-01-01 | Metro Treatment Plants / ABO00001 | SBWRP Reverse Osmosis System / B20122 | 8 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Torres, Gabriel | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  |  | Added - Aug 1st |  |  |  |  | 2025-09-22 |  | 2025-09-22 | 2023-09-19 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-05-16 |  | 2025-05-16 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 19000000 |  | 19000000 |  | 28238384 |  | 28238384 | 8500000 | 15169426 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19071 | AIL00005 | Traffic Signal Mods Grp 19-02 | 2025-01-01 | Traffic Signals - Modify & Modernize / AIL00005 | Traffic Signal Mods Grp 19-02 / B19071 | 2 | Transportation | Design Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Kim, Jinsil | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  |  | Added - Aug 1st |  |  |  |  | 2025-08-28 |  | 2025-08-28 | 2022-09-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-31 |  | 2025-01-31 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 380350 |  | 380350 |  | 850000 |  | 850000 | 594500 | -64150 | 0 | 0 | 0 | 0 | No | No | Yes | No | No | No | No | No | No | No | Yes
B15097 | AID00001 | Block 8R UUP - CIP | 2025-01-01 | Utilities Undergrounding Program / AID00001 | Block 8R UUP - CIP / B15097 | 8 | Utility Undergrounding | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  |  | Added - Aug 1st |  |  |  |  | 2025-11-14 |  | 2025-11-14 | 2019-06-03 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-05-07 |  | 2025-05-07 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 1114000 |  | 1114000 |  | 1464000 |  | 1464000 | 4280026 | -4706626 | 0 | 0 | 0 | 0 | No | No | No | Yes | Yes | Yes | Yes | No | No | No | Yes
B23031 | AFA00001 | Miramar Pl Fleet Main Facility Upgrade | 2025-01-01 | Minor Improvements to Landfills / AFA00001 | Miramar Pl Fleet Main Facility Upgrade / B23031 | 6 | Buildings | Job Order Contract | Environmental Services | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Getz, Shannon | No Project Charter or Amendment | Removed | On Schedule |  | Added - Aug 1st | FY26 |  |  | Added - Aug 1st |  |  |  |  | 2025-10-02 |  | 2025-10-02 | 2024-05-17 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-30 |  | 2025-06-30 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 853260 |  | 853260 |  | 1333242.23 |  | 1333242.23 | 553500 | 603242.23 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B16158 | AKA00003 | Otay 2nd Pipeline Phase 3 | 2025-01-01 | Large Diameter Water Transmission PPL / AKA00003 | Otay 2nd Pipeline Phase 3 / B16158 | Project outside of City limits | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F1 | Vitelle, Brian | Salha, Rawsan | Charter Only | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-03-14 | 2025-12-09 |  | 2025-12-09 | 2020-10-01 | FY25 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 | 2024-09-03 | 2025-05-30 |  | 2025-05-30 | FY25 | Q1 | FY25 | Q4 |  |  | FY25 | Q4 | 15000000 | 28600000 |  | 28600000 | 25422257 | 42266000 |  | 42266000 | 10116000 | 29630000 | 0.64 | 0.64 | 0 | 0 | Yes | No | No | No | Yes | No | No | No | No | No | Yes
B23091 | AIK00003 | Sidewalk Replacement Group 2330 - LV & N | 2025-01-01 | Sidewalk Repair & Replacement / AIK00003 | Sidewalk Replacement Group 2330 - LV & N / B23091 | Geo-Mapping is in progress | Transportation | Design Bid Build | Transportation | Transportation | TD | Hoenes, Craig | Luong, Eric | No Project Charter or Amendment | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-03-17 | 2025-11-07 |  | 2025-11-07 | 2024-05-13 | FY25 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 | 2025-03-17 | 2025-05-01 |  | 2025-05-01 | FY25 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 | 2000000 | 1370969 |  | 1370969 | 3121906 | 2844288.79 |  | 2844288.79 | 2000000 | -306354.16 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
B19142 | AKB00003 | Pacific Beach Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Pacific Beach Improv 1 (W) / B19142 | 1 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Sherzai, Jamal | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st |  |  |  |  | 2025-10-27 |  | 2025-10-27 | 2024-12-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-04-25 |  | 2025-04-25 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 6060100 |  | 6060100 |  | 8710558 |  | 8710558 | 5638300 | 529058 | 2.85 | 2.85 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22085 | ALA00001 | PW Genesee Avenue Median Improv | 2025-01-01 | Pure Water Program / ALA00001 | PW Genesee Avenue Median Improv / B22085 | 6 | Transportation | Design Bid Build | Public Utilities | PUD Pure Water | PUD_PW | Tadros, Sameh | Block, Colleen | No Project Charter or Amendment | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-01-02 | 2025-09-10 |  | 2025-09-10 | 2024-12-31 | FY25 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-07-10 | 2025-03-10 |  | 2025-03-10 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 1100000 | 1100000 |  | 1100000 | 2007591.45 | 2007591.45 |  | 2007591.45 | 1100000 | 83615.45 | 0 | 0 | 0 | 0 | Yes | Yes | No | No | No | No | No | No | No | No | Yes
L22000.3 | L22000 | Alvarado Laboratory ImprovementsTrailers | 2025-01-01 | Alvarado Laboratory Improvements / L22000 | Alvarado Laboratory ImprovementsTrailers / L22000.3 | 7 | Water | Job Order Contract | Public Utilities | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Rummani, Zina | No Project Charter or Amendment | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2024-12-03 | 2025-07-01 |  | 2025-07-01 | 2024-07-18 | FY25 | Q2 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-08-29 | 2025-01-14 |  | 2025-01-14 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 1500000 | 2173927 |  | 2173927 | 2102000 | 4039878 |  | 4039878 | 1090800 | 502000 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B21114 | AGF00007 | Mt View Sports Courts ADA Improvements | 2025-01-01 | Park Improvements / AGF00007 | Mt View Sports Courts ADA Improvements / B21114 | 4 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Kieser-Hua, Lin | Charter Only | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-01-15 | 2025-12-09 |  | 2025-12-09 | 2024-07-16 | FY25 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 | 2024-07-16 | 2025-05-30 |  | 2025-05-30 | FY25 | Q1 | FY25 | Q4 |  |  | FY25 | Q4 | 365894 | 458026 |  | 458026 | 863873 | 993329 |  | 993329 | 196200 | 318873 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B23011 | AGF00007 | Willie Henderson Lighting Upgrades | 2025-01-01 | Park Improvements / AGF00007 | Willie Henderson Lighting Upgrades / B23011 | 4 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Kieser-Hua, Lin | No Project Charter or Amendment | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-02-21 | 2025-09-02 |  | 2025-09-02 | 2024-09-03 | FY25 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-08-19 | 2025-02-28 |  | 2025-02-28 | FY25 | Q1 | FY25 | Q3 |  |  | FY25 | Q3 | 795781 | 1301682 |  | 1301682 | 1312359 | 2132550 |  | 2132550 | 633000 | 779550 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
L20000.2 | L20000 | Rancho Bernardo CP Dog Park | 2025-01-01 | Rancho Bernardo CP Improvements / L20000 | Rancho Bernardo CP Dog Park / L20000.2 | 5 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Grotzinger, Juliana | Charter Only | Removed | On Schedule |  | On Published List | FY26 |  |  | On Published List |  |  |  | 2025-04-16 | 2025-09-16 |  | 2025-09-16 | 2023-04-03 | FY25 | Q4 | FY26 | Q1 |  |  | FY26 | Q1 | 2024-10-03 | 2025-03-07 |  | 2025-03-07 | FY25 | Q2 | FY25 | Q3 |  |  | FY25 | Q3 | 3073177.8 | 3073177.8 |  | 3073177.8 | 5149197.43 | 5149197.43 |  | 5149197.43 | 743000 | 3696197.43 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B19158 | AGF00004 | Dusty Rhodes Parking Lot Improvements | 2025-01-01 | Mission Bay Improvements / AGF00004 | Dusty Rhodes Parking Lot Improvements / B19158 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Nguyen, Kevin | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st |  |  |  |  | 2025-10-22 |  | 2025-10-22 | 2022-05-31 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-04-15 |  | 2025-04-15 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 785629 |  | 785629 |  | 1785629 |  | 1785629 | 338720 | 858000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19180 | AGF00004 | Dusty Rhodes Comfort Station Improvement | 2025-01-01 | Mission Bay Improvements / AGF00004 | Dusty Rhodes Comfort Station Improvement / B19180 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Nguyen, Kevin | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st |  |  |  |  | 2025-10-22 |  | 2025-10-22 | 2022-05-31 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-04-15 |  | 2025-04-15 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 1200000 |  | 1200000 |  | 2765334.15 |  | 2765334.15 | 1015640 | 396334 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19181 | AGF00004 | Dusty Rhodes Playground | 2025-01-01 | Mission Bay Improvements / AGF00004 | Dusty Rhodes Playground / B19181 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Nguyen, Kevin | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st |  |  |  |  | 2025-10-22 |  | 2025-10-22 | 2022-05-31 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-04-15 |  | 2025-04-15 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 4000000 |  | 4000000 |  | 5205715 |  | 5205715 | 1015640 | 3261715 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B00429 | AJA00001 | Buchanan Canyon Sewer B (UP) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Buchanan Canyon Sewer B (UP) / B00429 | 3 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-12-24 |  | 2025-12-24 | 2010-03-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-03-24 |  | 2025-03-24 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 15203592.04 |  | 15203592.04 |  | 17666617.04 |  | 17666617.04 | 2487492 | 14020221.61 | 0 | 0 | 0.79 | 0.79 | No | No | No | No | No | No | No | Yes | Yes | Yes | Yes
B15102 | ACC00001 | Green Infrastructure Group 1024 | 2025-01-01 | Stormwater Green Infrastructure / ACC00001 | Green Infrastructure Group 1024 / B15102 | 4 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Talamayan, Jonard | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-12-31 |  | 2025-12-31 | 2018-06-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-23 |  | 2025-06-23 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 1653146 |  | 1653146 |  | 4043254 |  | 4043254 | 1474100 | 1001500 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B15103 | ACC00001 | Green Infrastructure Group 1027 | 2025-01-01 | Stormwater Green Infrastructure / ACC00001 | Green Infrastructure Group 1027 / B15103 | 3 | Storm Water Drainage | Design Bid Build | Stormwater | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-11-19 |  | 2025-11-19 | 2018-06-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-02 |  | 2025-06-02 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 1600000 |  | 1600000 |  | 2600000 |  | 2600000 | 1491000 | 600000 | 0 | 0 | 0 | 0 | No | No | No | Yes | No | Yes | Yes | No | No | No | Yes
B16119 | AIH00002 | Pacific Beach 1 SL Series Circuit Conv | 2025-01-01 | Street Light Circuit Upgrades / AIH00002 | Pacific Beach 1 SL Series Circuit Conv / B16119 | 1 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2026-01-08 |  | 2026-01-08 | 2019-10-01 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-06-30 |  | 2025-06-30 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 5100000 |  | 5100000 |  | 6600000 |  | 6600000 | 4067300 | 439000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | Yes | No | No | Yes
B17019 | AIL00004 | 31st St @ National Ave Traffic Signal | 2025-01-01 | Traffic Signals - Citywide / AIL00004 | 31st St @ National Ave Traffic Signal / B17019 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Amendment Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-11-26 |  | 2025-11-26 | 2022-02-10 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-04-02 |  | 2025-04-02 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 1250000 |  | 1250000 |  | 1858400 |  | 1858400 | 379050 | 983600 | 0 | 0 | 0 | 0 | No | Yes | No | No | No | No | No | No | No | No | Yes
B19033 | AJA00001 | Hillcrest Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Hillcrest Improv 1 (S) / B19033 | 3 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Owen, Regan | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2026-01-08 |  | 2026-01-08 | 2023-04-03 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-06-30 |  | 2025-06-30 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 4496500 |  | 4496500 |  | 8791537 |  | 8791537 | 4496500 | 127940 | 0 | 0 | 1.77 | 1.77 | No | No | No | No | No | No | No | No | No | No | Yes
B19034 | AKB00003 | Hillcrest Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Hillcrest Improv 1 (W) / B19034 | 3 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Owen, Regan | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2026-01-08 |  | 2026-01-08 | 2023-04-03 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-06-30 |  | 2025-06-30 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2490600 |  | 2490600 |  | 4035250 |  | 4035250 | 2490600 | 418750 | 1.56 | 1.56 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19056 | AIE00002 | Torrey Pines Rd, Prospect-Coast Walk GR | 2025-01-01 | Guard Rails / AIE00002 | Torrey Pines Rd, Prospect-Coast Walk GR / B19056 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Mansury, Nazie | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-11-03 |  | 2025-11-03 | 2025-11-03 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-05-01 |  | 2025-05-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 769700 |  | 769700 |  | 1540573.03 |  | 1540573.03 | 692730 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19148 | AKB00003 | College West Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | College West Improv 1 (W) / B19148 | 9 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-07-30 |  | 2025-07-30 | 2025-08-25 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-18 |  | 2025-02-18 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 8076829.55 |  | 8076829.55 |  | 10018773.55 |  | 10018773.55 | 2961000 | 5784773.55 | 1.32 | 1.32 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19152 | AJA00001 | College West Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | College West Improv 1 (S) / B19152 | 9 | Sewer | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Cheung, Jody | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-07-30 |  | 2025-07-30 | 2025-08-25 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-18 |  | 2025-02-18 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 12470080 |  | 12470080 |  | 15312859 |  | 15312859 | 8137300 | 3676459 | 0 | 0 | 2.65 | 2.65 | No | No | No | No | No | No | No | No | No | No | Yes
B19196 | AKB00003 | Mission Valley West Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Mission Valley West Improv 1 (W) / B19196 | 3 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-08-12 |  | 2025-08-12 | 2023-04-03 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-31 |  | 2025-01-31 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 10435290.82 |  | 10435290.82 |  | 13469079 |  | 13469079 | 5249400 | 5673779 | 2.97 | 2.97 | 0 | 0 | No | No | Yes | No | No | No | No | No | No | No | Yes
B19206 | AJA00001 | Mission Valley West Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Mission Valley West Improv 1 (S) / B19206 | 3 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | VejarParra, Roberto | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-08-12 |  | 2025-08-12 | 2023-04-03 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-31 |  | 2025-01-31 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 1463637.39 |  | 1463637.39 |  | 1814057.21 |  | 1814057.21 | 425400 | 1182357.21 | 0 | 0 | 0.18 | 0.18 | No | No | Yes | No | No | No | No | No | No | No | Yes
B19212 | AGF00004 | Robb Field Gateway Path | 2025-01-01 | Mission Bay Improvements / AGF00004 | Robb Field Gateway Path / B19212 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Grotzinger, Juliana | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-12-10 |  | 2025-12-10 | 2023-09-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-02 |  | 2025-06-02 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2242915 |  | 2242915 |  | 3233046 |  | 3233046 | 393000 | 2440046 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20034 | AJA00001 | Clairemont Mesa East Improv 4 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Clairemont Mesa East Improv 4 (S) / B20034 | 2 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Mansury, Nazie | Charter & Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2026-01-07 |  | 2026-01-07 | 2025-12-10 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-06-27 |  | 2025-06-27 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 11700000 |  | 11700000 |  | 15950000 |  | 15950000 | 11700000 | 0 | 0 | 0 | 3.68 | 3.68 | No | No | No | No | No | No | No | No | No | No | Yes
B22015 | AKB00003 | Via De La Valle Pipeline | 2025-01-01 | Main Replacements / AKB00003 | Via De La Valle Pipeline / B22015 | 1 | Water | Design Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Randles, Jacob | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2026-02-26 |  | 2026-02-26 | 2024-03-06 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-04-16 |  | 2025-04-16 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 4298000 |  | 4298000 |  | 6547000 |  | 6547000 | 4298000 | 0 | 1.13 | 1.13 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22139 | ABT00001 | Scripps Miramar Ranch Library Roof Repl | 2025-01-01 | City Facility Improvements / ABT00001 | Scripps Miramar Ranch Library Roof Repl / B22139 | 5 | Buildings | Design Bid Build | General Services | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Hossan, Farhad | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-07-08 |  | 2025-07-08 | 2025-05-02 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-02-28 |  | 2025-02-28 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 2292271 |  | 2292271 |  | 3267971 |  | 3267971 | 1700391.6 | 679971 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22151 | AKB00003 | Paradise Hills Pipeline Replacement | 2025-01-01 | Main Replacements / AKB00003 | Paradise Hills Pipeline Replacement / B22151 | 4 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Katzenstein, Phuong | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-12-18 |  | 2025-12-18 | 2025-10-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-11 |  | 2025-06-11 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2087100 |  | 2087100 |  | 4634544 |  | 4634544 | 2087100 | 1289941 | 0.79 | 0.79 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23013 | AAA00001 | Unleaded Aviation Fuel Tank | 2025-01-01 | Montgomery Field / AAA00001 | Unleaded Aviation Fuel Tank / B23013 | 7 | Airport | Design Build | Airports | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Castaneyra, Jose | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-12-18 |  | 2025-12-18 | 2024-06-03 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-10 |  | 2025-06-10 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 572400 |  | 572400 |  | 980000 |  | 980000 | 572400 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23098 | ACC00001 | Auburn Creek Trash Capture Devices | 2025-01-01 | Stormwater Green Infrastructure / ACC00001 | Auburn Creek Trash Capture Devices / B23098 | 9 | Storm Water Drainage | Design Bid Build | Stormwater | Storm Water | SWD | Dastgheibi, Sara | Garcia Guzman, Julio | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-12-15 |  | 2025-12-15 | 2025-09-17 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-13 |  | 2025-06-13 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 15619361 |  | 15619361 |  | 23624095 |  | 23624095 | 15619361 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23145 | AIL00004 | 47th St & Hartley St HAWK | 2025-01-01 | Traffic Signals - Citywide / AIL00004 | 47th St & Hartley St HAWK / B23145 | 4 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Damnjanovic, Nenad | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-11-24 |  | 2025-11-24 | 2025-10-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-05-15 |  | 2025-05-15 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 528480 |  | 528480 |  | 988100 |  | 988100 | 528480 | -4400 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S00951 | S00951 | Coastal Rail Trail | 2025-01-01 | Coastal Rail Trail / S00951 | Coastal Rail Trail / S00951 | 1, 6 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Randles, Jacob | Charter Amendment Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-12-10 |  | 2025-12-10 | 2025-02-14 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-04-03 |  | 2025-04-03 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 19837589 |  | 19837589 |  | 30158004.61 |  | 30158004.61 | 19157589 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | Yes | No | No | No | No | No | Yes
S13008 | S13008 | Mohnike Adobe and Barn Restoration | 2025-01-01 | Mohnike Adobe and Barn Restoration / S13008 | Mohnike Adobe and Barn Restoration / S13008 | 6 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Getz, Shannon | Charter & Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-12-17 |  | 2025-12-17 | 2022-11-29 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-09 |  | 2025-06-09 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 3451214 |  | 3451214 |  | 5086017.51 |  | 5086017.51 | 1950000 | 2389017.55 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B18026 | AGF00006 | Narragansett Avenue Access | 2025-01-01 | Coastal Erosion and Access / AGF00006 | Narragansett Avenue Access / B18026 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | Afagh, Negin | Charter Only | Removed | On Schedule |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st |  |  |  |  | 2025-09-04 |  | 2025-09-04 | 2024-08-26 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-03-04 |  | 2025-03-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 806135 |  | 806135 |  | 1984181.17 |  | 1984181.17 | 134000 | 1191181.17 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19190 | AKB00003 | Allied Gardens Improv 2 (W) | 2025-01-01 | Main Replacements / AKB00003 | Allied Gardens Improv 2 (W) / B19190 | 7 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Crespo, Santiago | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st |  |  |  |  | 2025-11-18 |  | 2025-11-18 | 2024-11-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-05-09 |  | 2025-05-09 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 670700 |  | 670700 |  | 1037770 |  | 1037770 | 670700 | -129230 | 0.42 | 0.42 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23148 | AIL00001 | Otay Mesa Rd Pedestrian Improvements | 2025-01-01 | Traffic Calming / AIL00001 | Otay Mesa Rd Pedestrian Improvements / B23148 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Damnjanovic, Nenad | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st |  |  |  |  | 2025-12-29 |  | 2025-12-29 | 2026-01-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-26 |  | 2025-06-26 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 321750 |  | 321750 |  | 661600 |  | 661600 | 321750 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25014 | TBD | AC Water & Sewer Group 1033 North (W) | 2025-01-01 | TBD | AC Water & Sewer Group 1033 North (W) / B25014 | 3, 2 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st |  |  |  |  | 2025-07-16 |  | 2025-07-16 | 2025-07-16 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-03 |  | 2025-01-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 15500000 |  | 15500000 |  | 19685000 |  | 19685000 | 15500000 | 0 | 1.51 | 1.51 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25049 | TBD | AC Overlay Group 2511 | 2025-01-01 | TBD | AC Overlay Group 2511 / B25049 | 5 | Transportation | Job Order Contract | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st |  |  |  |  | 2025-07-11 |  | 2025-07-11 | 2025-09-02 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-03-03 |  | 2025-03-03 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 3914850 |  | 3914850 |  | 4641000 |  | 4641000 | 3914850 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25054 | TBD | AC Overlay Group 2516 | 2025-01-01 | TBD | AC Overlay Group 2516 / B25054 | 1, 6 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st |  |  |  |  | 2026-01-08 |  | 2026-01-08 | 2026-01-08 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-06-30 |  | 2025-06-30 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 7433000 |  | 7433000 |  | 8780000 |  | 8780000 | 7433000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25055 | TBD | AC Overlay Group 2517 | 2025-01-01 | TBD | AC Overlay Group 2517 / B25055 | 6, 7 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | CamachoDiaz, Jason | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st |  |  |  |  | 2025-08-12 |  | 2025-08-12 | 2026-01-08 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-01-31 |  | 2025-01-31 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 7162263 |  | 7162263 |  | 8355973 |  | 8355973 | 8219250 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25056 | TBD | AC Overlay Group 2518 | 2025-01-01 | TBD | AC Overlay Group 2518 / B25056 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st |  |  |  |  | 2026-01-08 |  | 2026-01-08 | 2026-01-08 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-06-30 |  | 2025-06-30 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 7212000 |  | 7212000 |  | 8520000 |  | 8520000 | 7212000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25057 | TBD | AC Overlay Group 2522 | 2025-01-01 | TBD | AC Overlay Group 2522 / B25057 | 9, 4 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Mills, Amy | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st |  |  |  |  | 2025-10-07 |  | 2025-10-07 | 2026-01-09 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-03-28 |  | 2025-03-28 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 4827750 |  | 4827750 |  | 5715000 |  | 5715000 | 4827750 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20116 | ABT00001 | Air & Space Museum Roof Replacement | 2025-01-01 | City Facility Improvements / ABT00001 | Air & Space Museum Roof Replacement / B20116 | 3 | Buildings | Design Bid Build | General Services | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Castaneyra, Jose | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-08-28 |  | 2025-08-28 | 2024-07-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-05-19 |  | 2025-05-19 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 4755900 |  | 4755900 |  | 7897741 |  | 7897741 | 4174000 | 1107741 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19163 | AGF00004 | Rose Marie Starns Parking Lot Imprvemts | 2025-01-01 | Mission Bay Improvements / AGF00004 | Rose Marie Starns Parking Lot Imprvemts / B19163 | 2 | Parks | Job Order Contract | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk1 | Schroth-Nichols, Elizabeth | Afagh, Negin | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-10-09 |  | 2025-10-09 | 2024-01-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-04-02 |  | 2025-04-02 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2981811 |  | 2981811 |  | 4044832 |  | 4044832 | 3804300 | -1900168 | 0 | 0 | 0 | 0 | No | No | No | No | No | Yes | No | No | No | No | Yes
B20140 | AIL00004 | Mississippi St @ El Cajon Blvd T/Signal | 2025-01-01 | Traffic Signals - Citywide / AIL00004 | Mississippi St @ El Cajon Blvd T/Signal / B20140 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-09-23 |  | 2025-09-23 | 2023-07-13 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-04-03 |  | 2025-04-03 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 1050000 |  | 1050000 |  | 1860000 |  | 1860000 | 353570 | 1153000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20102 | AKB00003 | El Cerrito Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | El Cerrito Improv 1 (W) / B20102 | 9 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Owen, Regan | Charter Only | Removed | On Schedule |  |  | FY26 |  |  | Added - Dec 1st |  |  |  |  | 2025-12-22 |  | 2025-12-22 | 2023-12-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-12 |  | 2025-06-12 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2635300 |  | 2635300 |  | 5135514 |  | 5135514 | 1321500 | 3216714 | 0.74 | 0.74 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20103 | AJA00001 | El Cerrito Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | El Cerrito Improv 1 (S) / B20103 | 9 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Owen, Regan | Charter Only | Removed | On Schedule |  |  | FY26 |  |  | Added - Dec 1st |  |  |  |  | 2025-12-22 |  | 2025-12-22 | 2023-12-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-12 |  | 2025-06-12 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 8271800 |  | 8271800 |  | 14806833 |  | 14806833 | 5670200 | 1032323 | 0 | 0 | 2.36 | 2.36 | No | No | No | No | No | No | No | No | No | No | Yes
B22111 | AIL00004 | Center City Traffic Signals-15th Street | 2025-01-01 | Traffic Signals - Citywide / AIL00004 | Center City Traffic Signals-15th Street / B22111 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Guillermo, Erick | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  |  | Added - Dec 1st |  |  |  |  | 2025-10-08 |  | 2025-10-08 | 2025-01-10 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-04-01 |  | 2025-04-01 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 1875000 |  | 1875000 |  | 2710000 |  | 2710000 | 1200000 | 875000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B21067 | S22013 | Dams & Reservoirs Security Improvements | 2025-01-01 | Dams & Reservoirs Security Improvements / S22013 | Dams & Reservoirs Security Improvements / B21067 | 8, 7, 5 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Stohr, John | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2026-01-08 |  | 2026-01-08 | 2023-05-01 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-06-30 |  | 2025-06-30 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 15300000 |  | 15300000 |  | 27300000 |  | 27300000 | 8440400 | 15352500 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22091 | AJA00001 | Golden Hill Improv 2 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Golden Hill Improv 2 (S) / B22091 | 3, 8 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Stohr, John | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-10-17 |  | 2025-10-17 | 2026-06-11 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-12 |  | 2025-06-12 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 2293200 |  | 2293200 |  | 3693000 |  | 3693000 | 2293200 | 0 | 0 | 0 | 0.97 | 0.97 | No | No | No | No | No | No | No | No | No | No | Yes
B22093 | AKB00003 | Golden Hill Improv 2 (W) | 2025-01-01 | Main Replacements / AKB00003 | Golden Hill Improv 2 (W) / B22093 | 3 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Stohr, John | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-10-23 |  | 2025-10-23 | 2026-06-11 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-18 |  | 2025-06-18 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 7356600 |  | 7356600 |  | 11847000 |  | 11847000 | 7356600 | 0 | 2.78 | 2.78 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B15047 | AIL00004 | Division St & Osborn St Traffic Signal | 2025-01-01 | Traffic Signals - Citywide / AIL00004 | Division St & Osborn St Traffic Signal / B15047 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | Removed | On Schedule |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2025-12-12 |  | 2025-12-12 | 2020-06-12 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-06-04 |  | 2025-06-04 | FY00 | Q3 | FY25 | Q4 |  |  | FY25 | Q4 |  | 1220000 |  | 1220000 |  | 2142278 |  | 2142278 | 212200 | 1867278 | 0 | 0 | 0 | 0 | No | No | No | Yes | Yes | No | No | No | Yes | Yes | Yes
B25067 | TBD | AC Overlay Group 2511A | 2025-01-01 | TBD | AC Overlay Group 2511A / B25067 | Geo-Mapping is in progress | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  |  | Added - Jan 1st |  |  |  |  | 2025-09-11 |  | 2025-09-11 | 2025-09-11 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-03-04 |  | 2025-03-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 890000 |  | 890000 |  | 1240000 |  | 1240000 |  |  | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25068 | TBD | AC Overlay Group 2511B | 2025-01-01 | TBD | AC Overlay Group 2511B / B25068 | Geo-Mapping is in progress | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  |  | Added - Jan 1st |  |  |  |  | 2025-09-11 |  | 2025-09-11 | 2025-09-11 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-03-04 |  | 2025-03-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 890000 |  | 890000 |  | 1240000 |  | 1240000 |  |  | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25069 | TBD | AC Overlay Group 2511C | 2025-01-01 | TBD | AC Overlay Group 2511C / B25069 | Geo-Mapping is in progress | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | Removed | On Schedule |  |  | FY26 |  |  | Added - Jan 1st |  |  |  |  | 2025-09-11 |  | 2025-09-11 | 2025-09-11 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2025-03-04 |  | 2025-03-04 | FY00 | Q3 | FY25 | Q3 |  |  | FY25 | Q3 |  | 890000 |  | 890000 |  | 1240000 |  | 1240000 |  |  | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23071 | AEA00002 | Balboa Park Golf Course Improvements | 2025-01-01 | Balboa Park Golf Course / AEA00002 | Balboa Park Golf Course Improvements / B23071 | 3 | Parks | Design Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk2 | Genova, Darren | Chan, Ling | Charter Only | Removed | On Schedule |  |  | FY26 |  |  | Added - Jan 1st |  |  |  |  | 2026-03-18 |  | 2026-03-18 | 2026-06-01 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-09-05 | 2025-01-07 | 2025-01-07 | FY00 | Q3 | FY26 | Q1 | FY25 | Q3 | FY25 | Q3 |  | 3300000 |  | 3300000 |  | 6400000 |  | 6400000 | 2923299 | 999901 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24109 | TBD | Saturn Blvd Sidewalk Installation | 2025-01-01 | TBD | Saturn Blvd Sidewalk Installation / B24109 | 8 | Transportation | Quick Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Damnjanovic, Nenad | Charter Only | Removed | Removed |  | Added - Sep 1st | FY26 |  | Removed - Dec 1st |  | FY26 |  |  |  | 2026-03-09 |  | 2026-03-09 | 2025-05-06 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2026-02-04 |  | 2026-02-04 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 850000 |  | 850000 |  | 1500000 |  | 1500000 | 1010700 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20028 | AJA00001 | Stockton Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Stockton Improv 1 (S) / B20028 | 8, 9 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | Charter Only | Removed | Removed |  | Added - Aug 1st | FY26 |  |  | Added - Aug 1st | FY26 |  |  |  | 2025-10-31 |  | 2025-10-31 | 2023-10-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-07-07 |  | 2025-07-07 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 8284500 |  | 8284500 |  | 12307600 |  | 12307600 | 8284500 | 0 | 0 | 0 | 3.2 | 3.2 | No | No | No | No | No | No | No | No | No | No | Yes
B20030 | AKB00003 | Stockton Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Stockton Improv 1 (W) / B20030 | 8, 9 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Saleh, Aveen | Charter Only | Removed | Removed |  | Added - Aug 1st | FY26 |  |  | Added - Aug 1st | FY26 |  |  |  | 2025-10-31 |  | 2025-10-31 | 2023-10-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-07-07 |  | 2025-07-07 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 897030 |  | 897030 |  | 1553900 |  | 1553900 | 897030 | 249900 | 0.42 | 0.42 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B15065 | AIL00002 | Pacific Beach TS Interconnect Upgrade | 2025-01-01 | Install T/S Interconnect Systems / AIL00002 | Pacific Beach TS Interconnect Upgrade / B15065 | 1, 7, 2 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-01-12 |  | 2026-01-12 | 2020-06-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-07-02 |  | 2025-07-02 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 1607075.73 |  | 1607075.73 |  | 3221864.73 |  | 3221864.73 | 933030 | 977600 | 0 | 0 | 0 | 0 | No | No | Yes | Yes | Yes | No | No | No | No | No | Yes
B18017 | AIK00001 | 73rd St-El Cajon Bl to Saranac-Sidewalk | 2025-01-01 | New Walkways / AIK00001 | 73rd St-El Cajon Bl to Saranac-Sidewalk / B18017 | 9 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Mansury, Nazie | Charter & Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-03-10 |  | 2026-03-10 | 2022-12-08 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-27 |  | 2025-08-27 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 345000 |  | 345000 |  | 831750 |  | 831750 | 345000 | 30000 | 0 | 0 | 0 | 0 | No | No | No | Yes | No | No | No | No | No | No | Yes
B18107 | AKB00003 | AC Water & Sewer Group 1054 (W) | 2025-01-01 | Main Replacements / AKB00003 | AC Water & Sewer Group 1054 (W) / B18107 | 9, 4 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-05-19 |  | 2026-05-19 | 2023-04-03 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-11-05 |  | 2025-11-05 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 7899294 |  | 7899294 |  | 9589375 |  | 9589375 | 1982600 | 6710475 | 2.83 | 2.83 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B18108 | AJA00001 | AC Water and Sewer Group 1054 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | AC Water and Sewer Group 1054 (S) / B18108 | 9, 4 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-05-19 |  | 2026-05-19 | 2023-04-03 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-11-05 |  | 2025-11-05 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 9654693 |  | 9654693 |  | 11775933 |  | 11775933 | 2480600 | 8137633 | 0 | 0 | 1.7 | 1.7 | No | No | No | No | No | No | No | No | No | No | Yes
B19095 | ACC00001 | Streamview Drive Green Infrastructure | 2025-01-01 | Stormwater Green Infrastructure / ACC00001 | Streamview Drive Green Infrastructure / B19095 | 9, 4 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter & Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-05-18 |  | 2026-05-18 | 2023-03-30 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-11-04 |  | 2025-11-04 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 19416048 |  | 19416048 |  | 24222655 |  | 24222655 | 6852000 | 13512655 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B21098 | AJA00001 | Valencia Park Improv 5 (s) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Valencia Park Improv 5 (s) / B21098 | 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS4 | Narvaez, Rex | Aghdam, Sanoubar | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-01-09 |  | 2026-01-09 | 2024-05-01 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-07-15 |  | 2025-07-15 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 5435700 |  | 5435700 |  | 6864800 |  | 6864800 | 5435700 | 0 | 0 | 0 | 1.41 | 1.41 | No | No | No | No | No | No | No | No | No | No | Yes
B22008 | AJA00002 | Chollas View Improv 1 (S) | 2025-01-01 | Pipeline Rehabilitation / AJA00002 | Chollas View Improv 1 (S) / B22008 | 4 | Sewer | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Mills, Amy | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-01-15 |  | 2026-01-15 | 2026-01-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-07-15 |  | 2025-07-15 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 5501610 |  | 5501610 |  | 8523700 |  | 8523700 | 5501610 | 0 | 0 | 0 | 4.24 | 4.24 | No | No | No | No | No | No | No | No | No | No | Yes
B22101 | AIL00005 | Front & Washington TS Modification | 2025-01-01 | Traffic Signals - Modify & Modernize / AIL00005 | Front & Washington TS Modification / B22101 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Guillermo, Erick | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-01-13 |  | 2026-01-13 | 2024-02-14 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-07-03 |  | 2025-07-03 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 931888.62 |  | 931888.62 |  | 1530688.62 |  | 1530688.62 | 576200 | 389888.62 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23147 | AIL00001 | Osler Street Traffic Calming | 2025-01-01 | Traffic Calming / AIL00001 | Osler Street Traffic Calming / B23147 | 7 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Randles, Jacob | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-01-06 |  | 2026-01-06 | 2025-12-01 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-07-08 |  | 2025-07-08 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 346600 |  | 346600 |  | 633950 |  | 633950 | 346600 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S18000 | S18000 | Streamview Drive Improvements Phase 2 | 2025-01-01 | Streamview Drive Improvements Phase 2 / S18000 | Streamview Drive Improvements Phase 2 / S18000 | 9 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Piromari, Diluvan | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-05-18 |  | 2026-05-18 | 2021-08-10 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-11-04 |  | 2025-11-04 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 17917057 |  | 17917057 |  | 23086456 |  | 23086456 | 9469400 | 8524456 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B18162 | AIL00005 | Downtown Audibles 04th & E S29 | 2025-01-01 | Traffic Signals - Modify & Modernize / AIL00005 | Downtown Audibles 04th & E S29 / B18162 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Guillermo, Erick | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Dec 1st |  | 2026-02-24 |  | 2026-02-24 | 2021-10-22 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-20 |  | 2025-08-20 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 996500 |  | 996500 |  | 1400000 |  | 1400000 | 385100 | 783600 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22150 | AID00005 | Palm Ave I-5 to Georgia Street Repairs | 2025-01-01 | Resurfacing of City Streets / AID00005 | Palm Ave I-5 to Georgia Street Repairs / B22150 | 8 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Poomchongkho, Nusra | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Dec 1st |  | 2026-01-20 |  | 2026-01-20 | 2024-09-05 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-15 |  | 2025-08-15 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2680000 |  | 2680000 |  | 4000000 |  | 4000000 | 1393020 | 1786500 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23076 | AIL00005 | 32nd St & Market St Intersection Upgrade | 2025-01-01 | Traffic Signals - Modify & Modernize / AIL00005 | 32nd St & Market St Intersection Upgrade / B23076 | 9 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Xiao, Jie | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Dec 1st |  | 2026-02-09 |  | 2026-02-09 | 2024-12-31 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-07 |  | 2025-08-07 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 650000 |  | 650000 |  | 1006960 |  | 1006960 | 381240 | 268760 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S24002 | TBD | Barret Dam Outlet Bulkhead & Drawdown | 2025-01-01 | TBD | Barret Dam Outlet Bulkhead & Drawdown / S24002 | Project outside of City limits | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_Dams | Van Martin, Debbie | Hawk, Gavin | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Dec 1st |  | 2026-02-05 |  | 2026-02-05 | 2028-01-19 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-05 |  | 2025-08-05 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 13700000 |  | 13700000 |  | 21446250 |  | 21446250 | 9810000 | 6746250 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25046 | TBD | AC Overlay Group 2508 | 2025-01-01 | TBD | AC Overlay Group 2508 / B25046 | 1, 5 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st | FY26 |  | Removed - Dec 1st |  | 2025-10-24 |  | 2025-10-24 | 2025-09-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-08-22 |  | 2025-08-22 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 4160500 |  | 4160500 |  | 4930000 |  | 4930000 | 4160500 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25047 | TBD | AC Overlay Group 2509 | 2025-01-01 | TBD | AC Overlay Group 2509 / B25047 | 1 | Transportation | Job Order Contract | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st | FY26 |  | Removed - Dec 1st |  | 2025-10-24 |  | 2025-10-24 | 2025-09-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-08-22 |  | 2025-08-22 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 3307950 |  | 3307950 |  | 3927000 |  | 3927000 | 3307950 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25050 | TBD | AC Overlay Group 2512 | 2025-01-01 | TBD | AC Overlay Group 2512 / B25050 | 5 | Transportation | Job Order Contract | Transportation | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Katzenstein, Phuong | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st | FY26 |  | Removed - Dec 1st |  | 2025-10-24 |  | 2025-10-24 | 2025-09-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-08-22 |  | 2025-08-22 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 4290550 |  | 4290550 |  | 5083000 |  | 5083000 | 4290550 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25051 | TBD | AC Overlay Group 2513 | 2025-01-01 | TBD | AC Overlay Group 2513 / B25051 | 5 | Transportation | Design Bid Build | Transportation | Facility & Parks Project Delivery | FPPD_PB1 | Gibson, William | Perez, Marlon | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st | FY26 |  | Removed - Dec 1st |  | 2026-05-04 |  | 2026-05-04 | 2026-01-08 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-10-21 |  | 2025-10-21 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 5920000 |  | 5920000 |  | 7000000 |  | 7000000 | 5920000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25052 | TBD | AC Overlay Group 2514 | 2025-01-01 | TBD | AC Overlay Group 2514 / B25052 | 7, 2 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Mansour, Amanda | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st | FY26 |  | Removed - Dec 1st |  | 2026-03-05 |  | 2026-03-05 | 2026-01-08 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-22 |  | 2025-08-22 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 8295750 |  | 8295750 |  | 9795000 |  | 9795000 | 7875000 | 495000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25053 | TBD | AC Overlay Group 2515 | 2025-01-01 | TBD | AC Overlay Group 2515 / B25053 | 6 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS2 | Ramos-Banuelos, Jaime | Katzenstein, Phuong | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st | FY26 |  | Removed - Dec 1st |  | 2026-03-05 |  | 2026-03-05 | 2026-01-08 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-22 |  | 2025-08-22 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 7875000 |  | 7875000 |  | 9300000 |  | 9300000 | 7875000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B25058 | TBD | AC Overlay Group 2523 | 2025-01-01 | TBD | AC Overlay Group 2523 / B25058 | 9, 4 | Transportation | Design Bid Build | Transportation | Utilities Project Delivery | UPD_WWS3 | Jaro, Janice | Sherzai, Hossai | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Oct 1st | Added - Oct 1st | FY26 |  | Removed - Dec 1st |  | 2026-03-05 |  | 2026-03-05 | 2026-01-08 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-22 |  | 2025-08-22 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 7046250 |  | 7046250 |  | 8325000 |  | 8325000 | 7046250 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23030 | AIL00005 | Linda Vista & Comstock Intersection Upg | 2025-01-01 | Traffic Signals - Modify & Modernize / AIL00005 | Linda Vista & Comstock Intersection Upg / B23030 | 7 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Chan, Chun Yu | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Dec 1st |  | 2026-01-15 |  | 2026-01-15 | 2025-01-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-12 |  | 2025-08-12 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 729720 |  | 729720 |  | 1281200 |  | 1281200 | 729720 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B17033 | ACC00001 | Los Pen Lagoon Restoration Ph 1 | 2025-01-01 | Stormwater Green Infrastructure / ACC00001 | Los Pen Lagoon Restoration Ph 1 / B17033 | 1 | Storm Water Drainage | Design Bid Build | Stormwater | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Damnjanovic, Nenad | Charter & Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Nov 1st |  | 2026-02-13 |  | 2026-02-13 | 2023-06-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-05 |  | 2025-08-05 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 76251937 |  | 76251937 |  | 120284661 |  | 120284661 | 22061000 | 81370454 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B18022 | AJA00001 | AC Water & Sewer Group 1033 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | AC Water & Sewer Group 1033 (S) / B18022 | 3 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | Charter & Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Nov 1st |  | 2026-01-20 |  | 2026-01-20 | 2026-01-23 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-07-10 |  | 2025-07-10 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 13488432.36 |  | 13488432.36 |  | 18046948.7 |  | 18046948.7 | 11610241.02 | 3301942.59 | 0 | 0 | 2.43 | 2.43 | No | No | No | No | No | No | No | No | No | No | Yes
B20054 | AGE00001 | West Sycamore Staging Area | 2025-01-01 | Resource Based Open Space Parks / AGE00001 | West Sycamore Staging Area / B20054 | 6 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Calleran, Mark | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Nov 1st |  | 2026-03-12 |  | 2026-03-12 | 2023-02-06 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-29 |  | 2025-08-29 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 2100000 |  | 2100000 |  | 3935188 |  | 3935188 | 1282600 | 1741170 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22135 | AIL00001 | Milton St Burgener Blvd Curb Ext (NSG) | 2025-01-01 | Traffic Calming / AIL00001 | Milton St Burgener Blvd Curb Ext (NSG) / B22135 | 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TS | Ashrafzadeh, Mastaneh | Chan, Chun Yu | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Nov 1st |  | 2026-01-22 |  | 2026-01-22 | 2026-03-11 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-07-15 |  | 2025-07-15 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 723780 |  | 723780 |  | 1072200 |  | 1072200 | 723780 | -259700 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B24107 | TBD | TS Upgrades - Camino Ruiz & TX Madison | 2025-01-01 | TBD | TS Upgrades - Camino Ruiz & TX Madison / B24107 | 3, 6 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Xiao, Jie | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Nov 1st |  | 2026-04-02 |  | 2026-04-02 | 2025-07-15 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-09-19 |  | 2025-09-19 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 1200000 |  | 1200000 |  | 1805000 |  | 1805000 | 1200000 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20096 | AGF00007 | Willie Henderson Sports Complex Imp | 2025-01-01 | Park Improvements / AGF00007 | Willie Henderson Sports Complex Imp / B20096 | 4 | Buildings | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Kieser-Hua, Lin | Charter Only | Removed | Removed |  | Added - Aug 1st | FY26 |  | Removed - Oct 1st | Added - Aug 1st | FY26 |  |  |  | 2026-01-09 |  | 2026-01-09 | 2023-10-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-07-01 |  | 2025-07-01 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 13393226 |  | 13393226 |  | 18775465 |  | 18775465 | 2290000 | 14233465 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S21004 | S21004 | Rancho Bernardo Industrial Pump Stn Repl | 2025-01-01 | Rancho Bernardo Industrial Pump Stn Replacement / S21004 | Rancho Bernardo Industrial Pump Stn Repl / S21004 | 5 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Safavi, Ramin | Charter & Amendment | Removed | Removed |  | On Published List | FY26 |  | Removed - Aug 1st | On Published List | FY26 |  |  | 2025-04-02 | 2026-02-19 |  | 2026-02-19 | 2025-09-15 | FY25 | Q4 | FY26 | Q3 |  |  | FY26 | Q3 | 2024-09-19 | 2025-08-08 |  | 2025-08-08 | FY25 | Q1 | FY26 | Q1 |  |  | FY26 | Q1 | 8533000 | 9308762 |  | 9308762 | 13048000 | 15511809 |  | 15511809 | 9308762 | -0.5 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
B00032 | AKB00003 | Water Group 525C | 2025-01-01 | Main Replacements / AKB00003 | Water Group 525C / B00032 | 8 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Abdelmottaleb, Noha | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-04-15 |  | 2026-04-15 | 2024-03-27 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-10-14 |  | 2025-10-14 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 3632000 |  | 3632000 |  | 5474000 |  | 5474000 | 3268800 | 0 | 0.99 | 0.99 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B00131 | AKB00003 | Water Group 525E | 2025-01-01 | Main Replacements / AKB00003 | Water Group 525E / B00131 | 8 | Water | Design Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Abdelmottaleb, Noha | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-04-15 |  | 2026-04-15 | 2025-07-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-10-14 |  | 2025-10-14 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 3819600 |  | 3819600 |  | 6478000 |  | 6478000 | 3819600 | 320000 | 1.15 | 1.15 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B18077 | AKB00003 | Water Group 972 CI | 2025-01-01 | Main Replacements / AKB00003 | Water Group 972 CI / B18077 | 3, 8, 7, 9, 4 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Owen, Regan | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-04-30 |  | 2026-04-30 | 2022-05-06 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-10-17 |  | 2025-10-17 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 3468757.98 |  | 3468757.98 |  | 6255694.76 |  | 6255694.76 | 2837800 | 2093594.76 | 0.82 | 0.82 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B18236 | AGE00001 | Black Mountain Mine Remediation | 2025-01-01 | Resource Based Open Space Parks / AGE00001 | Black Mountain Mine Remediation / B18236 | 5 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Rummani, Zina | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-06-12 |  | 2026-06-12 | 2023-05-18 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-12-02 |  | 2025-12-02 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 545598 |  | 545598 |  | 1523857.5 |  | 1523857.5 | 565000 | 678857.5 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20008 | AJA00001 | Colina Del Sol Improv 1 (S) | 2025-01-01 | Sewer Main Replacements / AJA00001 | Colina Del Sol Improv 1 (S) / B20008 | 9 | Sewer | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Yelsits, Daniel | Charter & Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-03-04 |  | 2026-03-04 | 2025-07-31 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-21 |  | 2025-08-21 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 10164535 |  | 10164535 |  | 16311869 |  | 16311869 | 8316033.3 | 0 | 0 | 0 | 1.74 | 1.74 | No | No | No | No | No | No | No | No | No | No | Yes
B20010 | AKB00003 | Colina Del Sol Improv 1 (W) | 2025-01-01 | Main Replacements / AKB00003 | Colina Del Sol Improv 1 (W) / B20010 | 9 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Drainage | Straughn, Jayna | Yelsits, Daniel | Charter & Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-03-04 |  | 2026-03-04 | 2025-07-31 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-21 |  | 2025-08-21 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 7464500 |  | 7464500 |  | 12165952 |  | 12165952 | 6113289.6 | 0 | 1.28 | 1.28 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B21053 | ABI00001 | Otay WTP Raw Water PS Slope Restoration | 2025-01-01 | Water Treatment Plants / ABI00001 | Otay WTP Raw Water PS Slope Restoration / B21053 | 8 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_Dams | Van Martin, Debbie | Hawk, Gavin | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-02-06 |  | 2026-02-06 | 2024-11-01 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-07-29 |  | 2025-07-29 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 5657750 |  | 5657750 |  | 10323033 |  | 10323033 | 5553200 | 2319833 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B21102 | AIG00001 | Carmel Mtn @ Carmel Country Roundabout | 2025-01-01 | Median Installation / AIG00001 | Carmel Mtn @ Carmel Country Roundabout / B21102 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Leon, Heidi | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-05-15 |  | 2026-05-15 | 2023-10-02 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-11-03 |  | 2025-11-03 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 3222000 |  | 3222000 |  | 3932100 |  | 3932100 | 2502600 | 719400 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B22149 | AIH00001 | Installation of City Owned SL 2201 (NSG) | 2025-01-01 | Installation of City Owned Street Lights / AIH00001 | Installation of City Owned SL 2201 (NSG) / B22149 | 8, 9, 4 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_SSD | Zhang, Dayue | Xiao, Jie | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-06-08 |  | 2026-06-08 | 2025-03-03 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-11-25 |  | 2025-11-25 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 600000 |  | 600000 |  | 957000 |  | 957000 | 393570 | 255200 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B19069 | AIL00005 | Traffic Signal Mods Grp 19-01 | 2025-01-01 | Traffic Signals - Modify & Modernize / AIL00005 | Traffic Signal Mods Grp 19-01 / B19069 | 7, 9, 2 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_UUS | Barhoumi, Zach | Lasaga, Fernando | Charter Only | Removed | Removed |  |  | FY27 |  | Removed - Aug 1st | Added - Aug 1st | FY27 |  |  |  | 2026-06-24 |  | 2026-06-24 | 2022-08-04 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2025-12-11 |  | 2025-12-11 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 1850000 |  | 1850000 |  | 2637100 |  | 2637100 | 320300 | 2081700 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B16111 | ACC00001 | Green Infrastructure Group 1012 | 2025-01-01 | Stormwater Green Infrastructure / ACC00001 | Green Infrastructure Group 1012 / B16111 | 4 | Storm Water Drainage | Design Bid Build | Stormwater | Storm Water | SWD | Dastgheibi, Sara | Hosseini Shakib, Iman | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Dec 1st |  | 2026-03-04 |  | 2026-03-04 | 2025-12-24 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2025-08-21 |  | 2025-08-21 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 1958595.56 |  | 1958595.56 |  | 4477215.31 |  | 4477215.31 | 1958595.56 | 0 | 0 | 0 | 0 | 0 | No | Yes | No | No | No | No | No | No | No | No | Yes
S10008 | S10008 | El Monte Pipeline No. 2 | 2025-01-01 | El Monte Pipeline No 2 / S10008 | El Monte Pipeline No. 2 / S10008 | 7 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_F2 | Rubalcava, Eric | Bustamante, Ramesis W | Charter & Amendment | Removed | Removed |  |  | FY27 |  | Removed - Aug 1st | Added - Aug 1st | FY27 |  |  |  | 2025-11-26 |  | 2025-11-26 | 2022-08-01 | FY00 | Q3 | FY26 | Q2 |  |  | FY26 | Q2 |  | 2025-07-02 |  | 2025-07-02 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 74000000 |  | 74000000 |  | 92099966 |  | 92099966 | 15867067 | 67100015 | 0.07 | 0.07 | 0 | 0 | No | No | Yes | No | No | No | No | No | No | No | Yes
L22000.1 | L22000 | Alvarado Laboratory Improvements Phase 1 | 2025-01-01 | Alvarado Laboratory Improvements / L22000 | Alvarado Laboratory Improvements Phase 1 / L22000.1 | 7 | Buildings | Design Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Rummani, Zina | Charter Only | Removed | Advertised | Yes |  | FY27 |  | Removed - Aug 1st | Added - Aug 1st |  |  |  |  | 2026-11-12 |  | 2026-11-12 | 2026-04-01 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-01-29 | 2024-07-11 | 2024-07-11 | FY00 | Q3 | FY26 | Q3 | FY25 | Q1 | FY25 | Q1 |  | 111263361 |  | 111263361 |  | 163205603.7 |  | 163205603.7 | 80030700 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B21070 | ABT00003 | Solar Implementation @ EMTS Lab Bldg | 2025-01-01 | Citywide Energy Improvements / ABT00003 | Solar Implementation @ EMTS Lab Bldg / B21070 | 2 | Buildings | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Hossan, Farhad | Charter Only | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-11-03 |  | 2026-11-03 | 2025-11-04 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-01 |  | 2026-05-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2930204 |  | 2930204 |  | 4200585.39 |  | 4200585.39 | 2007900 | 1248739.5 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S21003 | S21003 | EMTS Lab Remodel at NTC | 2025-01-01 | Enviro Monitoring Tech Svcs Div Lab Remodel at NTC / S21003 | EMTS Lab Remodel at NTC / S21003 | 2 | Buildings | Design Bid Build | Public Utilities | Facility & Parks Project Delivery | FPPD_PB2 | Lozano, Edgar | Hossan, Farhad | No Project Charter or Amendment | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  |  |  | 2026-11-03 |  | 2026-11-03 | 2025-11-04 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-05-01 |  | 2026-05-01 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 38352047 |  | 38352047 |  | 54125501 |  | 54125501 | 21971700 | 21685499.78 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20142 | AIG00001 | 6th Ave @ Juniper St Roundabout | 2025-01-01 | Median Installation / AIG00001 | 6th Ave @ Juniper St Roundabout / B20142 | 3 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Leon, Heidi | Charter Routing | Removed | Removed |  |  | FY26 |  | Removed - Aug 1st | Added - Aug 1st | FY26 |  | Removed - Nov 1st |  | 2026-08-14 |  | 2026-08-14 | 2023-01-03 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2025-09-26 |  | 2025-09-26 | FY00 | Q3 | FY26 | Q1 |  |  | FY26 | Q1 |  | 1606300 |  | 1606300 |  | 2835000 |  | 2835000 | 1119100 | 1285000 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
L23001.1 | L230011 | El Camino Real Pipeline North | 2025-01-01 | El Camino Real Pipeline North / L230011 | El Camino Real Pipeline North / L23001.1 | 1 | Water | Design Bid Build | Public Utilities | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Kiehler, Matthew | Charter Only | Removed | Removed |  | Added - Aug 1st | FY27 |  |  | Added - Aug 1st | FY27 |  | Removed - Nov 1st |  | 2026-08-03 |  | 2026-08-03 | 2024-07-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-02 |  | 2026-02-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2643850 |  | 2643850 |  | 3872567.5 |  | 3872567.5 | 1710000 | 885588 | 0.51 | 0.51 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
S00856 | S00856 | El Camino Real to ViaDeLaValle (1/2mile) | 2025-01-01 | El Camino Real to ViaDeLaValle (1/2 mile) / S00856 | El Camino Real to ViaDeLaValle (1/2mile) / S00856 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_Bridges | Rekani, Ronak | Randles, Jacob | Charter Amendment Only | Removed | Removed |  | Added - Aug 1st | FY27 |  |  | Added - Aug 1st | FY27 |  | Removed - Nov 1st |  | 2026-08-03 |  | 2026-08-03 | 2023-04-03 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-02 |  | 2026-02-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 69117148 |  | 69117148 |  | 102639440.3 |  | 102639440.3 | 19425981 | 64690047.3 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
L14005.1 | L14005 | Demolition of Loma Land Structures | 2025-01-01 | Sunset Cliffs Park Drainage Improvements / L14005 | Demolition of Loma Land Structures / L14005.1 | 2 | Parks | Design Bid Build | Parks & Recreation | Facility & Parks Project Delivery | FPPD_Pk3 | Oliver, Kevin | Kieser-Hua, Lin | Charter Only | Removed | Removed |  | Added - Aug 1st | FY27 |  |  | Added - Aug 1st | FY27 |  | Removed - Nov 1st |  | 2026-09-09 |  | 2026-09-09 | 2018-02-01 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-03-02 |  | 2026-03-02 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 1462500 |  | 1462500 |  | 3164990 |  | 3164990 | 320000 | 2311990 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | Yes | No | No | No | Yes
B22138 | AID00005 | Crespo Dr (Mecca-Soledad) Improv (P) | 2025-01-01 | Resurfacing of City Streets / AID00005 | Crespo Dr (Mecca-Soledad) Improv (P) / B22138 | 1 | Transportation | Design Bid Build | Transportation | Stormwater & Transportation Project Delivery | SWATPD_TM | Schultz, Louis | Sanfilippo, Scott | No Project Charter or Amendment | Removed | Removed |  | Added - Aug 1st | FY27 |  | Removed - Oct 1st | Added - Aug 1st | FY27 |  |  |  | 2026-09-23 |  | 2026-09-23 | 2024-12-17 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-03-27 |  | 2026-03-27 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 412920 |  | 412920 |  | 688400 |  | 688400 | 412920 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B23136 | ABL00001 | Miramar Reservoir Recreation Facilities | 2025-01-01 | Standpipe & Reservoir Rehabilitations / ABL00001 | Miramar Reservoir Recreation Facilities / B23136 | 5 | Water | Design Bid Build | Public Utilities | PUD Pure Water | PUD_PW | Martin, Reyhaneh | Rekani, Aras | No Project Charter or Amendment | Removed | Removed |  |  | FY27 |  | Removed - Aug 1st | Added - Aug 1st | FY27 |  |  |  | 2026-08-11 |  | 2026-08-11 | 2025-05-09 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2026-02-13 |  | 2026-02-13 | FY00 | Q3 | FY26 | Q3 |  |  | FY26 | Q3 |  | 2122858 |  | 2122858 |  | 3027142 |  | 3027142 | 1300000 | 300000 | 0 | 0 | 0 | 0 | No | Yes | No | No | No | No | No | No | No | No | Yes
B22130 | ACA00001 | Famosa Slough Alley Slope Restoration | 2025-01-01 | Flood Resilience Infrastructure / ACA00001 | Famosa Slough Alley Slope Restoration / B22130 | 2 | Storm Water Drainage | Design Bid Build | Stormwater | Storm Water | SWD | Eckert, Kristopher | Salvani, Anthony | Charter Only | Removed | Removed |  |  | FY27 |  | Removed - Aug 1st | Added - Aug 1st | FY27 |  |  |  | 2026-10-26 |  | 2026-10-26 | 2025-12-16 | FY00 | Q3 | FY27 | Q2 |  |  | FY27 | Q2 |  | 2026-04-17 |  | 2026-04-17 | FY00 | Q3 | FY26 | Q4 |  |  | FY26 | Q4 |  | 2104442 |  | 2104442 |  | 4277675 |  | 4277675 | 4164804 | -1403357 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
B20060 | AGF00007 | Chicano Park Improvements Phase III | 2025-01-01 | Park Improvements / AGF00007 | Chicano Park Improvements Phase III / B20060 | 8 | Parks | Job Order Contract | Parks & Recreation | Facility & Parks Project Delivery | FPPD_FID | Lewis, Nikki | Le, Hong Khanh | Charter & Amendment | Removed | Removed |  | On Published List | FY26 |  |  | On Published List | FY26 |  | Removed - Nov 1st | 2024-12-09 | 2026-12-03 |  | 2026-12-03 | 2024-02-16 | FY25 | Q2 | FY27 | Q2 |  |  | FY27 | Q2 | 2024-09-05 | 2026-11-18 |  | 2026-11-18 | FY25 | Q1 | FY27 | Q2 |  |  | FY27 | Q2 | 1202064.94 | 1202064.94 |  | 1202064.94 | 2024320.94 | 2024320.94 |  | 2024320.94 | 1088771 | 199999.94 | 0 | 0 | 0 | 0 | Yes | No | No | No | No | No | No | No | No | No | Yes
S00969 | S00969 | Carmel Country Road Low Flow Channel | 2025-01-01 | Carmel Country Road Low Flow Channel / S00969 | Carmel Country Road Low Flow Channel / S00969 | 1 | Storm Water Drainage | Design Bid Build | Stormwater | Storm Water | SWD | Salvani, Anthony | Salvani, Anthony | No Project Charter or Amendment | Removed | Removed |  |  | FY27 |  | Removed - Aug 1st | Added - Aug 1st | FY27 |  |  |  | 2027-03-10 |  | 2027-03-10 | 2027-02-03 | FY00 | Q3 | FY27 | Q3 |  |  | FY27 | Q3 |  | 2026-08-27 |  | 2026-08-27 | FY00 | Q3 | FY27 | Q1 |  |  | FY27 | Q1 |  | 2872402 |  | 2872402 |  | 6849729 |  | 6849729 | 2872402 | 0 | 0 | 0 | 0 | 0 | No | No | No | No | No | No | No | Yes | No | Yes | Yes
B19199 | AKB00003 | AC Water Group 1023A | 2025-01-01 | Main Replacements / AKB00003 | AC Water Group 1023A / B19199 | 3 | Water | Design Bid Build | Public Utilities | Utilities Project Delivery | UPD_WWS1 | Sleiman, Alex | Abdelmottaleb, Noha | Charter Only | Removed | Removed |  |  | FY28 |  | Removed - Aug 1st | Added - Aug 1st | FY28 |  |  |  | 2027-11-16 |  | 2027-11-16 | 2020-09-01 | FY00 | Q3 | FY28 | Q2 |  |  | FY28 | Q2 |  | 2027-06-08 |  | 2027-06-08 | FY00 | Q3 | FY27 | Q4 |  |  | FY27 | Q4 |  | 1000000 |  | 1000000 |  | 1754360 |  | 1754360 | 800000 | 573360 | 0.23 | 0.23 | 0 | 0 | No | No | No | No | No | No | No | No | No | No | Yes
Note on P3: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Awarded in FY24
Note on P4: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Awarded in FY24
Note on P5: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: No record of LNTP in FY24 as of today
Note on A41: [Threaded comment] Your version of Excel allows you to read this threaded comment; however, any edits to it will get removed if the file is opened in a newer version of Excel. Learn more: https://go.microsoft.com/fwlink/?linkid=870924 Comment: Confirm this project has not been LNTP'd previously. Mark as Awarded for now.

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only