## Sheet1
Energy Cooperation Agreement Implementation Plan Matrix
# | Energy Cooperation Agreement Implementation Plan Matrix | SDG&E Lead | City Lead | Ongoing Alignment | Future Milestones | Compliance Review Committee Status Update
5 | Clean Energy Collaboration Opportunities
5.a. | San Diego Community Power. SDG&E supports customer choice and the transition of energy procurement to local or state control. SDG&E agrees to follow the CCA Code of Conduct and to provide San Diego Community Power (“SDCP”) grid services and customer information in accordance with SDG&E Tariff Rule 27 and associated CPUC orders and proceedings. SDG&E has assembled and will continue to strengthen a dedicated team to act as the primary interface between SDG&E and staff from SDCP and other CCAs. SDG&E shares a goal with SDCP of making the customer experience as seamless as possible. | CCA Customer Programs | Sustainability | •SDG&E, SDCP & Calpine met September 16, 2021 to conduct a debrief on transition efforts so far, celebrate what we did well and discuss areas where we can jointly improve. | Continue to support our 5 shared goals: • Supporting customer choice and the transition of energy procurement to regional CCA partners • Making the customer experience as seamless and easy as possible, being responsive to customer needs. • Formation and support of dedicated and collaborative teams working together across all partners and support organizations • Compliance and strategic alignment – working together through Commission rules and Decisions to advocate for what’s best for our region • Ongoing data and information sharing to ensure operational success and customer benefits. • If requested, SDG&E will provide input and/or collaborate with SDCP on the development of the Community Power Plan in 2022. | SDG&E is working closely with SDCP on tranfering customers by municipality from February to May 2022.
5.b. | Evaluate Energy Efficiency and Demand Response Opportunities with SDCP. SDG&E will cooperatively work with the City, SDCP and third-party statewide implementers to identify energy efficiency and demand response programs which the City and SDCP may administer or in which they may participate. | Customer Programs | Sustainability | •San Diego Community Power discussed options at their September 2021 board meeting for establishing energy efficiency programs after Phase 3 enrollment is complete. Two options for accessing CPUC funds for this work include electing to serve as a Program Administrator, or forming a Regional Energy Network with another public agency. | • SDG&E plans to collaborate with SDCP on their opportunities moving forward - this is part of our larger ongoing partnership with SDCP.
5.c. | Enhanced Tree Planting. SDG&E will continue to support the City’s tree planting efforts through SDG&E’s Right Tree, Right Place program (or successor programs),and identify additional tree planting locations, assist with tree species ideas, and provide technical support through SDG&E’s highly trained arborists. SDG&E plans to supplement the City’s efforts with direct in-community charitable support for planting up to 2,500 trees in the City in the ten years following the Effective Date. The City may claim any GHG credits that may be earned for this program. | Vegetation Management & Community Relations | City Arborist | • Partnership with San Diego Parks Foundation. Trees were planted in the following City of San Diego parks: Mountain View Community Park (21 trees, Jan./Feb. 2021), Southcrest Community Park (32 trees, Sept. 2021) and Montclair Neighborhood Park (23 trees,Dec. 2021). • Partnership with Downtown San Diego Partnership, planting 10 street trees in East Village (began Apr. 2021, to continue in 2022) • Tree planting event and community tree giveaway in partnership with Forever Balboa Park, planting 10 trees in Balboa Park and distributing more than 300 saplings to park visitors (Nov. 2021). • Partnership with SD River Park Foundation to plant 40 native trees in the riparian area in Mission Valley (May 2021). • Partnership with SD Unified School District and Healthy Day Partners to plant 29 fruit trees at school gardens in SDUSD (May-Nov. 2021). | • 400 trees in Cherokee Point, including door-to-door bilingual canvassing, park event for community education and tree sign-up, and planting street trees to begin in Spring 2022. • Implementing of a comprehensive tracking system with Davey tree that documents our progress; including number, type, location of tree to be report to Sustainability Department for GHG tracking. • District Wide Tree Planting identifying parks where districts would like trees planted. • Park event to educate community and do a tree sign up. • Allied Gardens - identifying and moving forward on street trees after Cherokee Point wraps up (2022-2023). | Reporting out of Cherokee Point tree planting; timeline development for future tree planting sites.
5.d. | Expand Green Waste Recycling. SDG&E and the City will work to identify vendors open to receiving green waste, which can help reduce the City’s carbon footprint by diverting waste from landfills. Furthermore, SDG&E and the City will investigate the opportunity to utilize this diverted waste as a fuel source as such technologies become available and feasible, potentially reducing GHG emissions. | Vegetation Management | Sustainability | • SDG&E currently tracks waste tonnage diversion; specifically, total tonnage delivered to landfill vendors and the percentage of that diverted to recycling material. • In addition, SDG&E has two 100% recycling vendors where our tree trimming contractors deliver green waste material. | • City and SDG&E teams to explore waste as a fuel source in 2030 once technology capabilities become availabile. | Share successes of vendors that SDG&E works with to expand the City's efforts for green waste recycling.
5.e. | Expand Clean Transportation Efforts. SDG&E will assist in the expansion of the City’s municipal electric or alternate-fuel fleet by providing SDG&E’s clean transportation expertise to the City through facilitated best practices training and will provide data and support for the Mayoral Executive Order to increase electric vehicle acquisition. Building on the more than 1900 vehicle chargers that SDG&E has already installed in the City, including multiple chargers at five City-owned facilities, SDG&E will continue to pilot additional vehicle electrification programs in and around the City, including chargers at schools, beaches and parks. | Clean Transportation & Policy Initiatives | Sustainability | • Accelerate to Zero (A2Z) Emissions Collaboration Coalition partners released a San Diego Regional Electric Vehicle (EV) Gap Analysis in late July 2021. • SDG&E’s Power Your Drive (PYD) program has installed over 3,000 EV charging stations across its service territory in multi-unit dwelling properties and commercial locations. • SDG&E currently offers a fleet electrification program, Power Your Drive for Fleets (PYDFF), and is investigating other potential pilot program opportunities related to public charging. | • A2Z Emissions Collaboration will develop and implement an EV Strategy that exceeds state goals and positions the region as a national leader on EVs. The Regional EV Strategy is expected to be complete in late 2022 or early 2023. • The PYD Extension program will encourage the deployment of additional EV charging stations at workplaces and multi-unit dwellings throughout the region. • SDG&E Clean Transportation team is conducting research and assessing future pilot opportunities related to fleet electrification and potential public right-of-way charging. Looking to collaborate with the City starting in Q3 2022. | Report on the regional EV strategy when it becomes available in late 2022 or early 2023; we anticipate begnning conversations in late 2022 on the City's medium to heavy fleet conversion. 4/7/2022 SDG&E hosted an EV Fleet Day.
5.f. | Energy Benchmarking. SDG&E will provide information and assistance to City staff to support the continued implementation of AB 802 benchmarking and the CEC’s associated regulations and requirements to track building energy efficiency in support of the City’s Climate Action Plan. | Customer Programs | Sustainability | • City of San Diego is ranked 14th Nationwide for National Benchmarking. • SDGE supported the Make Your Mark Campaign aimed at reducing Co2. • SDG&E helped with outreach to small businesses to comply with their benchmarking ordinance. • Held seminars with Center for Sustainable Energy to provide training to all the small businesses within City of San Diego's targeted zip codes. • In the past to further support the City's Make Your Mark Campaign, SDG&E made a donation to Ocean Discovery Institute (July 2020) for every business who voluntarily shared their energy usage to the city of San Diego for the Energy Efficiency Benchmarking. | • We will continue to actively communicate and partner with the City to maintain and advance the City's national ranking. • Onboarding of new businesses to begin in 2025. • SDG&E and the City will review the plan every five years.
5.g | Municipal Energy Strategy. SDG&E will help the City implement its Municipal Energy Strategy to reduce GHG emissions at all municipal buildings and facilities, including, without limitation, by administering energy audits, supporting the electrification of municipal buildings, seeking appropriate energy efficiency measures to reduce facility energy usage, and providing the City reports on energy usage in municipal buildings to compare use over time. | Customer Programs | Sustainability | • SDGE & City of SD previously had a 5 year Local Government Partnership. • The contract support 53 comprehensive audits performed by SE Engineers. • These audits can support future efforts to reduce GHG and implement in our future Climate Action plan implementation. | • Business Services will continue to help guide the City to programs available administered by SDG&E and by third-parties vendors/contractors. • Programs such as Federal Accounts Turnkey Program, Green Button Connect Tool, My Account, and our demand response programs. • SDG&E and the City will review the plan every five years.
5.h. | GHG Reduction Analysis. City and SDG&E shall work collaboratively to identify and study areas where electrification can be accelerated towards the achievement of the City’s climate action goals, while keeping affordability in mind and without causing economic disruption. | Environmental Services | City Fire & Climate Experts | • Share GHG inventory with City. • Use the Smart calculator to help find efficiencies and optimization around electrification. | • Highlight GHG reduction analysis through electrification. • Leverage identified GHG reduction opps to inform development of electrification/decarbonization programs offered by SDGE. • SDG&E and the City will review the plan every five years beginning in 2024. | SDG&E will share findings from GHG white paper released 4/5/2022
6 | Safe Energy Collaboration Opportunities
6.a. | Wildfire Safety. SDG&E will continue to develop and refine its nation leading weather network to provide hyper-localized situational awareness of potential weather threats to residents, businesses, the energy delivery system and the region. SDG&E will continue to provide fire-fighting air resources to protect the City and SDG&E’s entire service territory. SDG&E will investigate the deployment of weather stations and other technologies, such as tools to measure vegetation growth, color and hydration to further inform SDG&E’s state-of-the art fire risk index, as well as monitoring canyons where fires may be more likely to ignite and spread quickly. This information will be shared with City and County fire departments to provide real-time data for pending weather events and to create additional situational fire awareness. | Wildfire Mitigation & Emergency Management | City Fire & Climate Experts | • Provided funding for Community Emergency Response Teams and Fire Safe Councils in communities of concern across San Diego. • SDG&E sends regular fire potential forecasts and outlooks with the city and county fire departments. • SDG&E Emergency Management and City of San Diego Fire Chief Colin Stowell met on Jan. 19 2021 to discuss a general plan to establish joint training and exercise opportunities between his department and SDG&E related to: ​Aerial firefighting​; Incident communications​; Developing and implementing a plan to conduct tours​; Familiarization flights toward safe and successful missions within the City​; Ensure that clear processes and procedures are documented for ordering air support from the City to CalFIRE who is the SDG&E aerial firefighting dispatch agency​. •These will be ongoing, annual processes. The next step toward this objective is to clearly outline the program and begin scheduling the training, exercise, and tour/flight coordination. | • Continue support of Community Response Teams and Fire Safe Councils in underserved communities. • Improve communication around data and predictive information. Formalize how SDG&E shares with the City. Attend town councils to present on wildfire safety and best practices | SDG&E to proivde updates on the ongoing relationship.
6.b. | Increase Safety and Resiliency through Energy Intelligence. SDG&E will share intelligence and data from SDG&E meteorology teams and academic research partners identifying the areas of the City where undergrounding may be most beneficial for wildfire mitigation to inform the City’s sequencing of undergrounding projects. | Emergency Management & Regional Public Affairs | City Fire & Climate Experts | • SDG&E in process of building the data sharing infrastructure. • Ongoing identification of Canyonlands Wildfire Risk and undergrounding of critical infrastructure in these areas around the city. | • Continue to add intelligence and data to this data sharing platform. | SDG&E to report on fire hardening transition projects within the City.
6.c. | Facilitate Development of 100% Virtual EOC and City Outreach. SDG&E will lend its expertise to support development of the City’s Virtual Emergency Operations Center (“EOC”) to reduce reliance on physical presence and manage emergencies remotely. SDG&E staff will also attend town council and other public meetings to discuss SDG&E’s approach to wildfire management and share best practices for wildfire safety, including following public-safety power shut-off events. | Emergency Management | City Office of Emergency Services | • SDG&E meets regularly with the City of San Diego's Emergency Management team to discuss the virtual EOC and share best practices. •SDG&E presented to the Loire Valley Homeowner's Association on Jan. 18, 2021 on fire safety. •On Jan. 19, 2022, SDG&E and City teams met to review the SDG&E Virtual EOC program and processes. The City will continue to meet with SDG&E Virtual EOC subject matter experts to gather more information that may assist them in designing, developing and implementing a successful and safe Virtual EOC. | • SDG&E's Public Affairs team will work with Emergency Management to present information on wildfire safety, including public safety power shutoff events, in public meetings and at 4 community groups per year. •SDG&E will continue to meet with the City EOC team to share information on Virtual EOC design, development, and implementation. | SDG&E can offer a tour of our EOC; and report back on the status of meetings with the City.
6.d. | Develop Resiliency Review. SDG&E and the City will collaborate to review the resiliency of the City’s existing infrastructure and make recommendations to enable the City to better manage the impacts of climate change, especially with respect to wildfires and sea level rise, including, without limitation, the development of an inventory of critical municipal infrastructure. | Emergency Management | City Fire & Climate Experts | •SDG&E is committed to collaborating with the City as we continue to establish and conduct our vulnerability assessment of all our assets. •SDG&E partnered with Scripps Institute in of Oceanography in 2021 to improve risk assessment models using the best available science for the protection of SDG&E’s operations and infrastructure from coastal flooding and wildfires exacerbated by the climate crisis. We could consider expanding those efforts. | •Undergrounding of critical infrastructure to begin in 2022 (legacy projects), with new projects breaking ground in 2023. • Review to begin in 2024 and to be revisted in 2034.
7 | Reliable Energy Cooperation Opportunities
7.a. | Finalize & Refresh Central Dashboard for Energy Management. SDG&E will assist the City in developing a centralized dashboard to manage City-wide energy usage from its facilities, meters and accounts. SDG&E will work with third-party implementers and energy audit experts to support the City in reducing energy use where possible. | Customer Programs | Sustainability | • This Energy Dashboard was created in 2019 as part of the City of SD / SDG&E Executive Tiger Team. The City of SD dashboard is an application designed to perform analysis by aggregating and comparing data for 457 targeted accounts across various specified departments (these accounts were identified by the City). The purpose of the dashboard is to provide quick and easy access to critical energy use/costs; perform comparative financial analysis between different levels of the customer's departments yearly, monthly, and daily energy use/costs; estimate usage; and compare performance between single versus group accounts. Business services is currently collaborating with the City on enhancements to the dashboard. | •SDG&E will collaborate with the City’s Sustainability Department to expand dashboard accessibility and functionality across City departments. •Targeted to begin in 2024 and the plan will be reviewed every four years.
7.b. | CCA Cooperation. Facilitate Microgrid Development for City Water, Wastewater & Sewer Infrastructure Projects. SDG&E will share with the City expertise relating to facility and community-level microgrids to improve the resiliency of selected City facilities and neighborhoods. SDG&E will work with the City and SDCP to identify an appropriate distributed energy resources (“DER”) project for development within the City. If a mutually agreed project is identified, SDG&E will submit an application to the CPUC seeking any required approval for such project. The City agrees that it will make reasonable efforts to support such application at the CPUC. | CCA Customer Programs | Sustainability | • SDG&E will file its Microgrid Incentive Program (MIP) Implementation Plan by October 4, 2021. Prior to commencing the program, we must receive CPUC approval. Current estimate is that it will be approved Q1 or Q2 2022. Once the program is approved, we can start the technical consultations with communities, local governments, tribal governments, or other stakeholders. For context, the MIP is intended to provide funding for clean energy microgrids for vulnerable communities impacted by grid outages. | • Look at future Microgrid Incentive Program – targeting supporting vulnerable communities, including critical facilities, impacted by grid outages • Collaborate with the City to determine whether Governor’s Proclamation and Amended Scoping Ruling on Procurement provide additional opportunities for partnership on microgrids. • Program to be reviewed in 2025 and 2033.
7.c. | CCA Cooperation. Assist the City with Demand Response and Distributed Energy Resources (DER) Efforts. SDG&E will work with the City and SDCP to identify potential demand response or DER projects that may be available to the City pursuant to CPUC programs or through third parties. If a mutually agreed upon project is identified, SDG&E will submit an application to the CPUC seeking any required approval for such project. The City agrees that it will make reasonable efforts to support such application at the CPUC. | CCA Customer Programs | Sustainability | • Distributed Energy Resources (DER) Action Plan 2.0 proceeding is moving forward at the CPUC and set for a decision Q4 2021. The Commission is looking at moving 4 tracks forward: Load Flexibility and Rates, Grid Infrastructure, Market Integration & DER Customer Programs. | • The draft DER Action Plan 2.0 is pending placement on a future CPUC agenda for vote. • Program to be reviewed in 2025 and 2033.
8 | Equitable Energy Cooperation Opportunities
8.a. | Equity-Focused Solar Expansion: SDG&E shall work with the City of San Diego’s Environment Committee to define the program, outcomes, timeline around the equity focused solar program. SDG&E shall execute the approved program with non-profit organization of SDG&E’s choosing to build a program or supplement an existing program designed to increase the number of income-qualifying residential customers with access to solar. SDG&E commits to spend $1,000,000 of annual shareholder contributions in each of the first ten City fiscal years the Electric Franchise is in effect. As a condition of its contribution to the non-profit organization, SDG&E will require the non-profit organization to make available unused funds from a given year in future years. Such funds may be used for incentives, refunds, equipment, labor, program management and administration. | Commercial Council, Customer Programs & Regional Public Affairs | Council Engagement & Sustainability | • Center for Sustainable Energy (CSE) and SDG&E are finalizing a scope of work to expand access to solar for income-qualifying customer encouraging broad participation of income-qualified residential customers in disadvantaged and low-income communities (referred locally to as communities of concern) in the City of San Diego. • SDG&E and Center for Sustainability met Nov. 2021 and Jan. 2022 with Council Offices 7 and 9 to seek input on the program. | • Center for Sustainable Energy will take a targeted approach to ensure that benefits flow directly to income-qualified residential customers who stand to benefit the most from utility bill savings and improved air quality • SDG&E and Center for Sustainability will continue to update Council Offices as this program processes • Anticipated launch in Summer 2022 | SDG&E will report on the launch and status of the program.
8.b. | Affordable Housing. SDG&E understands that utility design and coordination is critical to ensuring a steady supply of new housing in the City, and that the City is focused on enhancing housing supply. SDG&E agrees to begin tracking affordable housing utility design applications within the City, and to create a dashboard that tracks utility coordination and completion timing. Additionally, SDG&E agrees to support operational enhancements related to more rapid affordable housing development. | Design & Project Management | Sustainability |  | • We can begin construction of the dashboard in 2022.
8.c. | Encourage Diversity in Local Clean Energy Workforce. SDG&E will aid local workforce development organizations to identify underserved populations to launch the careers and develop the next generation of clean energy infrastructure leaders | Staffing & Diversity Outreach & Community Relations | Sustainability | •SDG&E has met with labor partners in Nov. 2021 and Jan. 2022 to discuss current programs and opportunities. | •SDG&E would like to work with San Diego Energy Equity Campus economic and environmentally sustainable hub for all south San Diego residents. SDG&E hopes to support programming, provide knowledge sharing ,and technical capacity building at the renewable energy campus. •Identifying pre-apprenticeships and workforce readiness programs to sponsor in underserved communities.
8.d. | Undergrounding Prioritization. The City and SDG&E acknowledge the success of the ongoing electric distribution undergrounding program. A majority of the electric system in the City has already been undergrounded. However, the City and SDG&E acknowledge that there is more work to be done. SDG&E and the City will cooperate to refresh the City-driven accelerated undergrounding program to prioritize projects in communities of concern. | Design & Project Management | Streets | • Undergrounding Memorandum of Understanding (MOU) passed unanimously through the Environment Committee on Jan 20, 2022. • Undergrounding Memorandum of Understanding (MOU) goes to Full Council on Feb. 15, 2022 | • Legacy projects continued in 2022, with new projects beginning in 2023. | SDG&E will report on the status of legacy projects and projected launch of new projects.
8.e. | Energy Efficiency Campaign within Communities of Concern. SDG&E will work with the City to expand outreach to low-income and hard-to-reach customers eligible for SDG&E’s Energy Assistance Residential programs and other programs for low-income customers via targeted marketing and other appropriate mechanisms. | Customer Programs | Sustainability | • Prior to the pandemic, SDG&E Business Services and the City had begun preliminary outreach to small businesses in San Ysidro and Nestor promoting Business Energy Solutions and Rate Comparisons (Right Rate, Right time). | •Identifying and containing our efforts in Communities of Concern to conduct business outreach to small businesses on Energy Efficiency and Bill saving opportunity programs, to begin in 2023.
8.f. | State & Federal Grants. The City and SDG&E will research available local, state and federal government and agency grants to identify projects that could help the City meet its climate action, equity and resiliency goals, with a focus on communities of concern, including grants or programs from the California Energy Commission, CPUC and the Department of Energy. | Advanced Technology Integration | Sustainability | • SDG&E approached the City to assist City in maintaining a grant from the FEMA Building Resilient Infrastructure and Communities (BRIC) Grant Project. • SDG&E approeached the the City to assist the City in an application for Infratructure Investment and Jobs Act funding for a Community of Concern Modernization. | • SDG&E will continue to partner with the City on applicable grants as they arise; including opportunities around clean transportation. | SDG&E will report on any opportunities, should they arise.
9 | Ensuring Transparency
9.a. | Rate Transparency. Once a year, SDG&E shall offer to present to the Council on rate structure, planned rate filings and rate changes. | Customer Pricing & Regional Public Affairs | Council President's Office | • Presenation occurred 12/7/21. SDG&E has begun internal efforts to accurately and effectively explain our current rate structures.SDG&E is planning to include gas rates and GRC specific explanantions. | • Offer made in June 2022, presentation target date of mid September 2022 to full Council. | SDG&E to provide rates overview to CRC.
9.b. | Major Projects & Undergrounding. Twice a year, SDG&E shall offer to present to the appropriate City Council Committee on planned major energy and gas projects, status of undergrounding projects, and 20SD undergrounding fund collections. | Regional Public Affairs, Design & Project Management & Regional Public Affairs | Environment Committee | • 1st meeting of 2022 ocurred with Undergrouding MOU Envirnment Committee on January 20th and approved at full council February 15th 2022. | • October 13th 2022 to Environment Committee | SDG&E to provide undergrounding overview to CRC.
9.c. | Supporting Customer Equity. Once a year, SDG&E shall offer to present to the appropriate City Council Committee a status update on the distribution of regulated public purpose program (PPP) funds within the City, including CARE, FERA,LIHEAP, energy efficiency, lighting programs, demand response and others as appropriate. | Customer Programs & Regional Public Affairs | Land Use & Housing Committee | • Sustainability dicussing alternative committee options with the Mayor's office. | • Special Environment Meeting in November, unless alternative committee is assigned from the City to SDG&E. | SDG&E to provide customer equity overview to CRC.
9.d. | Supporting Climate Equity. Twice a year, SDG&E shall offer to present to the appropriate City Council Committee on the ways SDG&E is supporting the City’s Climate Action Plan goals, SDG&E’s support for SDCP, and other projects SDG&E is working on to support GHG reduction efforts | Environmental Services & Regional Public Affairs | Environment Committee | • First Presentation made at Environment Committee on May 26th, 2022. | • November post monitoring report of CAP 2.0 | SDG&E to provide climate equity overview to CRC.
9.e. | Supporting Municipal Staff & Operations. Four times a year, an Officer of SDG&E shall offer to meet with the City’s Chief Operating Officer (or designees, if requested by the COO), to discuss infrastructure projects, coordination on facility movement and relocation, municipal energy bills, account questions/management, and other topics of mutual concern. The COO, or designated City staff, will present an annual information item to the appropriate City Council Committee providing an overview of the quarterly meetings with SDGE. | Regional Public Affairs | COO's Office | •The first quarterly meeting between Scott Crider, our Senior VP of Customer Service and External Affairs, and Jay Goldstone, the City’s Chief Operating Officer took place on 9/21. The topic of the meeting was to discuss infrastructure projects, coordination on facility movement and relocation, municipal energy bills, account questions/management, and other topics of mutual concern. The meeting was very productive and RPA is working on providing additional information requested from City staff. •Subsequent meetings tookplace March 10th and June 7th. | • Scheduled COO Meetings September 20th and December 9th of 2022.
9.f. | Compliance Review Committee. At least once a year, SDG&E will provide an update to the Compliance Review Committee on the implementation of this Agreement. | Regional Public Affairs | COO's Office & Intergovernmental Affairs | • Resolution for establishing a Franchise Compliance Review Committee (CRC) June 21st, 2022. | • Nominations are due from Council by July 7th, 2022. Established by July 8th, 2022.