## Forecast of Projects
Line Number | Project Name | Project Name (Text) | Project Number | Asset Managing Department | Contract Type | Estimated Total Contract Cost ($) | Estimated Total Project Cost ($) | Fiscal Year Advertising | Quarter Advertising | Fiscal Year Awarding | Quarter Awarding
1 | Block 8R UUP | Block 8R UUP | 21003599 | Transportation & Storm Water | Design Bid Build | 7929999.965 | 10705499.6271 | FY20 | Q2 | FY21 | Q1
2 | Rancho Penasquitos Paving Group 1 | Rancho Penasquitos Paving Group 1 | B20138 | Transportation & Storm Water | Job Order Contract | 3286393.08 | 3779352.042 | FY20 | Q4 | FY21 | Q1
3 | PHR Pump Track Fence | PHR Pump Track Fence | B20031 | Parks & Recreation | Emergency (As-needed) | 274902.9997 | 274902.9997 | FY21 | Q1 | FY21 | Q1
4 | Sewer & AC Water Group 763 (S) | Sewer & AC Water Group 763 (S) | B00374 | Public Utilities | Design Bid Build | 8986036.06 | 10611812.9784 | FY21 | Q1 | FY21 | Q4
5 | Sewer and AC Water Group 812 (S) | Sewer and AC Water Group 812 (S) | B00426 | Public Utilities | Design Bid Build | 3047000 | 5304265.55 | FY21 | Q1 | FY21 | Q3
6 | Rolando Improv 1 (W) | Rolando Improv 1 (W) | B20126 | Public Utilities | Design Bid Build | 4336299.9997 | 6201099.9986 | FY21 | Q2 | FY21 | Q3
7 | High Purity Oxygen Addition System PQPS | High Purity Oxygen Addition System PQPS | B21001 | Public Utilities | Design Bid Build | 1933000 | 2416250 | FY21 | Q2 | FY21 | Q4
8 | AC Overlay Group 2012 MM/RP | AC Overlay Group 2012 MM/RP | TBD | Transportation & Storm Water | Design Bid Build | 3992691.4773 | 4697284.0909 | FY21 | Q3 | FY21 | Q3
9 | AC Overlay Group 2016 Navajo G2 | AC Overlay Group 2016 Navajo G2 | TBD | Transportation & Storm Water | Design Bid Build | 4707300 | 5538000 | FY21 | Q3 | FY21 | Q3
10 | AC Overlay Group 2014 Southwest | AC Overlay Group 2014 Southwest | TBD | Transportation & Storm Water | Design Bid Build | 8884200 | 10452000 | FY21 | Q3 | FY21 | Q4
11 | AC Overlay Group 2015 Southeast | AC Overlay Group 2015 Southeast | TBD | Transportation & Storm Water | Design Bid Build | 7094100 | 8346000 | FY21 | Q3 | FY21 | Q4
12 | Sidewalk Replacement Group 2030 | Sidewalk Replacement Group 2030 | TBD | Transportation & Storm Water | Design Bid Build | 1500000 | 1800000 | FY21 | Q3 | FY21 | Q4
13 | Palm Ave Storm Drain | Palm Ave Storm Drain | B17163 | Transportation & Storm Water | Job Order Contract | 288700 | 393815 | FY20 | Q4 | FY21 | Q2
14 | Cardinal Road Emergency SD Replacement | Cardinal Road Emergency SD Replacement | B19090 | Transportation & Storm Water | Sole Source Emergency | 106700 | 5150000 | FY19 | Q2 | FY21 | Q1
15 | Market Street-47th to Euclid-Complete Street | Market Street-47th to Euclid-Complete Street | S16061 | Transportation & Storm Water | Design Bid Build | 6110156.8948 | 9719908.7477 | FY19 | Q4 | FY21 | Q1
16 | ADA S/W Group 4E College | ADA S/W Group 4E College | B16107 | Transportation & Storm Water | Design Bid Build | 360000 | 862080.9997 | FY20 | Q3 | FY21 | Q1
17 | 5865 Cozzens Street SD Emergency | 5865 Cozzens Street SD Emergency | B20068 | Transportation & Storm Water | Emergency (As-needed) | 40629.2 | 749999.9998 | FY20 | Q2 | FY21 | Q1
18 | MBGC Clubhouse Demo/Prtbl Building Instl | MBGC Clubhouse Demo/Prtbl Building Instl | S01090 | Parks & Recreation | Design Bid Build | 4770578 | 7399999.9888 | FY20 | Q2 | FY21 | Q3
19 | MBGC Irrigation & Electrical Upgrades | MBGC Irrigation & Electrical Upgrades | S11010 | Parks & Recreation | Design Bid Build | 2807051 | 4459999.7998 | FY20 | Q2 | FY21 | Q3
20 | SEWER GJ 798C | SEWER GJ 798C | B00409 | Public Utilities | Design Bid Build | 212419.9998 | 590884.9995 | FY20 | Q4 | FY21 | Q2
21 | District 1 Block 1-J UUD | District 1 Block 1-J UUD | B00836 | Transportation & Storm Water | Job Order Contract | 422809 | 971808.85 | FY20 | Q3 | FY21 | Q3
22 | Block 8R UUP - CIP | Block 8R UUP - CIP | B15097 | Transportation & Storm Water | Design Bid Build | 1113999.9967 | 1463999.9961 | FY20 | Q2 | FY21 | Q2
23 | Nimitz Bridge at NTC Rehabilitation | Nimitz Bridge at NTC Rehabilitation | B15198 | Transportation & Storm Water | Design Bid Build | 344665.9999 | 929999.9999 | FY20 | Q4 | FY21 | Q1
24 | Sewer Group 776A | Sewer Group 776A | B16034 | Public Utilities | Design Bid Build | 4194279 | 5780973.9933 | FY20 | Q3 | FY21 | Q2
25 | ADA Curb Ramp Winder & McKee | ADA Curb Ramp Winder & McKee | B16108 | Transportation & Storm Water | Design Bid Build | 346000 | 910799.9997 | FY20 | Q4 | FY21 | Q2
26 | Market Street Water Pipe Replacement | Market Street Water Pipe Replacement | B17052 | Public Utilities | Design Bid Build | 1528878.4973 | 1926448.4971 | FY20 | Q1 | FY21 | Q1
27 | Market Street Sewer Pipe Replacement | Market Street Sewer Pipe Replacement | B17054 | Public Utilities | Design Bid Build | 342554.8996 | 486972.8995 | FY20 | Q1 | FY21 | Q1
28 | Sewer and AC Water Group 1032 (S) | Sewer and AC Water Group 1032 (S) | B17104 | Public Utilities | Design Bid Build | 6388999.9907 | 8517999.9895 | FY20 | Q3 | FY21 | Q2
29 | Sewer and AC Water Group 1032 (W) | Sewer and AC Water Group 1032 (W) | B17105 | Public Utilities | Design Bid Build | 7070999.9937 | 9427999.992 | FY20 | Q3 | FY21 | Q2
30 | Mission Beach Water & Sewer Repl (W) | Mission Beach Water & Sewer Repl (W) | B17169 | Public Utilities | Design Bid Build | 13035279.9536 | 15336195.9536 | FY20 | Q3 | FY21 | Q3
31 | Mission Beach Water & Sewer Repl (S) | Mission Beach Water & Sewer Repl (S) | B17170 | Public Utilities | Design Bid Build | 2194514.9953 | 2641714.9953 | FY20 | Q3 | FY21 | Q3
32 | Intelligent Cities Outdoor Lightng Proj2 | Intelligent Cities Outdoor Lightng Proj2 | B18036 | Sustainability | Design Bid Build | 9000000 | 30000000 | FY20 | Q2 | FY21 | Q1
33 | Center City - New Traffic Signals | Center City - New Traffic Signals | B18083 | Transportation & Storm Water | Design Bid Build | 1345350 | 2152799.9993 | FY20 | Q3 | FY21 | Q1
34 | Alvarado TS Water Main Relocations | Alvarado TS Water Main Relocations | B18104 | Public Utilities | Design Bid Build | 9999999.9134 | 10438399.9128 | FY20 | Q3 | FY21 | Q2
35 | Accelerated Pipeline Rehab Ref Group 846 | Accelerated Pipeline Rehab Ref Group 846 | B18185 | Public Utilities | Design Bid Build | 1005500 | 1177588 | FY20 | Q4 | FY21 | Q3
36 | ADA APS Group 1E - Broadway PH 2 | ADA APS Group 1E - Broadway PH 2 | B18213 | Transportation & Storm Water | Design Bid Build | 80499.9997 | 149999.9997 | FY20 | Q3 | FY21 | Q3
37 | OB Dog Beach Accessibility Improvements | OB Dog Beach Accessibility Improvements | B19000 | Parks & Recreation | Job Order Contract | 759805.6666 | 1143305.6643 | FY20 | Q4 | FY21 | Q2
38 | Miramar Ranch North Paving G1 | Miramar Ranch North Paving G1 | B19007 | Transportation & Storm Water | Design Bid Build | 3925869.52 | 5080555.259 | FY20 | Q3 | FY21 | Q1
39 | SBWRP Variable Frequency Drive Repl | SBWRP Variable Frequency Drive Repl | B19066 | Public Utilities | Design Bid Build | 550000 | 955500 | FY20 | Q4 | FY21 | Q4
40 | Mingei Museum Dome Waterproofing | Mingei Museum Dome Waterproofing | B19067 | Parks & Recreation | Minor Contract | 295149.9999 | 360149.9999 | FY20 | Q1 | FY21 | Q1
41 | City Heights Pool Reconstruction | City Heights Pool Reconstruction | B19068 | Parks & Recreation | Design Bid Build | 5502229 | 6781681.9984 | FY20 | Q1 | FY21 | Q2
42 | Downtown Complete St Impl Phase 2 | Downtown Complete St Impl Phase 2 | B19143 | Transportation & Storm Water | Design Bid Build | 1792937.45 | 3461636.6174 | FY20 | Q2 | FY21 | Q1
43 | Tierrasanta Pool Stairway Replacement | Tierrasanta Pool Stairway Replacement | B20115 | Real Estate Assets | Job Order Contract | 222271 | 248416.25 | FY20 | Q3 | FY21 | Q2
44 | Island Ave Mini Park Improvements | Island Ave Mini Park Improvements | L16000.2 | Parks & Recreation | Design Bid Build | 2162000 | 3227649.9992 | FY20 | Q2 | FY21 | Q3
45 | J Street Mini Park Improvement | J Street Mini Park Improvement | L16000.6 | Parks & Recreation | Design Bid Build | 847913 | 1524999.9989 | FY20 | Q1 | FY21 | Q1
46 | Dennery Ranch Neighborhood Park | Dennery Ranch Neighborhood Park | S00636 | Parks & Recreation | Agency/ Developer Managed Built - City Paid | 5069999.9924 | 15099999.5226 | FY20 | Q1 | FY21 | Q3
47 | FAIRBROO K NEIGHBORHOOD PARK - DEVELOPMEN | FAIRBROO K NEIGHBORHOOD PARK - DEVELOPMEN | S01083 | Parks & Recreation | Design Bid Build | 3535353.53 | 6011281.4262 | FY20 | Q4 | FY21 | Q1
48 | La Jolla Village/I-805 Landscape Maint | La Jolla Village/I-805 Landscape Maint | S15017 | Transportation & Storm Water | Design Bid Build | 438069 | 610000 | FY20 | Q4 | FY21 | Q1
49 | Alvarado Trunk Sewer Phase IV | Alvarado Trunk Sewer Phase IV | S15019 | Public Utilities | Design Bid Build | 54999999.949 | 66999999.726 | FY20 | Q3 | FY21 | Q2
50 | Fire-Rescue Air Ops Facility - PH II | Fire-Rescue Air Ops Facility - PH II | S18007 | Fire-Rescue | Design Build | 1000000 | 22481000.29 | FY20 | Q2 | FY21 | Q2
51 | Pomerado Park Reservoir Upgrade | Pomerado Park Reservoir Upgrade | B00156 | Public Utilities | Design Bid Build | 4875000 | 6234999.9979 | FY21 | Q2 | FY21 | Q4
52 | North City Pure Water Facility | North City Pure Water Facility | B15139 | Public Utilities | Design Bid Build | 416828625 | 498601841.314 | FY21 | Q1 | FY21 | Q3
53 | Mid-City & Eastern Area Signal Mods | Mid-City & Eastern Area Signal Mods | B17128 | Transportation & Storm Water | Job Order Contract | 389085.999 | 1089999.9988 | FY22 | Q2 | FY21 | Q1
54 | Highland & Monroe Aves Storm Drain Repl | Highland & Monroe Aves Storm Drain Repl | B12096 | Transportation & Storm Water | Design Bid Build | 1585999.9759 | 2168870.9001 | FY21 | Q2 | FY21 | Q3
55 | North City Pure Water Pump Station | North City Pure Water Pump Station | B15140 | Public Utilities | Design Bid Build | 13350922 | 17617144.9973 | FY21 | Q1 | FY21 | Q3
56 | Storm Drain Group 968 | Storm Drain Group 968 | B15028 | Transportation & Storm Water | Design Bid Build | 131000 | 3810047 | FY21 | Q2 | FY21 | Q2
57 | Block 1M1 UUP (La Jolla) | Block 1M1 UUP (La Jolla) | B15084 | Transportation & Storm Water | Job Order Contract | 252449.9994 | 397000 | FY21 | Q2 | FY21 | Q2
58 | Block 6H UUP | Block 6H UUP | B15086 | Transportation & Storm Water | Job Order Contract | 350000 | 523000 | FY21 | Q2 | FY21 | Q3
59 | 7649 Shorewood Dr SD Repl Emergency | 7649 Shorewood Dr SD Repl Emergency | B20143 | Transportation & Storm Water | Emergency (As-needed) | 450000 | 750000 | FY20 | Q4 | FY21 | Q1
60 | 836 Gage Drive SD Replacement Emergency | 836 Gage Drive SD Replacement Emergency | B20109 | Transportation & Storm Water | Emergency (As-needed) | 600000 | 750000 | FY20 | Q3 | FY21 | Q1
61 | Morena Pump Station (Package A) | Morena Pump Station (Package A) | B15141 | Public Utilities | Design Bid Build | 93975000 | 342027971.6063 | FY21 | Q1 | FY21 | Q3
62 | Morena Pipelines - North (Package B3) | Morena Pipelines - North (Package B3) | B15141 | Public Utilities | Design Bid Build | 86345000 | 103626000 | FY21 | Q1 | FY21 | Q3
63 | ADA S/W Group 3E W Point Loma | ADA S/W Group 3E W Point Loma | B16100 | Transportation & Storm Water | Design Bid Build | 538000 | 1140199.9998 | FY21 | Q1 | FY21 | Q3
64 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | Fanuel St III (Grand-PB Dr) Rd Imp UU188 | B17071 | Transportation & Storm Water | Design Bid Build | 137121 | 221565 | FY21 | Q1 | FY21 | Q2
65 | El Cajon Bl-Highland-58th Improv | El Cajon Bl-Highland-58th Improv | B17003 | Transportation & Storm Water | Design Bid Build | 643000 | 1104999.9998 | FY21 | Q2 | FY21 | Q4
66 | San Vicente PH I-II Rd Imp UU505-UU506 | San Vicente PH I-II Rd Imp UU505-UU506 | B17098 | Transportation & Storm Water | Design Bid Build | 359483 | 961628.05 | FY21 | Q1 | FY21 | Q2
67 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | Howard PHI-II(Park-Texas) Rd Imp UU71-72 | B18136 | Transportation & Storm Water | Design Bid Build | 190910 | 389315.04 | FY21 | Q1 | FY21 | Q2
68 | Curb Ramp Improvement Group 1701 | Curb Ramp Improvement Group 1701 | B17114 | Transportation & Storm Water | Design Bid Build | 1130000 | 1829999.9985 | FY21 | Q2 | FY21 | Q3
69 | Sewer and AC Water Group 812 (W) | Sewer and AC Water Group 812 (W) | B17115 | Public Utilities | Design Bid Build | 1916000 | 4960265.5494 | FY21 | Q1 | FY21 | Q3
70 | Sewer and AC Water Group 763 (W) | Sewer and AC Water Group 763 (W) | B17116 | Public Utilities | Design Bid Build | 1972544.5 | 2305317.9961 | FY21 | Q1 | FY21 | Q4
71 | Wightman (Chamoune -Euclid) Rd Imp UU388 | Wightman (Chamoune -Euclid) Rd Imp UU388 | B18138 | Transportation & Storm Water | Design Bid Build | 123367.07 | 517829.54 | FY21 | Q1 | FY21 | Q2
72 | Torrey Pines Gf-Repr Storm Drain Outfall | Torrey Pines Gf-Repr Storm Drain Outfall | B17152 | Transportation & Storm Water | Design Bid Build | 2135000 | 3359999.9977 | FY21 | Q1 | FY21 | Q3
73 | Sewer Group 843 | Sewer Group 843 | B17189 | Public Utilities | Design Bid Build | 6127389 | 8022288.9842 | FY21 | Q2 | FY21 | Q2
74 | Asphalt Resurfacing Group 1901 | Asphalt Resurfacing Group 1901 | B18134 | Transportation & Storm Water | Design Bid Build | 9746100 | 10486046.07 | FY21 | Q2 | FY21 | Q2
75 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | Mission Bl(Loring-Turquoise) Rd Imp UU30 | B18140 | Transportation & Storm Water | Design Bid Build | 170777 | 1212543.95 | FY21 | Q1 | FY21 | Q2
76 | Golfcrest(Jackson-Wandermere)Rd ImpUU584 | Golfcrest(Jackson-Wandermere)Rd ImpUU584 | B18149 | Transportation & Storm Water | Design Bid Build | 221988 | 428008.8 | FY21 | Q1 | FY21 | Q2
77 | Hilltop PH I(Boundary-Toyne)Rd Imp UU617 | Hilltop PH I(Boundary-Toyne)Rd Imp UU617 | B18153 | Transportation & Storm Water | Design Bid Build | 235392 | 622463.2 | FY21 | Q1 | FY21 | Q2
78 | Concrete Street Panel Repl - Coast Bl | Concrete Street Panel Repl - Coast Bl | B20046 | Transportation & Storm Water | Design Bid Build | 829590.8485 | 1400655.8485 | FY21 | Q1 | FY21 | Q3
79 | Coast Cave SD Accelerated Replacement | Coast Cave SD Accelerated Replacement | B20076 | Transportation & Storm Water | Design Bid Build | 223094.9995 | 313422.9995 | FY21 | Q1 | FY21 | Q2
80 | Olive St Park Acquisition and Develpment | Olive St Park Acquisition and Develpment | S10051 | Parks & Recreation | Design Bid Build | 1983000 | 5171585 | FY21 | Q1 | FY21 | Q3
81 | Adult Fitness Course East Shore | Adult Fitness Course East Shore | B18223 | Parks & Recreation | Design Bid Build | 1060000 | 1953999.998 | FY21 | Q2 | FY21 | Q2
82 | Tecolote North Playground Improvements | Tecolote North Playground Improvements | B18232 | Parks & Recreation | Design Bid Build | 1469984 | 2964000 | FY21 | Q2 | FY21 | Q2
83 | Tecolote North Comfort Station Imp | Tecolote North Comfort Station Imp | B18233 | Parks & Recreation | Design Bid Build | 1639422 | 1962999.9978 | FY21 | Q2 | FY21 | Q2
84 | AC Overlay Group 2010 Peninsula | AC Overlay Group 2010 Peninsula | TBD | Transportation & Storm Water | Design Bid Build | 6871844.3182 | 8084522.7273 | FY21 | Q1 | FY21 | Q2
85 | Tecolote South Comfort Station Imp | Tecolote South Comfort Station Imp | B19015 | Parks & Recreation | Design Bid Build | 1608085 | 1930999.9988 | FY21 | Q2 | FY21 | Q2
86 | Tecolote South Playground Improvements | Tecolote South Playground Improvements | B19016 | Parks & Recreation | Design Bid Build | 2537976 | 3026999.9984 | FY21 | Q2 | FY21 | Q2
87 | Tecolote South Parking Lot Improvements | Tecolote South Parking Lot Improvements | B19017 | Parks & Recreation | Design Bid Build | 419282 | 527999.9997 | FY21 | Q2 | FY21 | Q2
88 | Bay Ho Improv 1 (S) | Bay Ho Improv 1 (S) | B19088 | Public Utilities | Design Bid Build | 5208400 | 7024799.9987 | FY21 | Q2 | FY21 | Q3
89 | AC Overlay Group 2011 Rancho Bernardo | AC Overlay Group 2011 Rancho Bernardo | TBD | Transportation & Storm Water | Design Bid Build | 6972675.5682 | 8203147.7273 | FY21 | Q1 | FY21 | Q2
90 | AC Overlay Group 2013 La Jolla Pkwy | AC Overlay Group 2013 La Jolla Pkwy | TBD | Transportation & Storm Water | Design Bid Build | 3778773.422 | 4445615.7906 | FY21 | Q1 | FY21 | Q2
91 | Chollas Crane Replacement | Chollas Crane Replacement | L14002.4 | Fleet Operations | Design Bid Build | 300000 | 554999.9995 | FY21 | Q2 | FY21 | Q3
92 | Chollas Paint Booth | Chollas Paint Booth | L14002.5 | Fleet Operations | Design Bid Build | 303000 | 665999.9994 | FY21 | Q2 | FY21 | Q3
93 | EMTS Boat Dock Esplanade | EMTS Boat Dock Esplanade | S00319 | Public Utilities | Design Bid Build | 2160379.9969 | 3332999.9907 | FY21 | Q2 | FY21 | Q3
94 | University Ave Mobility Plan | University Ave Mobility Plan | S00915 | Transportation & Storm Water | Design Bid Build | 5974533 | 9553349.6129 | FY21 | Q2 | FY21 | Q4
95 | La Paz Mini Park | La Paz Mini Park | S11103 | Parks & Recreation | Design Bid Build | 1502338 | 2602839.9999 | FY21 | Q2 | FY21 | Q4
96 | Convention Center Phase III Expansion | Convention Center Phase III Expansion | S12022 | Citywide | Construction Manager at Risk | 0 | 0 | FY21 | Q2 | FY21 | Q2
97 | Salk Neighborhood Park & Joint Use Devel | Salk Neighborhood Park & Joint Use Devel | S14007 | Parks & Recreation | Design Bid Build | 5576686 | 7237278.3035 | FY21 | Q2 | FY21 | Q3
98 | Water Group 968 | Water Group 968 | B14099 | Public Utilities | Design Bid Build | 2152300 | 5064806.4596 | FY21 | Q1 | FY21 | Q4
99 | Olive Grove Community Park ADA Improveme | Olive Grove Community Park ADA Improveme | S15028 | Parks & Recreation | Design Bid Build | 2386894.9992 | 3437267.999 | FY21 | Q2 | FY21 | Q3
100 | Harbor Drive Trunk Sewer Replacement | Harbor Drive Trunk Sewer Replacement | S18006 | Public Utilities | Design Bid Build | 14699999.945 | 21044999.938 | FY21 | Q2 | FY21 | Q2
101 | Sewer and AC Water Group 793 (S) | Sewer and AC Water Group 793 (S) | B00394 | Public Utilities | Design Bid Build | 5305291 | 6624610.9997 | FY21 | Q2 | FY21 | Q4
102 | Fanuel St PI Archer to Tourmaline UUD | Fanuel St PI Archer to Tourmaline UUD | B00721 | Transportation & Storm Water | Job Order Contract | 90344 | 142046.9999 | FY20 | Q3 | FY21 | Q1
103 | Water & Sewer Group 965 (S) | Water & Sewer Group 965 (S) | B12048 | Public Utilities | Design Bid Build | 1855399.9945 | 2932599.9942 | FY21 | Q2 | FY21 | Q4
104 | Water & Sewer Group 965 (W) | Water & Sewer Group 965 (W) | B12057 | Public Utilities | Design Bid Build | 1769499.9913 | 2934599.991 | FY21 | Q2 | FY21 | Q4
105 | Adams Ave (1620) Storm Drain Replacement | Adams Ave (1620) Storm Drain Replacement | B13102 | Transportation & Storm Water | Design Bid Build | 499999.9832 | 1059999.9868 | FY21 | Q2 | FY21 | Q4
106 | Navajo Storm Drains | Navajo Storm Drains | B15029 | Transportation & Storm Water | Design Bid Build | 2100399.9866 | 3266408.9865 | FY21 | Q2 | FY21 | Q4
107 | Logan Heights LID (South) | Logan Heights LID (South) | B15051 | Transportation & Storm Water | Design Bid Build | 3705000 | 5315999.9947 | FY21 | Q2 | FY21 | Q4
108 | NCWRP Expansion | NCWRP Expansion | B15142 | Public Utilities | Design Bid Build | 123741147.975 | 159419445.975 | FY21 | Q2 | FY21 | Q4
109 | Pressure Reducing Stations Upgrades Phs1 | Pressure Reducing Stations Upgrades Phs1 | B16017 | Public Utilities | Design Bid Build | 3739999.9907 | 6289999.9889 | FY21 | Q2 | FY21 | Q3
110 | North City Pure Water Pipeline | North City Pure Water Pipeline | B16035 | Public Utilities | Design Bid Build | 87680000 | 102239038.9885 | FY21 | Q2 | FY21 | Q4
111 | North City Pure Water Subaqueous Pipeline | North City Pure Water Subaqueous Pipeline | B16035 | Public Utilities | Design Bid Build | 5270000 | 7000000 | FY21 | Q2 | FY21 | Q4
112 | Southcrest Green Infrastructure (GI) | Southcrest Green Infrastructure (GI) | B16112 | Transportation & Storm Water | Design Bid Build | 3055400 | 4600000 | FY21 | Q2 | FY21 | Q4
113 | NCPWF Influent Pump Station and Pipeline | NCPWF Influent Pump Station and Pipeline | B16140 | Public Utilities | Design Bid Build | 29218850.8541 | 38413733.849 | FY21 | Q2 | FY21 | Q4
114 | Asphalt Resurfacing Group 1902 | Asphalt Resurfacing Group 1902 | B18135 | Transportation & Storm Water | Design Bid Build | 2552801.1364 | 3003295.4545 | FY21 | Q1 | FY21 | Q2
115 | Governor Dr @ Lakewood St Traffic Signal | Governor Dr @ Lakewood St Traffic Signal | B17016 | Transportation & Storm Water | Design Bid Build | 275700 | 460000 | FY21 | Q3 | FY21 | Q4
116 | Clairemont Mesa Sewer Pipe Replacement | Clairemont Mesa Sewer Pipe Replacement | B17087 | Public Utilities | Design Bid Build | 186000 | 346099.9998 | FY21 | Q2 | FY21 | Q4
117 | Balboa Park Pipeline Repl Ph II (S) | Balboa Park Pipeline Repl Ph II (S) | B17133 | Public Utilities | Design Bid Build | 1851999.9979 | 1730068.9996 | FY21 | Q2 | FY21 | Q4
118 | Balboa Park Pipeline Repl Ph II (W) | Balboa Park Pipeline Repl Ph II (W) | B17140 | Public Utilities | Design Bid Build | 3789999.9957 | 8041635.9934 | FY21 | Q2 | FY21 | Q4
119 | AC Water Group 1038 | AC Water Group 1038 | B17153 | Public Utilities | Design Bid Build | 22286633.9996 | 29568477.9958 | FY21 | Q2 | FY21 | Q4
120 | Street Reconstruction Group 1801 | Street Reconstruction Group 1801 | B17188 | Transportation & Storm Water | Design Bid Build | 8200000 | 12709999.996 | FY21 | Q2 | FY21 | Q3
121 | Sherman Height Community Center Playground | Sherman Height Community Center Playground | B18006 | Parks & Recreation | Design Bid Build | 350000 | 697471.2486 | FY21 | Q2 | FY21 | Q4
122 | Convert Bldg 619 @ NTC into Rec Center | Convert Bldg 619 @ NTC into Rec Center | B18087 | Parks & Recreation | Design Bid Build | 3578999.9926 | 6227999.9895 | FY21 | Q2 | FY21 | Q4
123 | AC Water & Sewer Group 1051 (W) | AC Water & Sewer Group 1051 (W) | B18091 | Public Utilities | Design Bid Build | 776299.9962 | 1004599.9962 | FY21 | Q2 | FY21 | Q4
124 | AC Water & Sewer Group 1051 (S) | AC Water & Sewer Group 1051 (S) | B18098 | Public Utilities | Design Bid Build | 3136599.9908 | 4059099.9908 | FY21 | Q2 | FY21 | Q4
125 | AC Water & Sewer Group 1036 (W) | AC Water & Sewer Group 1036 (W) | B18121 | Public Utilities | Design Bid Build | 3322800 | 4300100 | FY21 | Q2 | FY21 | Q4
126 | Coronado SB (27th SB-Madden)Rd Imp UU193 | Coronado SB (27th SB-Madden)Rd Imp UU193 | B18137 | Transportation & Storm Water | Design Bid Build | 268212.8 | 337203.2 | FY21 | Q2 | FY21 | Q4
127 | 32nd St PHII (Market-Imp.) Rd Imp UU17 | 32nd St PHII (Market-Imp.) Rd Imp UU17 | B18141 | Transportation & Storm Water | Design Bid Build | 268212.8 | 350089.2 | FY21 | Q2 | FY21 | Q4
128 | Block 6DD1 (Clairemont Mesa)Rd Imp UU410 | Block 6DD1 (Clairemont Mesa)Rd Imp UU410 | B18142 | Transportation & Storm Water | Design Bid Build | 1473215 | 1959763.9994 | FY21 | Q2 | FY21 | Q4
129 | 32nd St PH I (Market-F St) Rd Imp UU386 | 32nd St PH I (Market-F St) Rd Imp UU386 | B18144 | Transportation & Storm Water | Design Bid Build | 124122.35 | 159997.75 | FY21 | Q2 | FY21 | Q4
130 | 31st Street (Market-L ST) Rd Imp UU11 | 31st Street (Market-L ST) Rd Imp UU11 | B18147 | Transportation & Storm Water | Design Bid Build | 286745 | 366701.9999 | FY21 | Q2 | FY21 | Q4
131 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 | Cass (Grand-Pacific Bch Dr) Rd Imp UU143 | B18148 | Transportation & Storm Water | Design Bid Build | 109924 | 172018.7 | FY21 | Q2 | FY21 | Q4
132 | 25th (SB) (Coronado-Grove) Rd Imp UU995 | 25th (SB) (Coronado-Grove) Rd Imp UU995 | B18150 | Transportation & Storm Water | Design Bid Build | 88173 | 131599 | FY21 | Q2 | FY21 | Q4
133 | Hughes St (58th St-Jodi St) Rd Imp UU101 | Hughes St (58th St-Jodi St) Rd Imp UU101 | B18151 | Transportation & Storm Water | Design Bid Build | 208247 | 276934.9999 | FY21 | Q2 | FY21 | Q4
134 | Block 1M (La Jolla 4) Rd Imp UU659 | Block 1M (La Jolla 4) Rd Imp UU659 | B18155 | Transportation & Storm Water | Design Bid Build | 817563 | 1135146.1999 | FY21 | Q3 | FY21 | Q4
135 | ADACA Woodman St-Cielo to Pagel PL Sidwl | ADACA Woodman St-Cielo to Pagel PL Sidwl | B18159 | Transportation & Storm Water | Design Bid Build | 525260.9998 | 1001420.9997 | FY21 | Q2 | FY21 | Q4
136 | Talmadge AC Water Main Replacement | Talmadge AC Water Main Replacement | B18197 | Public Utilities | Design Bid Build | 814100 | 2138080.9999 | FY21 | Q2 | FY21 | Q4
137 | DeAnza North Parking Lot Improvements | DeAnza North Parking Lot Improvements | B18220 | Parks & Recreation | Design Bid Build | 579000 | 870166.9999 | FY21 | Q3 | FY21 | Q3
138 | Tecolote North Parking Lot Improvements | Tecolote North Parking Lot Improvements | B18231 | Parks & Recreation | Design Bid Build | 706160 | 868999.9991 | FY21 | Q2 | FY21 | Q2
139 | Santa Clara Playground Improvements | Santa Clara Playground Improvements | B19029 | Parks & Recreation | Design Bid Build | 1377008.9948 | 1959999.9849 | FY21 | Q2 | FY21 | Q4
140 | Santa Clara Comfort Station Improvements | Santa Clara Comfort Station Improvements | B19032 | Parks & Recreation | Design Bid Build | 506136.9989 | 749999.9987 | FY21 | Q2 | FY21 | Q4
141 | Linda Vista Skate Park Phase 2 | Linda Vista Skate Park Phase 2 | B19062 | Parks & Recreation | Job Order Contract | 168699.9999 | 348899.9997 | FY21 | Q2 | FY21 | Q4
142 | Accelerated MH Referral Group 1 | Accelerated MH Referral Group 1 | B19097 | Public Utilities | Design Bid Build | 515000 | 741979.9999 | FY21 | Q2 | FY21 | Q4
143 | Citywide Street Lights 1950 | Citywide Street Lights 1950 | B19125 | Transportation & Storm Water | Job Order Contract | 1350000 | 1490000 | FY21 | Q2 | FY21 | Q2
144 | Sewer Rehab 1051A | Sewer Rehab 1051A | B19145 | Public Utilities | Design Bid Build | 126199.9994 | 178199.9993 | FY21 | Q2 | FY21 | Q4
145 | AC Water and Sewer Group 1052A (W) | AC Water and Sewer Group 1052A (W) | B19166 | Public Utilities | Multiple Award Construction Contract | 3502400 | 5182899.8347 | FY21 | Q2 | FY21 | Q4
146 | AC Water & Sewer Group 1052A (S) | AC Water & Sewer Group 1052A (S) | B19169 | Public Utilities | Multiple Award Construction Contract | 1923000 | 2814099.9097 | FY21 | Q2 | FY21 | Q4
147 | Point Loma Library Chiller Replacement | Point Loma Library Chiller Replacement | B19203 | Library | Job Order Contract | 166000 | 279999.9999 | FY21 | Q2 | FY21 | Q3
148 | Balboa Park Golf Course - Bathroom Remod | Balboa Park Golf Course - Bathroom Remod | B20064 | Parks & Recreation | Job Order Contract | 61999.9999 | 128999.9999 | FY21 | Q2 | FY21 | Q4
149 | Miramar Landfill Trailer Replacements | Miramar Landfill Trailer Replacements | L17000.6 | Environmental Services | Design Build | 300000 | 400000 | FY21 | Q2 | FY21 | Q3
150 | Chollas Lake Electrical Upgrade | Chollas Lake Electrical Upgrade | L18001.1 | Parks & Recreation | Design Bid Build | 424000 | 850000 | FY21 | Q2 | FY21 | Q4
151 | Miramar Landfill Storm Water Basin Improvements | Miramar Landfill Storm Water Basin Improvements | L18002.3 | Environmental Services | Design Bid Build | 6000000 | 8000000 | FY21 | Q2 | FY21 | Q3
152 | Hickman Fields Athletic Area | Hickman Fields Athletic Area | S00751 | Parks & Recreation | Design Bid Build | 7200000 | 9566317.7193 | FY21 | Q2 | FY21 | Q3
153 | El Monte Pipeline No. 2 | El Monte Pipeline No. 2 | S10008 | Public Utilities | Design Bid Build | 17900000 | 24499999.9871 | FY21 | Q2 | FY21 | Q4
154 | Cielo & Woodman Pump Station | Cielo & Woodman Pump Station | S12012 | Public Utilities | Design Bid Build | 4678000 | 6677999.9978 | FY21 | Q2 | FY21 | Q4
155 | Alvarado 2nd Extension Pipeline | Alvarado 2nd Extension Pipeline | S12013 | Public Utilities | Design Bid Build | 65209999.9674 | 102648544.9081 | FY21 | Q2 | FY21 | Q4
156 | Wangenheim Joint Use Facility | Wangenheim Joint Use Facility | S15007 | Parks & Recreation | Design Bid Build | 6386395.9986 | 9517666.9971 | FY21 | Q2 | FY21 | Q3
157 | Fire Station 48 | Fire Station 48 | S15015 | Fire-Rescue | Design Build | 11137500 | 15091000 | FY21 | Q2 | FY21 | Q4
158 | Carmel Del Mar NP Comfort Station - Dev | Carmel Del Mar NP Comfort Station - Dev | S16034 | Parks & Recreation | Design Bid Build | 1519563.9997 | 2330563.9995 | FY21 | Q3 | FY21 | Q4
159 | Talmadge Traffic Calming Infrastructure | Talmadge Traffic Calming Infrastructure | S17001 | Parks & Recreation | Design Bid Build | 173937.9998 | 309999.999 | FY21 | Q2 | FY21 | Q4
160 | Kearny Mesa Pipeline Manway | Kearny Mesa Pipeline Manway | B20072 | Public Utilities | Design Bid Build | 330000 | 492700 | FY21 | Q3 | FY21 | Q4
161 | Water Group Job 952 | Water Group Job 952 | B11048 | Public Utilities | Design Bid Build | 5300000 | 7393193.9956 | FY21 | Q3 | FY21 | Q4
162 | Pipeline Rehabilitation AY-1 | Pipeline Rehabilitation AY-1 | B18212 | Public Utilities | Design Bid Build | 6561800 | 7841499.972 | FY21 | Q2 | FY21 | Q3
163 | Citywide Street Lights Group 1702 | Citywide Street Lights Group 1702 | B17051 | Transportation & Storm Water | Job Order Contract | 441199.9997 | 749144.1997 | FY21 | Q2 | FY21 | Q4
164 | Plumosa Park Series Circuit Conversion | Plumosa Park Series Circuit Conversion | B17101 | Transportation & Storm Water | Job Order Contract | 765000 | 1450000 | FY21 | Q3 | FY21 | Q4
165 | Ingulf St (Morena Bl-Erie St) SL UU123 | Ingulf St (Morena Bl-Erie St) SL UU123 | B18126 | Transportation & Storm Water | Job Order Contract | 24200 | 78000 | FY20 | Q3 | FY21 | Q1
166 | Orange Av PH3 Central-Fairmont SL UU24 | Orange Av PH3 Central-Fairmont SL UU24 | B18130 | Transportation & Storm Water | Job Order Contract | 53200 | 207600 | FY20 | Q3 | FY21 | Q2
167 | Thermal Ave - Donax Ave to Palm Ave Sidewalk | Thermal Ave - Donax Ave to Palm Ave Sidewalk | B18157 | Transportation & Storm Water | Design Bid Build | 1270300 | 1609099.9998 | FY21 | Q3 | FY21 | Q4
168 | Sidewalk Replacement Group 1903-SE & CH | Sidewalk Replacement Group 1903-SE & CH | B19014 | Transportation & Storm Water | Design Bid Build | 1000000 | 1649007.4795 | FY21 | Q3 | FY21 | Q4
169 | Downtown Complete St Impl Phase 3A | Downtown Complete St Impl Phase 3A | B19144 | Transportation & Storm Water | Design Bid Build | 4230000 | 6999999.999 | FY21 | Q3 | FY21 | Q4
170 | Rose Marie Starns Parking Lot Imprvemts | Rose Marie Starns Parking Lot Imprvemts | B19163 | Parks & Recreation | Design Bid Build | 1922000 | 2869999.9995 | FY21 | Q3 | FY21 | Q4
171 | Chollas Large Car Washes | Chollas Large Car Washes | L14002.3 | Fleet Operations | Design Bid Build | 1650000 | 2748369.9978 | FY21 | Q3 | FY21 | Q4
172 | PD Substation Small Carwashes | PD Substation Small Carwashes | L14002.6 | Fleet Operations | Design Bid Build | 2200000 | 3488515.9976 | FY21 | Q3 | FY21 | Q4
173 | SCRIPPS MIRAMAR RANCH LIB | SCRIPPS MIRAMAR RANCH LIB | S00811 | Library | Design Bid Build | 4270000 | 6076376.9181 | FY21 | Q3 | FY21 | Q4
174 | Cañon Street Pocket Park | Cañon Street Pocket Park | S16047 | Parks & Recreation | Design Bid Build | 1224349.9996 | 2567314.8994 | FY21 | Q3 | FY21 | Q4
175 | University Ave Complete Street | University Ave Complete Street | S18001 | Transportation & Storm Water | Design Bid Build | 4838300 | 7229399.9889 | FY21 | Q3 | FY21 | Q4
176 | AC Water & Sewer Group 1056 (W) | AC Water & Sewer Group 1056 (W) | B18181 | Public Utilities | Design Bid Build | 8535299.9968 | 11045699.9968 | FY21 | Q2 | FY21 | Q4
177 | AC Water & Sewer Group 1056 (S) | AC Water & Sewer Group 1056 (S) | B18182 | Public Utilities | Design Bid Build | 181799.9999 | 241699.9999 | FY21 | Q2 | FY21 | Q4
178 | Torrey Highlands NP Upgrades | Torrey Highlands NP Upgrades | S16036 | Parks & Recreation | Design Bid Build | 659999.9996 | 1027937.3911 | FY21 | Q2 | FY21 | Q2
179 | Mountain View Sports Courts | Mountain View Sports Courts | B18192 | Parks & Recreation | Job Order Contract | 542000 | 1251999.9998 | FY21 | Q1 | FY21 | Q2
180 | Balboa Park Pipeline Repl Ph III (W) | Balboa Park Pipeline Repl Ph III (W) | B17141 | Public Utilities | Design Bid Build | 3010000 | 5004135.2863 | FY20 | Q3 | FY21 | Q4
181 | Balboa Park Pipeline Repl Ph III (S) | Balboa Park Pipeline Repl Ph III (S) | B17134 | Public Utilities | Design Bid Build | 1213000 | 1998499.619 | FY21 | Q3 | FY21 | Q4
182 | MLK Rec Center Moisture Intrusion | MLK Rec Center Moisture Intrusion | B19001 | Parks & Recreation | Design Bid Build | 1020093 | 2439819.998 | FY21 | Q1 | FY21 | Q3
183 | San Diego Av (Old Town-McKee) SL UU598 | San Diego Av (Old Town-McKee) SL UU598 | B20045 | Transportation & Storm Water | Job Order Contract | 82200 | 333600 | FY20 | Q3 | FY21 | Q2
184 | Pacific Highlands Ranch Branch Library | Pacific Highlands Ranch Branch Library | S14023 | Library | Design Bid Build | 17443915 | 26164178 | FY21 | Q1 | FY21 | Q3
185 | Seminole PH2 (El Cajon-Stanley) SL UU630 | Seminole PH2 (El Cajon-Stanley) SL UU630 | B17013 | Transportation & Storm Water | Job Order Contract | 108000 | 269999.9997 | FY21 | Q1 | FY21 | Q1
186 | Citywide Street Lights Group 1801 | Citywide Street Lights Group 1801 | B18012 | Transportation & Storm Water | Design Bid Build | 120000 | 207238 | FY21 | Q2 | FY21 | Q3
187 | Block 3DD (Adams North) SL UU908 | Block 3DD (Adams North) SL UU908 | B20050 | Transportation & Storm Water | To Be Determined | 279399.9988 | 843999.9988 | FY21 | Q3 | FY21 | Q3
188 | University of SD FH/FS Reconnection | University of SD FH/FS Reconnection | B20136 | Public Utilities | Job Order Contract | 209479.8399 | 234479.8399 | FY21 | Q1 | FY21 | Q2
189 | Civita Franklin Ridge | Civita Franklin Ridge | 240033323 | Parks & Recreation | Agency/ Developer Managed Built Paid | 71000 | 223183.64 | FY21 | Q2 | FY21 | Q4
|  |  | 189 CIP Projects |  |  | 1449412990.2927 | 2162077005.0456

## Summary Table
Summary by Asset - Managing Departments
Asset - Managing Department | Estimated Construction Contract Award | Estimated Total Project Cost
Transportation & Storm Water | 86371599.8364 | 141416272.7791
Library | 21879915 | 32520554.918
Public Utilities | 93878000 | 113534950
Transportation & Storm Water | 50990779.002 | 59839217.8326
Parks & Recreation | 74679998.1712 | 121907285.5559
Public Utilities | 1089499927.2831 | 1609180421.4257
Sustainability | 9000000 | 30000000
Real Estate Assets | 222271 | 248416.25
Fire-Rescue | 12137500 | 37572000.29
Fleet Operations | 4453000 | 7457885.9943
Citywide | 0 | 0
Environmental Services | 6300000 | 8400000
FY 2021 Total | 1449412990.2927 | 2162077005.0456

## ESRI_MAPINFO_SHEET (hidden)
DO NOT EDIT
For Esri use only